## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | SM/06779 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte.(Part-A) | AE/SADAR |  | ORD/000123/2020-2021 | 1533/HD | 05/11/2020 | 05/12/2020 | ALOK ENTERPRISE A UNIT OF SAKET TREXIM PVT. LTD. | 18.84 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | SM/06779 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte.(Part-B) | AE/SADAR |  | ORD/000124/2020-2021 | 1534/HD | 05/11/2020 | 05/12/2020 | ALOK ENTERPRISE A UNIT OF SAKET TREXIM PVT. LTD. | 18.84 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | SM/06779 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte.(Part-C) | AE/SADAR |  | ORD/000125/2020-2021 | 1535/HD | 05/11/2020 | 05/12/2020 | ALOK ENTERPRISE A UNIT OF SAKET TREXIM PVT. LTD. | 18.84 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | SM/06779 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000876/2020-2021 | 844356 | 23/03/2021 | 23/03/2021 | BUILT INDIA | 15.55 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | SM/06779 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000373/2021-2022 | 844345 | 28/09/2021 | 28/09/2021 | UNIQUE AGENCY | 9.35 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | SM/06779 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000371/2021-2022 | 844343 | 28/09/2021 | 28/09/2021 | RAKESH ENTERPRISE | 4.11 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | SM/06779 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000774/2020-2021 | 84431 | 01/03/2021 | 01/03/2021 | UNIQUE AGENCY | 16.13 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | SM/06779 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000775/2020-2021 | 84432 | 01/03/2021 | 01/03/2021 | UNIQUE AGENCY | 16.15 | 0 | 0 | 0
9 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | SM/06779 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000211/2021-2022 | W/217 | 18/08/2021 | 18/08/2021 | ALOK ENTERPRISE | 16.11 | 0 | 0 | 0
10 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) | SM/06779 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | ORD/000925/2020-2021 | 627/21/2022 | 15/08/2020 | 15/08/2020 | RAKESH ENTERPRISE | 4.35 | 2.9 | 66.66 | 0
Total | [13 empty] | 138.27 | 2.9 | 2.1