## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II | SM/06780 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte.(Part-D) | AE/SADAR |  | ORD/000126/2020-2021 | 1536/HD | 05/11/2020 | 05/12/2020 | JDJ ENTERPRISE A UNIT OF JDJ TRADERS PRIVATE LIMITED | 18.83 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II | SM/06780 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Part-F | AE/SADAR |  | ORD/000128/2020-2021 | 1538/HD | 05/11/2020 | 05/12/2020 | BUILT INDIA | 18.12 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II | SM/06780 | Retrofitting | Laying of 50 mm & 75 mm dia.,Total 1948 mtr. Length additional UPVC pipe line for Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Command area of Gobindapur PWSS at Howrah Sadar Sub Division under howrah Division , PHE Dte. (Phase-II) (Part-M) | AE/SADAR |  | ORD/000082/2021-2022 | 1434/HD | 13/07/2021 | 12/08/2021 | A.P. POWER & CONCRETE | 4.8 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II | SM/06780 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte.(Part-E) | AE/SADAR |  | ORD/000127/2020-2021 | 1537/HD | 05/11/2020 | 05/12/2020 | BUILT INDIA | 18.06 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II | SM/06780 | Retrofitting | Laying of 90 mm dia 470 mtr. Length additional UPVC pipe line for Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Command area of Gobindapur PWSS at Howrah Sadar Sub Division under howrah Division , PHE Dte. (Phase-II) (Part-O) | AE/SADAR |  | ORD/000084/2021-2022 | 1436HD | 13/07/2021 | 12/08/2021 | BUILT INDIA | 2.41 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II | SM/06780 | Retrofitting | Laying of 63 mm dia. 1615 mtr. Length additional UPVC pipe line for Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Command area of Gobindapur PWSS at Howrah Sadar Sub Division under howrah Division , PHE Dte. (Phase-II) (Part-N) | AE/SADAR |  | ORD/000083/2021-2022 | 1435HD | 13/07/2021 | 12/08/2021 | A.P. POWER & CONCRETE | 4.31 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II | SM/06780 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Gobindapur PWSS at Howrah Sub Division under Howrah Division , PHE Dte. | AE/SADAR |  | ORD/000089/2021-2022 | 1441/HD | 13/07/2021 | 12/08/2021 | MONIRUL ISLAM | 4.76 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II | SM/06780 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-II) (Part-V) | AE/SADAR |  | ORD/000085/2021-2022 | 1437HD | 13/07/2021 | 12/08/2021 | MONIRUL ISLAM | 4.27 | 0 | 0 | 0
9 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II | SM/06780 | Retrofitting | Laying of 50 mm ,63 mm & 75 mm dia. 110mm dia 125mm dia,Total 1034 mtr. Length additional UPVC pipe line for Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Command area of Gobindapur PWSS at Howrah Sadar Sub Division under howrah Division , PHE Dte. (Phase-II) (Part-S) | AE/SADAR |  | ORD/000088/2021-2022 | 1440/HD | 13/07/2021 | 12/08/2021 | BUILT INDIA | 3.34 | 0 | 0 | 0
10 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II | SM/06780 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under J.B.Pur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-II) (Part-X) | AE/SADAR |  | ORD/000086/2021-2022 | 1438/HD | 13/07/2021 | 12/08/2021 | BUILT INDIA | 4.34 | 0 | 0 | 0
11 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II | SM/06780 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under J.B Pur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-II) (Part-W) | AE/SADAR |  | ORD/000087/2021-2022 | 1439/HD | 13/07/2021 | 12/08/2021 | BUILT INDIA | 2.61 | 0 | 0 | 0
12 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II | SM/06780 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Gobindapur piped water supply scheme under J.B.Pur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-II) (Part-L) | AE/SADAR |  | ORD/000081/2021-2022 | 1433/HD | 13/07/2021 | 12/08/2021 | A.P. POWER & CONCRETE | 4.79 | 0 | 0 | 0
13 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II | SM/06780 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000876/2020-2021 | 844356 | 23/03/2021 | 23/03/2021 | BUILT INDIA | 15.55 | 0 | 0 | 0
14 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II | SM/06780 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000480/2021-2022 | W/428 | 08/10/2021 | 08/10/2021 | A.P. POWER & CONCRETE | 4 | 0 | 0 | 0
15 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II | SM/06780 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000864/2020-2021 | 844357 | 23/03/2021 | 23/03/2021 | BUILT INDIA | 15.66 | 0 | 0 | 0
16 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II | SM/06780 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000473/2021-2022 | W/427 | 08/10/2021 | 08/10/2021 | A.P. POWER & CONCRETE | 8.92 | 0 | 0 | 0
17 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II | SM/06780 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000527/2021-2022 | 84439 | 16/11/2021 | 16/11/2021 | A.P. POWER & CONCRETE | 1.43 | 0 | 0 | 0
18 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II | SM/06780 | Retrofitting | Work Order for Retrofitting work for Supply, delivery & installation of CIDF Sluice Valve in different Node point and construction of Sluice Valve chamber for providing Functional Household Tap Connection (FHTC) from existing distribution system of Gobindapur PWSS under Howrah Sub Division of Howrah Division , PHE Dte. | AE/SADAR |  | ORD/000426/2021-2022 | 340/HD | 17/02/2022 | 19/03/2022 | MONIRUL ISLAM | 4.77 | 0 | 0 | 0
19 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II | SM/06780 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under J.B Pur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-II) (Part-W) |  |  | VCH/000852/2021-2022 | 844315 | 17/03/2022 | 17/03/2022 | BUILT INDIA | 2.57 | 0 | 0 | 0
20 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II | SM/06780 | Retrofitting | Retrofitting Gobindapur W/S Scheme. |  |  | VCH/000876/2021-2022 | 844334 | 30/03/2022 | 30/03/2022 | ALOK ENTERPRISE | 15.52 | 0 | 0 | 0
21 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II | SM/06780 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000645/2021-2022 | 844318 | 20/01/2022 | 20/01/2022 | MS ARPAN ENTERPRISE | 4.26 | 0 | 0 | 0
22 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II | SM/06780 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | ORD/000925/2020-2021 | 627/21/2022 | 15/08/2020 | 15/08/2020 | RAKESH ENTERPRISE | 4.35 | 1.45 | 33.34 | 0
23 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II | SM/06780 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | ORD/000926/2020-2021 | 27/21/2022 | 15/08/2020 | 15/08/2020 | BUILT INDIA | 1.77 | 1.77 | 100 | 0
24 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-II | SM/06780 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | ORD/000916/2020-2021 | 645/21/2022 | 15/08/2020 | 15/08/2020 | BUILT INDIA | 11.53 | 11.53 | 100 | 0
Total | [13 empty] | 181 | 14.75 | 8.15