## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-III) | SM/06781 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Part-G) | AE/SADAR |  | ORD/000121/2020-2021 | 1539/HD | 05/11/2020 | 05/12/2020 | UNIQUE AGENCY | 18.89 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-III) | SM/06781 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Part-H) | AE/SADAR |  | ORD/000122/2020-2021 | 1540/HD | 05/11/2020 | 05/12/2020 | UNIQUE AGENCY | 18.88 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-III) | SM/06781 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Part-I) | AE/SADAR |  | ORD/000129/2020-2021 | 1541/HD | 05/11/2020 | 05/12/2020 | A P POWER & CONCRETE | 18.85 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-III) | SM/06781 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000949/2020-2021 | 8443116 | 30/03/2021 | 30/03/2021 | MONIRUL ISLAM | 4.71 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-III) | SM/06781 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000932/2020-2021 | 8443103 | 30/03/2021 | 30/03/2021 | A.P. POWER & CONCRETE | 16.16 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-III) | SM/06781 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000645/2021-2022 | 844318 | 20/01/2022 | 20/01/2022 | MS ARPAN ENTERPRISE | 4.26 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-III) | SM/06781 | Retrofitting | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000648/2021-2022 | 844321 | 20/01/2022 | 20/01/2022 | MONIRUL ISLAM | 4.31 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-III) | SM/06781 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under J.B.Pur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-II) (Part-X) |  |  | VCH/000853/2021-2022 | 844317 | 21/03/2022 | 21/03/2022 | BUILT INDIA | 4.07 | 0 | 0 | 0
9 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-III) | SM/06781 | Retrofitting | Retrofitting Gobindapur W/S Scheme. |  |  | VCH/000876/2021-2022 | 844334 | 30/03/2022 | 30/03/2022 | ALOK ENTERPRISE | 15.52 | 0 | 0 | 0
10 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-III) | SM/06781 | Retrofitting | Mass Awarness generation and IEC activities. |  |  | VCH/000611/2021-2022 | 844313 | 23/12/2021 | 23/12/2021 | PRADIP KUMAR JATI | 42 | 0 | 0 | 0
11 | HOWRAH |  | Howrah Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-III) | SM/06781 | Retrofitting | Work Order for Laying of additional UPVC pipe line of 75 mm & 110mm dia,Total 450 mtr. Length for Retrofitting work for providing Functional Household Tap Connection (FHTC) including school, anganwari & other establishments like temple, mosque, govt. premises, mela ground, public toilets etc. within the Command area of Gobindapur PWSS under Howrah Sadar Sub Division of Howrah Division , PHE Dte. (Phase-III) | AE/SADAR |  | ORD/000424/2021-2022 | 338/HD | 17/02/2022 | 19/03/2022 | BUILT INDIA | 2.52 | 0 | 0 | 0
Total | [13 empty] | 150.17 | 0 | 0