## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply scheme (Phase-I) | SM/06783 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Balichak piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-B) (for Dhurkhali Mouza part) | AE/Ulu |  | ORD/000159/2020-2021 | 1622/HD | 09/11/2020 | 09/12/2020 | GHOSH CONCERN | 28.9 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply scheme (Phase-I) | SM/06783 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Balichak piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-A) (for Purba Bajepratap Mouza) | AE/Ulu |  | ORD/000158/2020-2021 | 1621/HD | 09/11/2020 | 09/12/2020 | GHOSH CONCERN | 25.92 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply scheme (Phase-I) | SM/06783 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Balichak piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-C) (for Dhurkhali Mouza part) | AE/Ulu |  | ORD/000160/2020-2021 | 1623/HD | 09/11/2020 | 09/12/2020 | N. G ENGINEERING | 22.81 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply scheme (Phase-I) | SM/06783 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply scheme. |  |  | VCH/000953/2020-2021 | 8443107 | 30/03/2021 | 30/03/2021 | P B ENTERPRISE | 23.52 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply scheme (Phase-I) | SM/06783 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply scheme. |  |  | VCH/000756/2020-2021 | 844334 | 25/02/2021 | 25/02/2021 | GHOSH CONCERN | 25.85 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply scheme (Phase-I) | SM/06783 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply Scheme. |  |  | VCH/000872/2020-2021 | 844329 | 17/03/2021 | 17/03/2021 | M/S CHANDIMATA CONSTRUCTION | 18.39 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply scheme (Phase-I) | SM/06783 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply Scheme. |  |  | VCH/000776/2020-2021 | 84433 | 01/03/2021 | 01/03/2021 | P B ENTERPRISE | 27.61 | 0 | 0 | 0
Total | [13 empty] | 173.02 | 0 | 0