## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Balichak and Banuchak mouza of Balichak piped water supply scheme (Phase-II) | SM/06784 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Balichak piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-E) for Balichak mouza part) | AE/Ulu | JE/USD | ORD/000162/2020-2021 | 1625/HD | 09/11/2020 | 09/12/2020 | P B ENTERPRISE | 26.26 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Balichak and Banuchak mouza of Balichak piped water supply scheme (Phase-II) | SM/06784 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Balichak piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-D) (for Banuchak mouza) | AE/Ulu | JE/USD | ORD/000161/2020-2021 | 1624/HD | 09/11/2020 | 09/12/2020 | M/S. CHANDIMATA CONSTRUCTION | 18.4 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Balichak and Banuchak mouza of Balichak piped water supply scheme (Phase-II) | SM/06784 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Balichak piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-F) for Balichak mouza part) | AE/Ulu | JE/USD | ORD/000163/2020-2021 | 1626/HD | 09/11/2020 | 09/12/2020 | P B ENTERPRISE | 27.61 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Balichak and Banuchak mouza of Balichak piped water supply scheme (Phase-II) | SM/06784 | Retrofitting | Survey and Collection of houshold details through mobile app and geo tagging the same including IMIS entry of water tap connection in each house hold from existing distribution system within scheme jurisdiction in different pipe water supply scheme |  |  | VCH/000077/2021-2022 | W/39 | 11/06/2021 | 11/06/2021 | STEELCONC AND ASSOCIATES | 4.73 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Balichak and Banuchak mouza of Balichak piped water supply scheme (Phase-II) | SM/06784 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply scheme. |  |  | VCH/000973/2020-2021 | 8443120 | 30/03/2021 | 30/03/2021 | GHOSH CONCERN | 27.96 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Balichak and Banuchak mouza of Balichak piped water supply scheme (Phase-II) | SM/06784 | Retrofitting | Retrofitting BalichakWater Supply Scheme |  |  | VCH/000891/2020-2021 | 844383 | 26/03/2021 | 26/03/2021 | N. G ENGINEERING | 21.63 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Balichak and Banuchak mouza of Balichak piped water supply scheme (Phase-II) | SM/06784 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply scheme. |  |  | VCH/000953/2020-2021 | 8443107 | 30/03/2021 | 30/03/2021 | P B ENTERPRISE | 23.52 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Balichak and Banuchak mouza of Balichak piped water supply scheme (Phase-II) | SM/06784 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply |  |  | VCH/000592/2021-2022 | W/594 | 21/12/2021 | 21/12/2021 | RANA ENTERPRISE | 7.58 | 0 | 0 | 0
9 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Balichak and Banuchak mouza of Balichak piped water supply scheme (Phase-II) | SM/06784 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000031/2021-2022 | 495/HD | 07/03/2022 | 07/03/2022 | Resource Division | 8.01 | 0 | 0 | 0
Total | [13 empty] | 165.71 | 0 | 0