## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bargazipur & Paschim Gazipur Mouza of Paschim Gazipur piped water supply scheme | SM/06788 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Paschim Gazipur piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-D) (for Paschim Gazipur mouza part) | AE/Ulu | JE/USD | ORD/000093/2020-2021 | 1305/HD | 12/10/2020 | 11/11/2020 | MENOKA ENGINEERING WORKS | 27.03 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bargazipur & Paschim Gazipur Mouza of Paschim Gazipur piped water supply scheme | SM/06788 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Paschim Gazipur piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-A) (for Bargazipur Mouza) | AE/Ulu | JE/USD | ORD/000090/2020-2021 | 1302/HD | 12/10/2020 | 11/11/2020 | ARINDAM ENTERPRISE | 9.05 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bargazipur & Paschim Gazipur Mouza of Paschim Gazipur piped water supply scheme | SM/06788 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Paschim Gazipur piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-B) (for Paschim Gazipur mouza part) | AE/Ulu | JE/USD | ORD/000091/2020-2021 | 1303/HD | 12/10/2020 | 11/11/2020 | CONSTRUCTION CORNER | 27.51 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bargazipur & Paschim Gazipur Mouza of Paschim Gazipur piped water supply scheme | SM/06788 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Paschim Gazipur piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-C) (for Paschim Gazipur mouza part) | AE/Ulu | JE/USD | ORD/000092/2020-2021 | 1304/HD | 12/10/2020 | 11/11/2020 | NIRMAL UDYOG | 27.33 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bargazipur & Paschim Gazipur Mouza of Paschim Gazipur piped water supply scheme | SM/06788 | Retrofitting | Retrofitting Paschim Gazipur Water Supply Scheme |  |  | VCH/000638/2020-2021 | W/518 | 15/01/2021 | 15/01/2021 | ARINDAM ENTERPRISE | 8.92 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bargazipur & Paschim Gazipur Mouza of Paschim Gazipur piped water supply scheme | SM/06788 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bargazipur & Paschim Gazipur Mouza of Paschim Gazipur piped water sup |  |  | VCH/001010/2020-2021 | 844384 | 26/03/2021 | 26/03/2021 | CONSTRUCTION CORNER | 22.55 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bargazipur & Paschim Gazipur Mouza of Paschim Gazipur piped water supply scheme | SM/06788 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bargazipur & Paschim Gazipur Mouza of Paschim Gazipur piped water SUPPLY SCHEME. |  |  | VCH/000853/2020-2021 | 844344 | 20/03/2021 | 20/03/2021 | NIRMAL UDYOG | 25.48 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bargazipur & Paschim Gazipur Mouza of Paschim Gazipur piped water supply scheme | SM/06788 | Retrofitting | Retrofitting of Paschim Gazipur Water Supply Scheme |  |  | VCH/000795/2020-2021 | 844319 | 11/03/2021 | 11/03/2021 | MENOKA ENGINEERING WORKS | 22.15 | 0 | 0 | 0
Total | [13 empty] | 170.04 | 0 | 0