## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme | SM/06789 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-M) (for Ratanpota & Kashtasangara(Part) Mouza) | AE/Ulu |  | ORD/000119/2020-2021 | 1514/HD | 04/11/2020 | 04/12/2020 | JAHANGIR ALAM | 25.61 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme | SM/06789 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-L) (for Kashtasangara(Part) | AE/Ulu |  | ORD/000118/2020-2021 | 1513/HD | 04/11/2020 | 04/12/2020 | JAHANGIR ALAM | 27.43 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme | SM/06789 | Retrofitting | Work Order for Additional Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte.(Part-G) (Phase-II) | AE/Ulu |  | ORD/000098/2022-2023 | 112/AE/USD | 15/06/2022 | 30/07/2022 | BUNBA CONSTRUCTION | 4.9 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme | SM/06789 | Retrofitting | Work Order for Additional laying of pipeline work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system (Majipara, Khosalpur, Kastosangra, Ratanpota) at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-F1) | AE/Ulu |  | ORD/000136/2022-2023 | 133/AE/USD | 20/06/2022 | 04/08/2022 | JAHANGIR ALAM | 4.71 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme | SM/06789 | Retrofitting | Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-B) (Phase-2) |  |  | VCH/001026/2021-2022 | BP-2021-22-451 | 25/03/2022 | 25/03/2022 | N. G ENGINEERING | 3.1 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme | SM/06789 | Retrofitting | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-A) |  |  | VCH/001027/2021-2022 | BP-2021-22-449 | 30/03/2022 | 30/03/2022 | M/S ASHIRBAD (INDIA) | 4.52 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme | SM/06789 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-C) (for Kasra Mouza (Part) |  |  | VCH/000932/2021-2022 | BP-2021-22-383 | 07/03/2022 | 07/03/2022 | DEV DAS SHAW | 18.73 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme | SM/06789 | Retrofitting | Cons of OHR Khoshalpur |  |  | VCH/001030/2021-2022 | BP-2021-22-324 | 16/02/2022 | 16/02/2022 | NATURAL RESOURCES CONSORTIUM | 8.49 | 0 | 0 | 0
9 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme | SM/06789 | Retrofitting | Construction of delivery spouts for filling movable water tanker in connection with flood prepardeness measure alongwith lying of tube well wash out with HDPE pipe of 4 nos Tube Wells of Khoshalpur Water Supply Scheme |  |  | VCH/000933/2021-2022 | BP-2021-22-384 | 07/03/2022 | 07/03/2022 | JAHANGIR ALAM | 1.08 | 0 | 0 | 0
10 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme | SM/06789 | Retrofitting | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-D) (Phase-2) | AE/Ulu |  | ORD/000299/2021-2022 | 2230/HD | 09/12/2021 | 08/01/2022 | PRADIP KUMAR JATI | 4.07 | 0 | 0 | 0
11 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme | SM/06789 | Retrofitting | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-D) (Phase-1) | AE/Ulu |  | ORD/000298/2021-2022 | 2229/HD | 09/12/2021 | 08/01/2022 | PRADIP KUMAR JATI | 4.07 | 0 | 0 | 0
12 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme | SM/06789 | Retrofitting | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-E) (Phase-2) | AE/Ulu |  | ORD/000302/2021-2022 | 2233/HD | 09/12/2021 | 08/01/2022 | DEV DAS SHAW | 3.49 | 0 | 0 | 0
13 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme | SM/06789 | Retrofitting | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-E) (Phase-1) | AE/Ulu |  | ORD/000301/2021-2022 | 2232/HD | 09/12/2021 | 08/01/2022 | DEV DAS SHAW | 3.49 | 0 | 0 | 0
14 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ratanpota & Kashtasangara Mouza of Khosalpur piped water supply scheme | SM/06789 | Retrofitting | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-E) (Phase-3) | AE/Ulu |  | ORD/000312/2021-2022 | 2243/HD | 09/12/2021 | 08/01/2022 | DEV DAS SHAW | 3.49 | 0 | 0 | 0
Total | [13 empty] | 117.17 | 0 | 0