## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) | SM/07008 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-B) [Tajpur Mouza part] | AE/Ulu | JE/USD | ORD/000267/2020-2021 | 1800/HD | 27/11/2020 | 27/12/2020 | AYUSH ENTERPRISE | 12.97 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) | SM/07008 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) |  |  | VCH/000851/2020-2021 | 844341 | 20/03/2021 | 20/03/2021 | AYUSH ENTERPRISE | 12.66 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) | SM/07008 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) |  |  | VCH/000944/2020-2021 | 8443110 | 30/03/2021 | 30/03/2021 | JOY CHANDI CONSTRUCTION | 30.29 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) | SM/07008 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) |  |  | VCH/000188/2021-2022 | W/176 | 06/08/2021 | 06/08/2021 | JAHANGIR ALAM | 29.23 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) | SM/07008 | Retrofitting | Work Order for Additional laying of pipeline for retrofitting work for providing Functional Household Tap Connection(FHTC) at Tajpur Water Supply scheme in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (Part-C) (Phase-I) | AE/Ulu | JE/USD | ORD/000054/2022-2023 | 1048/HD | 06/05/2022 | 05/06/2022 | JAHANGIR ALAM | 4.33 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) | SM/07008 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) |  |  | VCH/000640/2021-2022 | 84437 | 04/01/2022 | 04/01/2022 | JOY CHANDI CONSTRUCTION | 5.88 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) | SM/07008 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-B) |  |  | VCH/000687/2021-2022 | 844330 | 21/02/2022 | 21/02/2022 | AYUSH ENTERPRISE | 2.24 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) | SM/07008 | Retrofitting | Work order for interconnection between Replaced new Tube Well and existing OHR at Udong W/s scheme of Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu |  | ORD/000065/2022-2023 | 1059/HD | 06/05/2022 | 05/06/2022 | JAHANGIR ALAM | 0.91 | 0 | 0 | 0
Total | [13 empty] | 98.51 | 0 | 0