## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-2) | SM/07009 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-E) [Tajpur Mouza part] | AE/Ulu | JE/USD | ORD/000268/2020-2021 | 1801/HD | 27/11/2020 | 27/12/2020 | MITHU BUILDERS | 30.95 | 21.85 | 70.6 | 0
2 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-2) | SM/07009 | Retrofitting | Work Order for Additional laying of pipeline for retrofitting work for providing Functional Household Tap Connection(FHTC) at Tajpur Water Supply scheme in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (Part-C) (Phase-II) | AE/Ulu | JE/USD | ORD/000055/2022-2023 | 1049/HD | 06/05/2022 | 05/06/2022 | JAHANGIR ALAM | 3.76 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-2) | SM/07009 | Retrofitting | Cons of Balance work for boundary wall at HW Site and interconnection between OHR to LDS and rising main of Tajpur |  |  | VCH/000880/2021-2022 | 844332 | 30/03/2022 | 30/03/2022 | KANIKA CONSTRUCTION | 2.16 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-2) | SM/07009 | Retrofitting | Cons of approach road of Tajpur W/S Scheme. |  |  | VCH/000902/2021-2022 | 844330 | 29/03/2022 | 29/03/2022 | PIKASU BOSE | 2.46 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-2) | SM/07009 | Retrofitting | Construction of switch room ( 3.60 m x 3.0 m) with water supply & sanitary arrangement at tube well site of Vill Bansbagan of Tajpur PWSS of Amta-II Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. (SM/07009) | AE/Ulu | JE/BLK/amta2,JE/USD | ORD/000352/2024-2025 | 1168/AE/USD | 25/11/2024 | 09/01/2025 | ALI ENTERPRISE | 4.84 | 0 | 0 | 100
6 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-2) | SM/07009 | Retrofitting | Alternative laying of distribution pipe line with repairing of FHTC's at village-Mahishamuri, Tajpur G.P. of Tajpur PWSS of Amta-II Development Block in Uluberia Sub Division under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/RWS/Amta II | ORD/000772/2024-2025 | 1463/HD | 19/03/2025 | 16/09/2025 | MANIRUL ISLAM | 19.22 | 0 | 0 | 100
Total | [13 empty] | 63.39 | 21.85 | 34.47