## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block | SM/07010 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte.on, PHE Dte. (Part-D) [Sirol Mouza] | AE/Ulu |  | ORD/000272/2020-2021 | 1805/HD | 27/11/2020 | 27/12/2020 | JAHANGIR ALAM | 36.58 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block | SM/07010 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte.on, PHE Dte. (Part-A) [Narit Mouza part] | AE/Ulu |  | ORD/000269/2020-2021 | 1802/HD | 27/11/2020 | 27/12/2020 | M/S MANABESH ROY | 22.53 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block | SM/07010 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte.on, PHE Dte. (Part-B) [Narit Mouza part] | AE/Ulu |  | ORD/000270/2020-2021 | 1803/HD | 27/11/2020 | 27/12/2020 | SUNIRMAN ENTERPRISE | 19.47 | 16.2 | 83.2 | 0
4 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block | SM/07010 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte.on, PHE Dte. (Part-C) [Narit Mouza part] | AE/Ulu |  | ORD/000271/2020-2021 | 1804/HD | 27/11/2020 | 27/12/2020 | SADHURHAT CO OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 14.53 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block | SM/07010 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block |  |  | VCH/000657/2020-2021 | W/538 | 30/01/2021 | 30/01/2021 | JAHANGIR ALAM | 36.57 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block | SM/07010 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block |  |  | VCH/000998/2020-2021 | 844352 | 22/03/2021 | 22/03/2021 | SADHURHAT CO OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 14.34 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block | SM/07010 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block |  |  | VCH/000852/2020-2021 | 844343 | 20/03/2021 | 20/03/2021 | M/S MANABESH ROY | 15.07 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block | SM/07010 | Retrofitting | Hiring of Vehicle |  |  | VCH/000601/2021-2022 | W/579 | 16/12/2021 | 16/12/2021 | DIPANKAR GHOSH | 3.71 | 0 | 0 | 0
Total | [13 empty] | 162.81 | 16.2 | 9.95