## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-2) | SM/07075 | Retrofitting | Interconnection of Pump1 and 2 with proposed 700 cum reservoir for Bikihakola Water Supply scheme at Panchla Block under Howrah Division, P.H.E. Dte. |  |  | VCH/000604/2021-2022 | W/597 | 28/12/2021 | 28/12/2021 | UNIVERSAL CORPORATION | 23.22 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-2) | SM/07075 | Retrofitting | Trial Run and Operation & maintenance of pipe lines (LDS & Risingmain) sluice valve & street stand post etc. including operation of sluice valves at Bikihakola w/s scheme under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. (90 days from issue of Work Order) |  |  | VCH/000603/2021-2022 | W/598 | 24/12/2021 | 24/12/2021 | UNIVERSAL CORPORATION | 1.15 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-2) | SM/07075 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributin system of Bikihakola piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-II) |  |  | VCH/000851/2021-2022 | 844325 | 24/03/2022 | 24/03/2022 | M/S ASHIRBAD (INDIA) | 55.24 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-2) | SM/07075 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Bikiha kola piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-III) |  |  | VCH/000855/2021-2022 | 844326 | 24/03/2022 | 24/03/2022 | PRADIP KUMAR JATI | 89.17 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-2) | SM/07075 | Retrofitting | FHTC of Bikihakola W/SScheme under Panchla Block under Howrah Sadar Sub-Division PHE Dte. (Phase-IV) |  |  | VCH/000850/2021-2022 | 844323 | 24/03/2022 | 24/03/2022 | G.B. CONSTRUCTION AND CO | 62.79 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-2) | SM/07075 | Retrofitting | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Bikihakola piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-II) Part- A | AE/SADAR |  | ORD/000435/2021-2022 | 349/HD | 17/02/2022 | 19/03/2022 | UNIVERSAL CORPORATION | 4.3 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-2) | SM/07075 | Retrofitting | Work Order for Retrofitting work for Functional Household Tap Connection(FHTC) from existing distribution system of Bikihakola PWSS under Panchla Block of Howrah Sadar Sub Division under Howrah Division, PHE Dte.(Phase-II) (Part-A) No of House Hold= 100 nos. | AE/SADAR |  | ORD/000545/2021-2022 | 661/HD | 23/03/2022 | 12/04/2022 | UNIQUE CONSTRUCTION | 3.82 | 0 | 0 | 100
8 | HOWRAH |  | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-2) | SM/07075 | Retrofitting | Work Order for Retrofitting work for Functional Household Tap Connection(FHTC) from existing distribution system of Bikihakola PWSS under Panchla Block of Howrah Sadar Sub Division under Howrah Division, PHE Dte.(Phase-II) (Part-B)No of House Hold= 100 nos. | AE/SADAR |  | ORD/000546/2021-2022 | 662/HD | 23/03/2022 | 12/04/2022 | UNIQUE CONSTRUCTION | 3.67 | 0 | 0 | 100
Total | [13 empty] | 243.36 | 0 | 0