## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-3) | SM/07076 | Retrofitting | FHTC of Bikihakola W/SScheme under Panchla Block under Howrah Sadar Sub-Division PHE Dte. (Phase-IV) |  |  | VCH/000850/2021-2022 | 844323 | 24/03/2022 | 24/03/2022 | G.B. CONSTRUCTION AND CO | 62.79 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-3) | SM/07076 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributin system of Bikihakola piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-II) |  |  | VCH/000851/2021-2022 | 844325 | 24/03/2022 | 24/03/2022 | M/S ASHIRBAD (INDIA) | 55.24 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-3) | SM/07076 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Bikiha kola piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-III) |  |  | VCH/000855/2021-2022 | 844326 | 24/03/2022 | 24/03/2022 | PRADIP KUMAR JATI | 89.17 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-3) | SM/07076 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Bikiha kola piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-III) | AE/SADAR |  | ORD/000493/2020-2021 | 400/HD | 10/02/2021 | 12/03/2021 | PRADIP KUMAR JATI | 92.36 | 0 | 0 | 0
Total | [13 empty] | 299.56 | 0 | 0