## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-4) | SM/07077 | Retrofitting | Work Order for Survey & Collection of house hold details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system in Bikihakola Piped Water Supply Scheme under Howrah District. |  |  | VCH/000312/2022-2023 | BP-2022-23-53 | 11/05/2022 | 11/05/2022 | UNIVERSAL CORPORATION | 0.73 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-4) | SM/07077 | Retrofitting | Work Order for laying of Delivery Main proposed 700 cum reservoir for Bikihakola Water Supply scheme at Panchla Block under Howrah Division, P.H.E. Dte.( Part -II) |  |  | VCH/000304/2022-2023 | BP-2022-23-51 | 11/05/2022 | 11/05/2022 | UNIVERSAL CORPORATION | 4.44 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-4) | SM/07077 | Retrofitting | Continuation order for Trial Run and Operation & maintenance of pipe lines (LDS & Risingmain) sluice valve & street stand post etc. including operation of sluice valves at Bikihakola w/s scheme under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. (09/05/2021 to 31/08/2021)In continuation to the order under reference, and your application dated 06-05-2021, you are requested to continue the above mentioned work in consultation with the Assistant Engineer, Howrah Sadar Sub-Division, PHE Dte. |  |  | VCH/000993/2021-2022 | BP-2021-22-435 | 23/03/2022 | 23/03/2022 | UNIVERSAL CORPORATION | 1.53 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-4) | SM/07077 | Retrofitting | Work Order for laying of Delivery Main proposed 700 cum reservoir for Bikihakola Water Supply scheme at Panchla Block under Howrah Division, P.H.E. Dte. |  |  | VCH/000305/2022-2023 | BP-2022-23-52 | 11/05/2022 | 11/05/2022 | UNIVERSAL CORPORATION | 4.85 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-4) | SM/07077 | Retrofitting | O & M of distribution system and rising main pipe line (CI/DI/AC/UPVC) of Bikihakhola w/s scheme under Howrah Division, PHE Dte. Period for O & M (01.09.2021 to 31.12.2021) |  |  | VCH/000989/2021-2022 | BP-2021-22-434 | 23/03/2022 | 23/03/2022 | UNIVERSAL CORPORATION | 0.99 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-4) | SM/07077 | Retrofitting | Work Order for Laying of Delivery Main Proposal 700 cum reservoir for BikihaKola Water Supply Scheme at Panchla Block under Howrah Division, PHE Dte. (Part-IV) |  |  | VCH/000263/2022-2023 | BP-2022-23-49 | 11/05/2022 | 11/05/2022 | UNIVERSAL CORPORATION | 1.55 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-4) | SM/07077 | Retrofitting | Work Order for Laying of Delivery Main Proposal 700 cum reservoir for BikihaKola Water Supply Scheme at Panchla Block under Howrah Division, PHE Dte. (Part-III) |  |  | VCH/000281/2022-2023 | BP-2022-23-50 | 11/05/2022 | 11/05/2022 | UNIVERSAL CORPORATION | 3.19 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-4) | SM/07077 | Retrofitting | Work order for Survey & Collection of house hold details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system in Bikihakola Piped Water Supply Scheme under Howrah District. (Part-B) |  |  | VCH/000303/2022-2023 | BP-2022-23-45 | 11/05/2022 | 11/05/2022 | PRADIP KUMAR JATI | 0.73 | 0 | 0 | 0
9 | HOWRAH |  | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-4) | SM/07077 | Retrofitting | Work Order for Adopting Jack Pushing of 600 mm Dia M.S pipe as Casing to Cross Water carrier Pipe(Between Node Point 200-203 of LDS drawing) on Ranihati- Amta Road and adjoining work of Biki hakola Water Supply Scheme of Howrah Sadar Sub-Division, under Howrah Division P.H.E. Dte. | AE/SADAR |  | ORD/000413/2021-2022 | 377/HD | 21/02/2022 | 23/03/2022 | SAMIRON GHOSH | 26.38 | 0 | 0 | 0
10 | HOWRAH |  | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-4) | SM/07077 | Retrofitting | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Bikihakola piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-II) Part- A | AE/SADAR |  | ORD/000435/2021-2022 | 349/HD | 17/02/2022 | 19/03/2022 | UNIVERSAL CORPORATION | 4.3 | 0 | 0 | 0
11 | HOWRAH |  | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-4) | SM/07077 | Retrofitting | Work Order Retrofitting work of Laying Pipeline From Node Point 4-162, 162-220 for Bikihakola PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. | AE/SADAR |  | ORD/000596/2022-2023 | 2606/HD | 07/12/2022 | 21/01/2023 | UNIVERSAL CORPORATION | 11.28 | 0 | 0 | 40
12 | HOWRAH |  | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-4) | SM/07077 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Bikiha kola piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-IV) | AE/SADAR |  | ORD/000495/2020-2021 | 425/HD | 11/02/2021 | 13/03/2021 | G.B. CONSTRUCTION AND CO | 92.5 | 0 | 0 | 100
13 | HOWRAH |  | Howrah Division | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-4) | SM/07077 | Retrofitting | Construction of Approach road 3.00 mtr wide at Pump House -I of Bikihakola PWSS at Howrah Sadar Sub- Division under Howrah Division , P.H.E Dte | AE/SADAR |  | ORD/000097/2021-2022 | 1449/HD | 13/07/2021 | 12/08/2021 | S.M. CONSTRUCTION | 4.3 | 0 | 0 | 0
Total | [13 empty] | 156.77 | 0 | 0