## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chandrapur Piped Water Supply Scheme under Amta-I Block | SM/07396 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chandrapur PipedWater Supply Scheme under Amta-I Block under Howrah Division, PHE Dte. (PART-B) [CHANDRAPUR GP PART] |  |  | VCH/000814/2021-2022 | BP-2021-22-370 | 28/02/2022 | 28/02/2022 | QUICK CONCRETE PROJECT | 35.83 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chandrapur Piped Water Supply Scheme under Amta-I Block | SM/07396 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chandrapur Piped Water Supply Scheme under Amta-I Block under Howrah Division, PHE Dte. (PART-D) [CHANDRAPUR GP PART] |  |  | VCH/000971/2021-2022 | BP-2021-22-417 | 14/03/2022 | 14/03/2022 | MAA TARA CONSTRUCTION | 24.68 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chandrapur Piped Water Supply Scheme under Amta-I Block | SM/07396 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chandrapur Piped Water Supply Scheme under Amta-I Block under Howrah Division, PHE Dte. (PART-A) [MAHISHGOHA GP] |  |  | VCH/000926/2021-2022 | BP-2021-22-388 | 08/03/2022 | 08/03/2022 | PRADIP KUMAR JATI | 38.13 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chandrapur Piped Water Supply Scheme under Amta-I Block | SM/07396 | Retrofitting | Work Order for Additional pipe line work for providing Functional Household Tap Connection(FHTC) from existing distribution system (moksed para, Hazra para, molla para) at CHANDRAPUR W/S scheme under AMTA-I Block under Howrah Division, PHE Dte. (Part-I) | AE/Ulu | JE/USD | ORD/000381/2021-2022 | 2378/HD | 24/12/2021 | 23/01/2022 | MAA TARA CONSTRUCTION | 4.82 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chandrapur Piped Water Supply Scheme under Amta-I Block | SM/07396 | Retrofitting | Work Order for Additional pipe line work for providing Functional Household Tap Connection(FHTC) from existing distribution system ( Mirpara, Bodok para, Khapara, Adolpara) at CHANDRAPUR W/S scheme under AMTA-I Block under Howrah Division, PHE Dte. (part-II) | AE/Ulu | JE/USD | ORD/000382/2021-2022 | 2379/HD | 24/12/2021 | 23/01/2022 | QUICK CONCRETE PROJECT | 4.82 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chandrapur Piped Water Supply Scheme under Amta-I Block | SM/07396 | Retrofitting | Work Order for Additional pipeline work for providing Functional Household Tap Connection(FHTC) from existing distribution system (Hazari para, Beg para, Molla para, Chandrapur primary school) at CHANDRAPUR W/S scheme under AMTA-I Block under Howrah Division, PHE Dte. (Part-I) (Phase-B) | AE/Ulu | JE/USD | ORD/000135/2022-2023 | 132/AE/USD | 20/06/2022 | 04/08/2022 | DDD CONSTRUCTION | 4.78 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chandrapur Piped Water Supply Scheme under Amta-I Block | SM/07396 | Retrofitting | Sinking of 1 (One) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipe (CD) and UPVC Deep Well Screen (RDS) all complete at Chandrapur PWSS at Amta-I Block under Uluberia Sub Division within Howrah Division, P.H.E. Dte.(Location-Chatra) | AE/Ulu |  | ORD/000380/2024-2025 | 784/HD | 04/02/2025 | 24/02/2025 | AUXILIARY TUBEWELL DRILLERS | 14.4 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chandrapur Piped Water Supply Scheme under Amta-I Block | SM/07396 | Retrofitting | Sinking of 1 (One) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipe (CD) and UPVC Deep Well Screen (RDS) all complete at Chandrapur PWSS at Amta-I Block under Uluberia Sub Division within Howrah Division, P.H.E. Dte.(Location-Maheshguha) | AE/Ulu |  | ORD/000381/2024-2025 | 785/HD | 04/02/2025 | 24/02/2025 | AUXILIARY TUBEWELL DRILLERS | 14.4 | 0 | 0 | 0
Total | [13 empty] | 141.84 | 0 | 0