## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Supply Based Piped Water Supply Scheme For Uttar Khariop under Amta-II Block | SM/07465 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Supply Based Piped Water Supply Scheme For Uttar Khariop PWSS under Amta-II Block under Howrah Division, PHE Dte.(No of FHTC to be provided (Approx:- 1711) | AE/Ulu | JE/USD | ORD/000012/2021-2022 | 1198/HD | 31/05/2021 | 30/07/2021 | N. G ENGINEERING | 112.54 | 112.83 | 100.26 | 0
2 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Supply Based Piped Water Supply Scheme For Uttar Khariop under Amta-II Block | SM/07465 | Retrofitting | Survey & collection of house hold details through mobile app and geo tagging the same of water tap connection in each house hold from existing distribution system within scheme juridiction in Nakubar, Amragori, Joypur & Uttar Khorip and others Pipe Water Supply Scheme of Uluberia Sub-Division under Howrah Division, PHE Dte. |  |  | VCH/000284/2022-2023 | BP-2022-23-44 | 11/05/2022 | 11/05/2022 | M/S ASHIRBAD (INDIA) | 4.87 | 0 | 0 | 0
Total | [13 empty] | 117.41 | 112.83 | 96.1