## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Based Piped Water Supply Scheme For Nakubar under Amta-II Block | SM/07466 | Retrofitting | Retrofitting for Nakubar W/S Scheme. |  |  | VCH/000137/2021-2022 | W/263 | 03/09/2021 | 03/09/2021 | N. G ENGINEERING | 35.84 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Based Piped Water Supply Scheme For Nakubar under Amta-II Block | SM/07466 | Retrofitting | Retrofitting Nakubar |  |  | VCH/000051/2021-2022 | W/155 | 06/08/2021 | 06/08/2021 | M/S ASHIRBAD (INDIA) | 20.86 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Based Piped Water Supply Scheme For Nakubar under Amta-II Block | SM/07466 | Retrofitting | Retrofitting of Nakubar. |  |  | VCH/000771/2020-2021 | W/93 | 19/07/2021 | 19/07/2021 | SWASTIK ENTERPRISE | 14.6 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Based Piped Water Supply Scheme For Nakubar under Amta-II Block | SM/07466 | Retrofitting | Retrofitting for Nakubar W/S Scheme. |  |  | VCH/000136/2021-2022 |  | 24/08/2021 | 24/08/2021 | M/S ASHIRBAD (INDIA) | 38.07 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Based Piped Water Supply Scheme For Nakubar under Amta-II Block | SM/07466 | Retrofitting | Work Order for Additional laying of pipeline for retrofitting work for providing Functional Household Tap Connection(FHTC) at Nakubar Water Supply scheme in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000378/2021-2022 | 2368/HD | 23/12/2021 | 22/01/2022 | M/S ASHIRBAD (INDIA) | 4.57 | 4.54 | 99.37 | 0
6 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Based Piped Water Supply Scheme For Nakubar under Amta-II Block | SM/07466 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Based Piped Water Supply Scheme For Nakubar under Amta-II Block under Howrah Division, PHE Dte. (PART-D) [Ranjoybar MOUZA PART & Nakubar MOUZA PART] |  |  | VCH/000922/2021-2022 | W/797 | 03/03/2022 | 03/03/2022 | N. G ENGINEERING | 34.83 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Based Piped Water Supply Scheme For Nakubar under Amta-II Block | SM/07466 | Retrofitting | Alternative laying of distribution pipe line damaged due to improvement of road work by WBSRDA Howrah under PMGSY programme for restoration of FHTC's at Nakubar W/S scheme under Amta-II Block under Howrah Division, PHE Dte. Near Manuchack Zilla parisad pole | AE/Ulu |  | ORD/000877/2022-2023 | 949/AE/USD | 22/03/2023 | 21/04/2023 | M/S ASHIRBAD (INDIA) | 0.97 | 0.79 | 81.01 | 100
8 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Based Piped Water Supply Scheme For Nakubar under Amta-II Block | SM/07466 | Retrofitting | Alternative laying of distribution pipe line damaged due to improvement of road work by WBSRDA Howrah under PMGSY programme for restoration of FHTC's at Nakubar W/S scheme under Amta-II Block under Howrah Division, PHE Dte. near Kalimata Club and various places. | AE/Ulu |  | ORD/000878/2022-2023 | 950/AE/USD | 22/03/2023 | 21/04/2023 | M/S ASHIRBAD (INDIA) | 0.96 | 0.96 | 100 | 100
9 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Based Piped Water Supply Scheme For Nakubar under Amta-II Block | SM/07466 | Retrofitting | Alternative laying of distribution pipe line damaged due to improvement of road work by WBSRDA Howrah under PMGSY programme for restoration of FHTC's at Nakubar W/S scheme under Amta-II Block under Howrah Division, PHE Dte. At different places of Boalia mouza | AE/Ulu |  | ORD/000866/2022-2023 | 939/AE/USD | 22/03/2023 | 21/04/2023 | M/S ASHIRBAD (INDIA) | 0.97 | 0.78 | 80.4 | 100
Total | [13 empty] | 151.67 | 7.07 | 4.66