## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block | SM/07467 | Retrofitting | Retrofitting of Amragori. |  |  | VCH/000769/2020-2021 | W/97 | 19/07/2021 | 19/07/2021 | TANMOY ROY CHOUDHURY | 21.4 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block | SM/07467 | Retrofitting | Retrofitting of Amragori. |  |  | VCH/000768/2020-2021 | W/95 | 19/07/2021 | 19/07/2021 | MAA TARA CONSTRUCTION | 17.11 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block | SM/07467 | Retrofitting | Retrofitting of Amragori. |  |  | VCH/000772/2020-2021 | W/95 | 19/07/2021 | 19/07/2021 | RANA ENTERPRISE | 10.33 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block | SM/07467 | Retrofitting | Retrofitting of Amragori. |  |  | VCH/000770/2020-2021 |  | 24/03/2021 | 24/03/2021 | UNIQUE AGENCY | 21.75 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block | SM/07467 | Retrofitting | Retrofitting of Amragori. |  |  | VCH/000767/2020-2021 | W/386 | 19/07/2021 | 19/07/2021 | GHOSH ENTERPRISE. | 30.3 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block | SM/07467 | Retrofitting | Retrofitting of Amragori. |  |  | VCH/000766/2020-2021 |  | 24/03/2021 | 24/03/2021 | TANMOY ROY CHOUDHURY | 22.54 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block | SM/07467 | Retrofitting | Retrofitting of providing Functional Household Tap Connection from existing distribution system of Amragori & adj Mouzas piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-E) |  |  | VCH/000247/2021-2022 | BP-2021-22-164 | 07/10/2021 | 07/10/2021 | TANMOY ROY CHOUDHURY | 11.83 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block | SM/07467 | Retrofitting | Special maintenance of pipeline at Amragori Water Supply scheme in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (Phase-I) | AE/Ulu | JE/USD | ORD/000210/2021-2022 | 1820/HD | 17/09/2021 | 17/10/2021 | UNIQUE AGENCY | 2.27 | 0 | 0 | 0
9 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block | SM/07467 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) to Schools, AWC's & Public Institution of Amragori, Nakubar, Sarda, Tajpur, Joypur, Narit, Kanpur, Paschim Gazipur, Balichack, Uttar Pirpur W/S scheme under under Howrah Division, PHE Dte. | AE/Ulu | JE/USD | ORD/000245/2021-2022 | 2175/HD | 01/12/2021 | 31/12/2021 | JOY CHANDI CONSTRUCTION | 4.28 | 0 | 0 | 0
10 | HOWRAH |  | Central Drilling | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block | SM/07467 | Retrofitting | FUEL CHARGES FOR CAR NO. WB-05-2798, WB-04H-6870 & WB-25H-5187. |  |  | ORD/000062/2022-2023 | 789/CDD | 23/08/2022 | 30/08/2022 | MIRA SERVICE STATION | 0.65 | 0 | 0 | 0
11 | HOWRAH |  | Central Drilling | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block | SM/07467 | Retrofitting | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 230 MTRS DEPTH) BY DEPARTMENTAL RIG MACHINE FOR AMRAGORI PWSS, AMTA-II BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. |  |  | ORD/000050/2022-2023 | 299/CMSD-I (D) | 08/07/2022 | 23/07/2022 | DIPALI CONSTUCTION | 3.11 | 0 | 0 | 0
12 | HOWRAH |  | Central Drilling | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block | SM/07467 | Retrofitting | PROVIDING STRAINER CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT SARDA W/S SCH, AMTA-II BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. |  |  | ORD/000048/2022-2023 | 233/CMSD-I (D) | 20/06/2022 | 05/07/2022 | DIPALI CONSTUCTION | 4.76 | 0 | 0 | 0
13 | HOWRAH |  | Central Drilling | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block | SM/07467 | Retrofitting | PROVIDING HOUSING PIPE CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT SARDA W/S SCH, AMTA-II BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. |  |  | ORD/000049/2022-2023 | 232/CMSD-I (D) | 20/06/2022 | 05/07/2022 | DIPALI CONSTUCTION | 3.44 | 0 | 0 | 0
14 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block | SM/07467 | Retrofitting | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Amragori W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-A) |  |  | VCH/001033/2021-2022 | BP-2021-22-422 | 23/03/2022 | 23/03/2022 | RANA ENTERPRISE | 2.3 | 0 | 0 | 0
15 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block | SM/07467 | Retrofitting | WBSEDCL |  |  | VCH/000585/2022-2023 |  | 13/09/2022 | 13/09/2022 | WBSEDCL | 3.02 | 0 | 0 | 0
16 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block | SM/07467 | Retrofitting | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Amragori W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-A) |  |  | VCH/000976/2021-2022 | BP-2021-22-422 | 06/04/2022 | 06/04/2022 | RANA ENTERPRISE | 2.3 | 0 | 0 | 0
17 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block | SM/07467 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block under Howrah Division, PHE Dte. (PART-B) [Amragari MOUZA PART & Rautara MOUZA PART] |  |  | VCH/000799/2021-2022 | BP-2021-22-321 | 18/02/2022 | 18/02/2022 | UNIQUE AGENCY | 4.01 | 0 | 0 | 0
18 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block | SM/07467 | Retrofitting | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Amragori W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-C) |  |  | VCH/000975/2021-2022 | BP-2021-22-421 | 21/03/2022 | 21/03/2022 | MAA TARA CONSTRUCTION | 2.05 | 0 | 0 | 0
19 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block | SM/07467 | Retrofitting | Alternative laying of pipeline due to construction of PMGSY road for Amragori w/s scheme (from Danda's Misti's shop to Chacksalika Vimtala) at section (100-101-101B-101C-103-105-107-111-113-118-120-121-127-128-128B-135-136-141) under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. |  |  | VCH/000798/2021-2022 | BP-2021-22-322 | 18/02/2022 | 18/02/2022 | UNIQUE AGENCY | 3.38 | 0 | 0 | 0
20 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block | SM/07467 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block under Howrah Division, PHE Dte. (PART-C) [Rautara MOUZA PART] | AE/Ulu |  | ORD/000435/2020-2021 | 157/HD | 19/01/2021 | 18/02/2021 | GHOSH ENTERPRISE. | 42.22 | 5.52 | 13.08 | 0
21 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block | SM/07467 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block under Howrah Division, PHE Dte. (PART-B) [Amragari MOUZA PART & Rautara MOUZA PART] | AE/Ulu |  | ORD/000434/2020-2021 | 156/HD | 19/01/2021 | 18/02/2021 | UNIQUE AGENCY | 28.9 | 21.75 | 75.25 | 0
22 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block | SM/07467 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block under Howrah Division, PHE Dte. (PART-E) [Kakrol MOUZA PART] | AE/Ulu |  | ORD/000437/2020-2021 | 159/HD | 19/01/2021 | 18/02/2021 | TANMOY ROY CHOUDHURY | 38.98 | 40.46 | 103.81 | 0
23 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block | SM/07467 | Retrofitting | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block under Howrah Division, PHE Dte. (PART-F) [Kakrol MOUZA PART] | AE/Ulu |  | ORD/000438/2020-2021 | 160/HD | 19/01/2021 | 18/02/2021 | DEV DAS SHAW | 39.02 | 36.37 | 93.21 | 0
Total | [13 empty] | 319.94 | 104.1 | 32.54