## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block | SM/07880 | Retrofitting | Work Order for Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block under Howrah Division, PHE Dte. for 2452 nos. | AE/RWS | JE/USD | ORD/000459/2021-2022 | 443/HD | 02/03/2022 | 02/06/2022 | SAMIRON GHOSH | 126.42 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block | SM/07880 | Retrofitting | Work Order for Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block under Howrah Division, PHE Dte. for 2452 nos. |  |  | VCH/000409/2022-2023 | BP-2022-23-100 | 29/06/2022 | 29/06/2022 | SAMIRON GHOSH | 126.96 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block | SM/07880 | Retrofitting | Additional laying of pipeline for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block under Howrah Division, PHE Dte. (Phase-2) | AE/RWS,AE/Ulu | JE/USD | ORD/000261/2022-2023 | 345/AE/USD | 22/08/2022 | 06/10/2022 | SK ENTERPRISE | 4.83 | 4.83 | 99.86 | 0
4 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block | SM/07880 | Retrofitting | Additional laying of pipeline for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block under Howrah Division, PHE Dte. (Phase-3) | AE/RWS,AE/Ulu | JE/USD | ORD/000272/2022-2023 | 354/AE/USD | 22/08/2022 | 06/10/2022 | SK ENTERPRISE | 3.33 | 3.04 | 91.14 | 0
5 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block | SM/07880 | Retrofitting | Additional laying of pipeline for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block under Howrah Division, PHE Dte. (Phase-1) | AE/RWS,AE/Ulu | JE/USD | ORD/000260/2022-2023 | 344/AE/USD | 22/08/2022 | 06/10/2022 | SK ENTERPRISE | 4.8 | 4.16 | 86.57 | 0
6 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block | SM/07880 | Retrofitting | Work Order for Providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Phase-D) | AE/Ulu | JE/USD | ORD/000073/2023-2024 | 1934/HD | 10/05/2023 | 24/06/2023 | S.M. CONSTRUCTION | 4.96 | 4.96 | 99.97 | 100
Total | [13 empty] | 271.31 | 16.98 | 6.26