## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block | SM/07882 | Retrofitting | Work Order for Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block under Howrah Division, PHE Dte. for 2697 nos. | AE/Ulu | JE/USD | ORD/000003/2022-2023 | 789/HD | 06/04/2022 | 06/07/2022 | SAMIRON GHOSH | 139.78 | 0 | 0 | 100
2 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block | SM/07882 | Retrofitting | Work Order for Additional laying of HDPE pipe for Providing Functional Household Tap Connection(FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000727/2022-2023 | 517/HD | 09/02/2023 | 11/03/2023 | SAMIRON GHOSH | 40.57 | 0 | 0 | 100
3 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block | SM/07882 | Retrofitting | Additional FHTC & pipeline work in-connection with providing Functional Household Tap Connection(FHTC) from existing distribution system in Panpur Dakhinpara at Dakhin Harishpur W/S scheme under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu | JE/USD | ORD/000702/2023-2024 | 3247/AE/USD | 12/03/2024 | 02/04/2024 | MMS CONSTRUCTIONS PVT. LTD. | 0.97 | 0 | 0 | 100
4 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block | SM/07882 | Retrofitting | Additional FHTC & pipeline work in-connection with providing Functional Household Tap Connection(FHTC) from existing distribution system in Panpur Uttarpara at Dakhin Harishpur W/S scheme under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu | JE/USD | ORD/000703/2023-2024 | 3248/AE/USD | 12/03/2024 | 02/04/2024 | MMS CONSTRUCTIONS PVT. LTD. | 0.97 | 0 | 0 | 100
5 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block | SM/07882 | Retrofitting | Additional FHTC & pipeline work in-connection with providing Functional Household Tap Connection (FHTC) from existing distribution system in Dadpur Bamunpara at Dakhin Harishpur W/S scheme under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu | JE/USD | ORD/000708/2023-2024 | 3253/AE/USD | 12/03/2024 | 02/04/2024 | MMS CONSTRUCTIONS PVT. LTD. | 0.97 | 0 | 0 | 100
6 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block | SM/07882 | Retrofitting | Additional FHTC & pipeline work in-connection with providing Functional Household Tap Connection(FHTC) from existing distribution system in Dakhin Ramchandrapur Hazrapara at Dakhin Harishpur W/S scheme under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu | JE/USD | ORD/000706/2023-2024 | 3251/AE/USD | 12/03/2024 | 02/04/2024 | MMS CONSTRUCTIONS PVT. LTD. | 0.97 | 0 | 0 | 100
7 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block | SM/07882 | Retrofitting | Additional FHTC & pipeline work in-connection with providing Functional Household Tap Connection(FHTC) from existing distribution system in Dadpur Paschimpara at Dakhin Harishpur W/S scheme under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu | JE/USD | ORD/000711/2023-2024 | 3255/AE/USD | 12/03/2024 | 02/04/2024 | MMS CONSTRUCTIONS PVT. LTD. | 0.97 | 0 | 0 | 100
8 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block | SM/07882 | Retrofitting | Additional FHTC & pipeline work in-connection with providing Functional Household Tap Connection(FHTC) from existing distribution system in Panpur Ghoshpara at Dakhin Harishpur W/S scheme under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu | JE/USD | ORD/000704/2023-2024 | 3249/AE/USD | 12/03/2024 | 02/04/2024 | MMS CONSTRUCTIONS PVT. LTD. | 0.97 | 0 | 0 | 100
9 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block | SM/07882 | Retrofitting | Additional FHTC & pipeline work in-connection with providing Functional Household Tap Connection(FHTC) from existing distribution system in Dakhin Ramchandrapur Purbapara at Dakhin Harishpur W/S scheme under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu | JE/USD | ORD/000705/2023-2024 | 3250/AE/USD | 12/03/2024 | 02/04/2024 | MMS CONSTRUCTIONS PVT. LTD. | 0.97 | 0 | 0 | 100
10 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block | SM/07882 | Retrofitting | Additional FHTC & pipeline work in-connection with providing Functional Household Tap Connection(FHTC) from existing distribution system in Dadpur Majhipara at Dakhin Harishpur W/S scheme under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu | JE/USD | ORD/000710/2023-2024 | 3254/AE/USD | 12/03/2024 | 02/04/2024 | MMS CONSTRUCTIONS PVT. LTD. | 0.97 | 0 | 0 | 100
11 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block | SM/07882 | Retrofitting | Additional FHTC & pipeline work in-connection with providing Functional Household Tap Connection(FHTC) from existing distribution system in Dakhin Ramchandrapur Chatterjeepara at Dakhin Harishpur W/S scheme under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu | JE/USD | ORD/000707/2023-2024 | 3252/AE/USD | 12/03/2024 | 02/04/2024 | MMS CONSTRUCTIONS PVT. LTD. | 0.97 | 0 | 0 | 100
Total | [13 empty] | 189.08 | 0 | 0