## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block | SM/07883 | Retrofitting | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. 2184 nos | AE/Ulu | JE/USD | ORD/000376/2021-2022 | 93/HD | 17/01/2022 | 03/03/2022 | MA MANASA CONSTRUCTION | 84.61 | 86.67 | 102.43 | 0
2 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block | SM/07883 | Retrofitting | Work Order for Additional laying of pipeline for providing Functional Household Tap Connection(FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Phase-2) | AE/Ulu | JE/USD | ORD/000145/2022-2023 | 166/AE/USD | 28/06/2022 | 12/08/2022 | MA MANASA CONSTRUCTION | 4.78 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block | SM/07883 | Retrofitting | Work Order for Additional laying of pipeline for providing Functional Household Tap Connection(FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Phase-1) | AE/Ulu | JE/USD | ORD/000144/2022-2023 | 165/AE/USD | 28/06/2022 | 12/08/2022 | MA MANASA CONSTRUCTION | 4.84 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block | SM/07883 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block under Howrah Division, P.H.E Dte.(Phase-1). | AE/Ulu | JE/USD | ORD/000349/2022-2023 | 433/AE/USD | 13/09/2022 | 28/10/2022 | MA MANASA CONSTRUCTION | 4.85 | 4.81 | 99.23 | 0
5 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block | SM/07883 | Retrofitting | Additional laying of pipeline for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block under Howrah Division, P.H.E Dte.(Phase-4). | AE/Ulu | JE/USD | ORD/000352/2022-2023 | 436/AE/USD | 13/09/2022 | 28/10/2022 | MA MANASA CONSTRUCTION | 4.8 | 4.76 | 99.24 | 0
6 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block | SM/07883 | Retrofitting | Additional laying of pipeline for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block under Howrah Division, P.H.E Dte.(Phase-5). | AE/Ulu | JE/USD | ORD/000353/2022-2023 | 437/AE/USD | 13/09/2022 | 28/10/2022 | MA MANASA CONSTRUCTION | 4.79 | 4.76 | 99.41 | 0
7 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block | SM/07883 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000017/2021-2022 | 114/HD | 20/01/2022 | 20/01/2022 | Resource Division | 15.98 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block | SM/07883 | Retrofitting | Construction of boundary wall at HW site of Jhamtia W/S scheme in Uluberia Sub-division, under Howrah Division P.H.E Dte. ( Phase-1 ) | AE/Ulu | JE/USD | ORD/000385/2022-2023 | 472/AE/USD | 16/09/2022 | 31/10/2022 | TIYASA ENTERPRISE | 4.82 | 2.16 | 44.86 | 50
Total | [13 empty] | 129.47 | 103.18 | 79.69