## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-II) | SM/07884 | Retrofitting | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Zone-II) 2203 nos | AE/Ulu | JE/USD | ORD/000377/2021-2022 | 96/HD | 17/01/2022 | 03/03/2022 | DEV DAS SHAW | 82.22 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-II) | SM/07884 | Retrofitting | Additional laying of pipeline and internal pathway at Uttar & Dakhin Bhatora (Zone-II) Water Supply scheme in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu |  | ORD/000354/2021-2022 | 2440/HD | 29/12/2021 | 28/01/2022 | P B ENTERPRISE | 4.84 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-II) | SM/07884 | Retrofitting | Construction of boundary wall at 2nd TW site of Uttar & Dakhin Bhatora Zone-II w/s scheme in Uluberia Sub-Division under Howrah Division, P.H.E Dte. | AE/Ulu |  | ORD/000436/2022-2023 | 522/AE/USD | 27/09/2022 | 11/11/2022 | P B ENTERPRISE | 4.84 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-II) | SM/07884 | Retrofitting | Additional laying distribution pipeline and Road restoration at Village-Moyrachack of Amta-II Block under Uttar & Dakhin Bhatora PWSS under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu |  | ORD/000076/2025-2026 | 2762/HD | 12/06/2025 | 11/08/2025 | RANA ENTERPRISE | 56.75 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-II) | SM/07884 | Retrofitting | Additional Tube well of 250 X 150 mm Dia and 230 m deep by Direct Rotary method with UPVC Pipes all complete at vill-Moyrachack of Amta-II Block under Uttar & Dakhin Bhatora PWSS under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu |  | ORD/000068/2025-2026 | 2557/HD | 30/05/2025 | 29/06/2025 | PRANTIK DRILLING AGENCY | 14.71 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-II) | SM/07884 | Retrofitting | Construction of 1 no switch room (3.6m x 3.00 m ) with water supply & sanitary arrangement at TW sites of Moyrachack village under Uttar & Dakhin Bhatora PWSS under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu |  | ORD/000077/2025-2026 | 2763/HD | 12/06/2025 | 11/08/2025 | RANA ENTERPRISE | 6.86 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-II) | SM/07884 | Retrofitting | Supplying, fitting, fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Amta-II Block) (PART-A) | AE HQ | je_blk_ballyjag_how | ORD/000218/2025-2026 | 4116/HD | 14/10/2025 | 13/11/2025 | ABONTICA ENTERPRISE | 4.79 | 0 | 0 | 0
Total | [13 empty] | 175.01 | 0 | 0