## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-I) | SM/07885 | Retrofitting | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Zone-I) 1505 nos | AE/Ulu |  | ORD/000412/2021-2022 | 318/HD | 16/02/2022 | 02/04/2022 | GHOSH CONCERN | 58.39 | 51.23 | 87.75 | 0
2 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-I) | SM/07885 | Retrofitting | Work Order for Construction of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire around Other than head work site (2nd TW site) at Uttar & Dakhin Bhatora Zone-I of Amta-II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu |  | ORD/000056/2023-2024 | 1848/HD | 02/05/2023 | 01/07/2023 | SUNIL ENTERPRISE | 3.76 | 3.76 | 100 | 100
3 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block (Zone-I) | SM/07885 | Retrofitting | Additional laying distribution pipeline and Road restoration at Village-Moyrachack of Amta-II Block under Uttar & Dakhin Bhatora PWSS under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu |  | ORD/000076/2025-2026 | 2762/HD | 12/06/2025 | 11/08/2025 | RANA ENTERPRISE | 56.75 | 0 | 0 | 0
Total | [13 empty] | 118.9 | 54.99 | 46.25