## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Garbhabanipur Piped Water Supply Scheme under Udaynarayanpur Block | SM/07887 | Retrofitting | Work Order for Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Garbhabanipur Piped Water Supply Scheme under Udaynarayanpur Block under Howrah Division, PHE Dte. for 2275 nos. | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000567/2021-2022 | 733/HD | 31/03/2022 | 30/06/2022 | MITHU BUILDERS | 96.62 | 97.77 | 101.19 | 0
2 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Garbhabanipur Piped Water Supply Scheme under Udaynarayanpur Block | SM/07887 | Retrofitting | Construction of 2 storied switch room SLOPE ROOF (3.60m x 3.00m) with water supply & sanitary arrangement at 3rd TW site of Garbhabanipur PWSS of Udaynarayanpur Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000016/2025-2026 | 1936/HD | 21/04/2025 | 05/06/2025 | S.S ENTERPRISE | 8.81 | 0 | 0 | 100
3 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Garbhabanipur Piped Water Supply Scheme under Udaynarayanpur Block | SM/07887 | Retrofitting | Construction of boundary wall & Land Development at 2nd Tube well Site Garbhabanipur PWSS scheme under Udaynarayanpur Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000505/2024-2025 | 1037/HD | 24/02/2025 | 25/05/2025 | A.N ROY & CO | 9.67 | 0 | 0 | 100
4 | HOWRAH |  | Howrah Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Garbhabanipur Piped Water Supply Scheme under Udaynarayanpur Block | SM/07887 | Retrofitting | Construction of boundary wall & Land Development at HW Site Garbhabanipur PWSS scheme under Udaynarayanpur Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000504/2024-2025 | 1035/HD | 24/02/2025 | 24/06/2025 | BINOY KOLEY | 14.11 | 0 | 0 | 100
Total | [13 empty] | 129.2 | 97.77 | 75.67