## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Extension of Piped Water Supply to Anganwadi Centers (AWCs) under Howrah Division. | SM/07931 | Anganwadi | Work Order for Providing Tap Connection to Schools & ANGANWADI centers under Kulgachia PWSS under Uluberia-I Block under Uluberia Sub Division under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000768/2022-2023 | 735/HD | 23/02/2023 | 09/04/2023 | DEVEN ENTERPRISE | 1.99 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Extension of Piped Water Supply to Anganwadi Centers (AWCs) under Howrah Division. | SM/07931 | Anganwadi | Work Order for Providing Tap Connection to Schools & ANGANWADI centers under Shyampur-II Block under Uluberia Sub Division under Howrah Division, PHE Dte. | AE/Ulu | JE/RWS/Shyampur II | ORD/000769/2022-2023 | 736/HD | 23/02/2023 | 09/04/2023 | S.M. CONSTRUCTION | 3.83 | 1.98 | 51.76 | 100
3 | HOWRAH |  | Howrah Division | Extension of Piped Water Supply to Anganwadi Centers (AWCs) under Howrah Division. | SM/07931 | Anganwadi | Work Order for Providing Tap Connection to Schools & ANGANWADI centers under Shyampur-I Block under Uluberia Sub Division under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000789/2022-2023 | 864/HD | 01/03/2023 | 15/04/2023 | PRADIP KUMAR JATI | 9.13 | 3.44 | 37.65 | 100
4 | HOWRAH |  | Howrah Division | Extension of Piped Water Supply to Anganwadi Centers (AWCs) under Howrah Division. | SM/07931 | Anganwadi | Work Order for Providing Tap Connection to various awangari within Bagnan-I Block under Uluberia Sub Division under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000900/2022-2023 | 1102/HD | 17/03/2023 | 01/04/2023 | LOKENATH ENTERPRISES | 2.78 | 2.48 | 89.29 | 100
5 | HOWRAH |  | Howrah Division | Extension of Piped Water Supply to Anganwadi Centers (AWCs) under Howrah Division. | SM/07931 | Anganwadi | Work Order for Providing Tap Connection to various Schools within Bagnan-I Block under Uluberia Sub Division under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000901/2022-2023 | 1103/HD | 17/03/2023 | 01/04/2023 | LOKENATH ENTERPRISES | 6.65 | 6.62 | 99.57 | 100
6 | HOWRAH |  | Howrah Division | Extension of Piped Water Supply to Anganwadi Centers (AWCs) under Howrah Division. | SM/07931 | Anganwadi | Making provision of Running water arrangement with sinking of Tube well (100 x 40mm), 180 mtr deep along with installation of 1.0 HP Submersible pump including making water supply plumbing arrangement at Kandua AWC & Kandua Primary School under Amta-I Block under Uluberia Sub-Division under Howrah Division PHE Dte. | AE/Ulu | JE/USD | ORD/000584/2023-2024 | 3103/AE/USD | 29/02/2024 | 14/04/2024 | CHANDRANI ENTERPRISE | 1.84 | 1.82 | 98.93 | 100
Total | [13 empty] | 26.23 | 16.34 | 62.32