## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Rejuvenation of Amta Piped water supply scheme. | SM/08966 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000040/2022-2023 | 2639/HD | 09/12/2022 | 09/12/2022 | Resource Division | 68.93 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Rejuvenation of Amta Piped water supply scheme. | SM/08966 | Augmentation | Indent of Material |  |  | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 14/03/2022 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
3 | HOWRAH |  | Electrical | Rejuvenation of Amta Piped water supply scheme. | SM/08966 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rejuvenation of Amta water supply scheme, Zone - I, T.W. No. II, Block: Amta-I, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | ORD/000106/2022-2023 | 587/ED | 02/02/2023 | 03/05/2023 | D. K. ELECTRIC | 11.25 | 0 | 0 | 30
4 | HOWRAH |  | Electrical | Rejuvenation of Amta Piped water supply scheme. | SM/08966 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rejuvenation of Amta water supply scheme, Zone - I, T.W. No. I, Block: Amta-I, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | ORD/000107/2022-2023 | 588/ED | 02/02/2023 | 03/05/2023 | D. K. ELECTRIC | 11.25 | 0 | 0 | 30
5 | HOWRAH |  | Electrical | Rejuvenation of Amta Piped water supply scheme. | SM/08966 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rejuvenation of Amta water supply scheme, T.W. No.- III, Block: Amta-I, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | ORD/000060/2023-2024 | 1612/ED | 10/04/2023 | 09/07/2023 | D. K. ELECTRIC | 11.18 | 0 | 0 | 1
6 | HOWRAH |  | Electrical | Rejuvenation of Amta Piped water supply scheme. | SM/08966 | Augmentation | Quotation Bill for New Service Connection at Ranapara W/S. Sch. Amta-I |  |  | BILL/03888/2023-2024 | 298 | 21/09/2023 | 21/09/2023 | WBSEDCL | 5.12 | 0 | 0 | 0
7 | HOWRAH |  | Electrical | Rejuvenation of Amta Piped water supply scheme. | SM/08966 | Augmentation | Quotation bill for New Service Connection at Rej. of Amta W/S. Sch. PH-I |  |  | BILL/00796/2022-2023 | 160 | 15/02/2023 | 15/02/2023 | WBSEDCL | 11.41 | 0 | 0 | 0
8 | HOWRAH |  | Electrical | Rejuvenation of Amta Piped water supply scheme. | SM/08966 | Augmentation | Quotation Bill For New Service Connection at Rej. Amta. PH-II |  |  | BILL/00795/2022-2023 | 160 | 15/02/2023 | 15/02/2023 | WBSEDCL | 0.36 | 0 | 0 | 0
9 | HOWRAH |  | Electrical | Rejuvenation of Amta Piped water supply scheme. | SM/08966 | Augmentation | Quotation Bill for New Service Connection at Rej. of Amta W/S. Sch. |  |  | BILL/01566/2022-2023 | 200 | 17/03/2023 | 17/03/2023 | WBSEDCL | 2.7 | 0 | 0 | 0
10 | HOWRAH |  | Electrical | Rejuvenation of Amta Piped water supply scheme. | SM/08966 | Augmentation | Quotation Bill for New Service Connection at Rej. of Amta W/S. Sch. |  |  | BILL/01568/2022-2023 | 200 | 17/03/2023 | 17/03/2023 | WBSEDCL | 2.48 | 0 | 0 | 0
11 | HOWRAH |  | Howrah Division | Rejuvenation of Amta Piped water supply scheme. | SM/08966 | Augmentation | Work Order for 1 (One) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at 3rd TW site, Additional laying of pipeline and ancilary works for Zone-I, II, III and Construction of 2nos 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at Augmentation of Rejuvenation of Amta PWSS Zone-II & III 3rd TW site FOR ADDITIONAL WORK AT REJUVENATION OF AMTA PWSS OF AMTA-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. | AE/Ulu | JE/USD | ORD/000868/2022-2023 | 1352/HD | 27/03/2023 | 25/07/2023 | SAMIRON GHOSH | 399.6 | 0 | 0 | 100
12 | HOWRAH |  | Electrical | Rejuvenation of Amta Piped water supply scheme. | SM/08966 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Rejuvenation of AMTA water supply scheme, T.W. No. II (Replacement tubwell at PWD premises), Block: Amta-I, District - Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer6 | ORD/000064/2023-2024 | 1837/ED | 28/04/2023 | 27/07/2023 | D. K. ELECTRIC | 8.36 | 0 | 0 | 25
13 | HOWRAH |  | Electrical | Rejuvenation of Amta Piped water supply scheme. | SM/08966 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Amta (Ranapara) water supply scheme, T.W. No.-II, Block: Amta-II, District - Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer6 | ORD/001386/2023-2024 | 4736/ED | 15/12/2023 | 14/03/2024 | D. K. ELECTRIC | 10.74 | 0 | 0 | 100
14 | HOWRAH |  | Howrah Division | Rejuvenation of Amta Piped water supply scheme. | SM/08966 | Augmentation | Permanent restoration work of portable damage stretches of Ranihati-Haridaspur Amta Road from 15.40 Km to 16.70 Km due to laying of Water Supply Pipe Line by PHE i.c.w Rejuvenation of Amta Water Supply Scheme (Zone-II) |  |  | BILL/00033/2024-2025 | BP-2024-25-9 | 08/04/2024 | 08/04/2024 | EXECUTIVE ENGINEER HIGHWAY DIVISION P W ROADS HOWRAH | 20.73 | 0 | 0 | 0
15 | HOWRAH |  | Howrah Division | Rejuvenation of Amta Piped water supply scheme. | SM/08966 | Augmentation | Work Order for Sinking of Big dia Rig Bored Tube well 4 nos (300 x 250 mm x 250 mtr)for Zone-I, II & III, Land development of Head work site and 2nd Tube well site , Construction of boundary wall at 2nd Tube well Site (Zone-I), HW Site (Zone-I & III), Laying Distribution System Zone-I, Zone-II and Zone-III , FHTC Zone-I(3227), Zone-II(4732), Zone-III(2022), Construction of Two storied switch room ( 5.4 x 3.6) with water supply & sanitary arrangement cum godown at Head Work site of Zone-I,& Zone-III,Construction of switch room ( 3.60 m x 3.0 m) with water supply & sanitary arrangement at 2nd tube well Zone-I, Construction of 600 Cum OHR 20 mtr Staging Height (Zone-I) with pile foundation including soil test &design of piles, Constructionof 400 Cum OHR 20 mtr Staging Height (Zone-III) with pile foundation including soil test & design of piles, Interconnection 2nd Tube Well and First Tube Well ( Zone-I and Zone-III)of Rejuvenation of Amta Water Supply Scheme of Amta- I Block under Howrah Division, PHE Dte | AE/Ulu | JE/USD | ORD/000196/2022-2023 | 1637/HD | 10/08/2022 | 10/02/2024 | SAMIRON GHOSH | 1572.76 | 0 | 0 | 50
16 | HOWRAH |  | Howrah Division | Rejuvenation of Amta Piped water supply scheme. | SM/08966 | Augmentation | Additional FHTC at Rejuvenation of Amta PWSS (Zone-I) of Amta-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte.(SM/08966) | AE/Ulu | JE/USD | ORD/000121/2024-2025 | 3958/HD | 10/09/2024 | 09/03/2025 | ADITYA HAZRA | 54.31 | 0 | 0 | 100
Total | [13 empty] | 2704.38 | 0 | 0