## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Bagnan-I | Electrical | Chakur water supply scheme. | SM/08987 | New | Supply, Delivery & Installation of S/P/M & other Electrical/Mechanical equipments etc. including allied works for Chakur W/S. Sch. Howrah | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000005/2022-2023 | 781/ED | 05/05/2022 | 05/05/2023 | D. K. ELECTRIC | 10.41 | 9.61 | 92.31 | 0
2 | HOWRAH | Bagnan-I | Central Drilling | Chakur water supply scheme. | SM/08987 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 230 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR CHAKUR W/S SCH (Z-II), BAGNAN-I BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000260/2022-2023 | 308/CDD | 27/04/2022 | 27/05/2022 | PADMA ENGINEERING & CO. | 10.33 | 9.15 | 88.64 | 0
3 | HOWRAH | Bagnan-I | Howrah Division | Chakur water supply scheme. | SM/08987 | New | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Chamrail Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-D) No. of House Hold= 110 nos. |  |  | VCH/000813/2021-2022 | BP-2021-22-365 | 28/02/2022 | 28/02/2022 | APEX ENGINEERING | 2.77 | 0 | 0 | 0
4 | HOWRAH | Bagnan-I | Howrah Division | Chakur water supply scheme. | SM/08987 | New | WBSRDA |  |  | VCH/000570/2022-2023 |  | 07/09/2022 | 07/09/2022 | WBSRDA | 17.22 | 0 | 0 | 0
5 | HOWRAH | Bagnan-I | Howrah Division | Chakur water supply scheme. | SM/08987 | New | Chakur W/S Scheme. |  |  | VCH/000911/2021-2022 | BP-2021-22-482 | 30/03/2022 | 30/03/2022 | JAHANGIR ALAM | 58.28 | 0 | 0 | 0
6 | HOWRAH | Bagnan-I | Electrical | Chakur water supply scheme. | SM/08987 | New | Chakur water supply scheme. |  |  | VCH/002477/2021-2022 | 21-22/134 | 22/03/2022 | 22/03/2022 | WBSEDCL | 7.32 | 0 | 0 | 0
7 | HOWRAH | Bagnan-I | Howrah Division | Chakur water supply scheme. | SM/08987 | New | WBSRDA PAYMENT |  |  | VCH/000565/2022-2023 |  | 07/09/2022 | 07/09/2022 | WBSRDA | 17.22 | 0 | 0 | 0
8 | HOWRAH | Bagnan-I | Electrical | Chakur water supply scheme. | SM/08987 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Chakur water supply scheme, T.W. No. I, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000145/2022-2023 | 3528/ED | 30/12/2022 | 30/03/2023 | DAS ENTERPRISE | 10.66 | 10.38 | 97.31 | 0
9 | HOWRAH | Bagnan-I | Howrah Division | Chakur water supply scheme. | SM/08987 | New | Development of 2nd Tube well at Chakur PWSS of Bagnan-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu |  | ORD/000871/2022-2023 | 942/AE/USD | 22/03/2023 | 21/04/2023 | LOKENATH ENTERPRISES | 0.71 | 0.71 | 100 | 100
10 | HOWRAH | Bagnan-I | Howrah Division | Chakur water supply scheme. | SM/08987 | New | Material Requisition To Resource Division |  |  | RTOR000023/2021-2022 | 408/HD | 24/02/2022 | 24/02/2022 | Resource Division | 11.59 | 0 | 0 | 0
11 | HOWRAH | Bagnan-I | Howrah Division | Chakur water supply scheme. | SM/08987 | New | Material Requisition To Resource Division |  |  | RTOR000007/2022-2023 | 1222/HD | 09/06/2022 | 09/06/2022 | Resource Division | 1.35 | 0 | 0 | 0
12 | HOWRAH | Bagnan-I | Electrical | Chakur water supply scheme. | SM/08987 | New | Quotation Bill for New Service Connection at of Chakur W/S. Sch. PH-I |  |  | BILL/01914/2022-2023 | 02 | 11/04/2023 | 11/04/2023 | WBSEDCL | 0.69 | 0 | 0 | 0
13 | HOWRAH | Bagnan-I | Electrical | Chakur water supply scheme. | SM/08987 | New | Quotation bill for new service connection of WBSEDC at Chakur w/s scheme, T.W. No.-I |  |  | BILL/00779/2022-2023 | 150 | 08/02/2023 | 08/02/2023 | WBSEDCL | 2.74 | 0 | 0 | 0
14 | HOWRAH | Bagnan-I | Howrah Division | Chakur water supply scheme. | SM/08987 | New | Balance work in connection with water supply & sanitary arrangement of Pump House at Head Work site of Chakur Pipes water supply scheme of Bagnan-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000638/2023-2024 | 366/AE/USD | 21/08/2023 | 20/09/2023 | M.K.ENTERPRISE | 0.4 | 0 | 0 | 100
15 | HOWRAH | Bagnan-I | Howrah Division | Chakur water supply scheme. | SM/08987 | New | Work order for Ground Water Based Water Supply Scheme for Village CHAKUR of Bagnan I Block under Uluberia Sub-Division of Howrah Division, PHE Dte. | AE/Ulu | JE/USD | ORD/000372/2021-2022 | 69/HD | 11/01/2022 | 26/04/2025 | JAHANGIR ALAM | 162.65 | 77.42 | 47.6 | 83
16 | HOWRAH | Bagnan-I | Howrah Division | Chakur water supply scheme. | SM/08987 | New | Material Requisition To Resource Division |  |  | RTOR000045/2025-2026 | 4146/HD | 15/10/2025 | 15/10/2025 | Resource Division | 1.23 | 0 | 0 | 0
Total | [13 empty] | 315.57 | 107.26 | 33.99