## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Supply of Temporary drinking water by PVC water tankers(capacity 1000 liters) to different Cyclone (YASH) affected areas of Mahishadal Block of Purbo Midnapore District under Uluberia Sub Division under Howrah Division, PHE Dte. Name of Place- Mayachar (Part-1) | AE/Ulu |  | ORD/000462/2021-2022 | 1207/HD | 03/06/2021 | 18/06/2021 | PRADIP KUMAR JATI | 4.79 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order of Supply of Temporary drinking water by PVC water tankers(capacity 1000 liters) to different Cyclone (YASH) affected areas of Shyampur-I & II Block under Uluberia Sub Division under Howrah Division, PHE Dte. Name of Place- Saibania under DM Ghat-II GP | AE/Ulu |  | ORD/000469/2021-2022 | 1216/HD | 04/06/2021 | 19/06/2021 | NEW MAA TARA CONSTRUCTION | 4.62 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Supply of Temporary drinking water by PVC water tankers(capacity 1000 liters) to different Cyclone (YASH) affected areas of Bagnan-I Block under Uluberia Sub Division under Howrah Division, PHE Dte. Name of Place- Amrajole under Kalyanpur GP | AE/Ulu |  | ORD/000470/2021-2022 | 1217/HD | 04/06/2021 | 19/06/2021 | UNIVERSAL CONSTRUCTION | 4.83 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Supply of Temporary drinking water by PVC water tankers(capacity 1000 liters) to different Cyclone (YASH) affected areas of Bagnan-I Block under Uluberia Sub Division under Howrah Division, PHE Dte. Name of Place- Kalyanpur Masjid, Rotai under Kalyanpur GP | AE/Ulu |  | ORD/000472/2021-2022 | 1219/HD | 04/06/2021 | 19/06/2021 | UNIVERSAL CONSTRUCTION | 4.83 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Supply of Temporary drinking water by PVC water tankers(capacity 1000 liters) to different Cyclone (YASH) affected areas of Bagnan-I Block under Uluberia Sub Division under Howrah Division, PHE Dte. Name of Place- Paschim Bainan & Purba Bainan under Bainan GP (Part-2) | AE/Ulu |  | ORD/000474/2021-2022 | 1253/HD | 07/06/2021 | 22/06/2021 | ADITYA HAZRA | 1.42 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Temporary Supply of Drinking Water by PVC Water Tanks from different PWSS of various locations affected due to 'YASSH' Supercyclone at Domjur, Panchla, Jagatballavpur Block under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000497/2021-2022 | Camp-02/HD | 01/06/2021 | 06/06/2021 | M/S ASHIRBAD (INDIA) | 2.31 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Special renovation of damaged distribution Pipeline due to Cyclone YASH within the command area of Dakhin Durgapur w/s scheme under Howrah Division P.H.E Dte. | AE/Ulu |  | ORD/000216/2022-2023 | 220/AE/USD | 11/07/2022 | 10/08/2022 | PRADIP KUMAR JATI | 2.75 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Renovation of Pipeline damaged due to "Yash Cyclone" under Katagachi w/s scheme under Howrah Division P.H.E Dte. | AE/Ulu |  | ORD/000218/2022-2023 | 222/AE/USD | 11/07/2022 | 10/08/2022 | ASHOKE ENGINEERING WORKS | 1.18 | 0 | 0 | 0
9 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Renovation of Pipeline damaged due to "Yash Cyclone" under Bhagabanpur w/s scheme under Howrah Division P.H.E Dte. | AE/Ulu |  | ORD/000217/2022-2023 | 221/AE/USD | 11/07/2022 | 10/08/2022 | FARID UDDIN AHMED | 1.86 | 0 | 0 | 0
10 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for repairing of Pump house and Store room and ancillary work of HW site and 2nd TW site due to severe Cyclone "Yassh" of Shyampur Zone- II w/s scheme under Uluberia Sub-Division, of Howrah Division P.H.E Dte. | AE/Ulu |  | ORD/000198/2022-2023 | 204/AE/USD | 11/07/2022 | 10/08/2022 | NAG ENTERPRISE | 3.95 | 0 | 0 | 0
11 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Renovation of Pipeline damaged due to "Yash Cyclone" under Silampur w/s scheme under Uluberia Sub-Division under Howrah Division P.H.E Dte. | AE/Ulu |  | ORD/000212/2022-2023 | 216/AE/USD | 11/07/2022 | 10/08/2022 | MA- SITALA ENGINEERING WORKS. | 0.81 | 0 | 0 | 0
12 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for repairing of Pump house and Store room, boundary wall and ancillary work at 2nd TW site due to severe Cyclone "Yassh" of Belari w/s scheme under Uluberia Sub-Division, of Howrah Division P.H.E Dte. | AE/Ulu |  | ORD/000203/2022-2023 | 206/AE/USD | 11/07/2022 | 10/08/2022 | KALIDAS ENTERPRISE | 3.83 | 0 | 0 | 0
13 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Renovation of Pipeline damaged due to "Yash Cyclone" under Nischintapur w/s scheme under Howrah Division P.H.E Dte. | AE/Ulu |  | ORD/000214/2022-2023 | 218/AE/USD | 11/07/2022 | 10/08/2022 | DEV DAS SHAW | 1.76 | 0 | 0 | 0
14 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Special renovation of pipeline due to Cyclonic YASH at Deora High School to Renasa KG school, Deora Keopara pond side, Deora Atbala Bridge of Deora Water Supply scheme in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu |  | ORD/000215/2022-2023 | 219/AE/USD | 11/07/2022 | 10/08/2022 | S.S ENTERPRISE | 1.55 | 0 | 0 | 0
15 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Supply of Temporary drinking water by PVC water tankers(capacity 1000 liters) to different Cyclone (YASH) affected areas of Shyampur-I & II Block under Uluberia Sub Division under Howrah Division, PHE Dte. Name of Place- Bania under DM Ghat-I GP | AE/Ulu |  | ORD/000468/2021-2022 | 1209/HD | 03/06/2021 | 18/06/2021 | NEW MAA TARA CONSTRUCTION | 4.83 | 0 | 0 | 0
16 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Supply of Temporary drinking water by PVC water tankers(capacity 1000 liters) to different Cyclone (YASH) affected areas of Bagnan-I Block under Uluberia Sub Division under Howrah Division, PHE Dte. Name of Place- Baramahal under Kalyanpur GP | AE/Ulu |  | ORD/000471/2021-2022 | 1218/HD | 04/06/2021 | 19/06/2021 | UNIVERSAL CONSTRUCTION | 4.83 | 0 | 0 | 0
17 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Supply of Temporary drinking water by PVC water tankers(capacity 1000 liters) to different Cyclone (YASH) affected areas of Amta-II Block under Uluberia Sub Division under Howrah Division, PHE Dte. Name of Place- Mahishamori under Tajpur GP | AE/Ulu |  | ORD/000475/2021-2022 | 1254/HD | 07/06/2021 | 22/06/2021 | ADITYA HAZRA | 4.44 | 0 | 0 | 0
18 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Renovation of Pipeline damaged due to "Yash Cyclone" under Belari w/s scheme under Howrah Division P.H.E Dte. | AE/Ulu |  | ORD/000213/2022-2023 | 217/AE/USD | 11/07/2022 | 10/08/2022 | MA- SITALA ENGINEERING WORKS. | 1.17 | 0 | 0 | 0
19 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Supply of Temporary drinking water by PVC water tankers(capacity 1000 liters) to different Cyclone (YASH) affected areas of Mahishadal Block of Purbo Midnapore District under Uluberia Sub Division under Howrah Division, PHE Dte. Name of Place- Mayachar (Part-2) | AE/Ulu |  | ORD/000467/2021-2022 | 1208/HD | 03/06/2021 | 18/06/2021 | PRADIP KUMAR JATI | 1.77 | 0 | 0 | 0
20 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Alternative laying of distribution pipe line of Hallyan w/s scheme due to new construction of PMGSY Road / BGSY Road under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu |  | ORD/000296/2021-2022 | 2326/HD | 20/12/2021 | 19/01/2022 | JAHANGIR ALAM | 10.94 | 0 | 0 | 0
21 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Supply of Temporary drinking water by PVC water tankers(capacity 1000 liters) to different Cyclone (YASH) affected areas of Bagnan-I Block under Uluberia Sub Division under Howrah Division, PHE Dte. Name of Place- Paschim Bainan & Purba Bainan under Bainan GP (Part-1) | AE/Ulu |  | ORD/000473/2021-2022 | 1252/HD | 07/06/2021 | 22/06/2021 | ADITYA HAZRA | 4.8 | 0 | 0 | 0
22 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Laying of distribution pipe line for providing emergent water supply within the Howrah Zilla Parisad Bunglow campus for Silampur Water Supply Scheme under Shyampur-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. ( SL NO.-3 ) | AE/Ulu |  | ORD/000315/2022-2023 | 374/AE/USD | 30/08/2022 | 14/10/2022 | MJ ENTERPRISE | 1.88 | 0 | 0 | 0
23 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for repairing of Pump house and Store room and ancillary work of HW site and 2nd TW site due to severe Cyclone "Yassh" of Mellock Zone-I w/s scheme under Uluberia Sub-Division, of Howrah Division P.H.E Dte. | AE/Ulu |  | ORD/000201/2022-2023 | 202/AE/USD | 11/07/2022 | 10/08/2022 | SR TRADING CORPORATION | 3.47 | 0 | 0 | 0
24 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Sinking of 1 (one) no Replaced PVC big dia Tube well 300 mm x 200 mm dia of 240 mtr deep at Bagnan (Zone-I) under Bagnan Water Supply Scheme under Uluberia Sub-Division under Howrah Division P.H.E Dte. | AE/Ulu |  | ORD/000189/2022-2023 | 1514/HD | 22/07/2022 | 11/08/2022 | LOKENATH ENTERPRISES | 15.23 | 0 | 0 | 0
25 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Big Dia Tube at Mugkalyan Water Supply Scheme |  |  | VCH/000584/2022-2023 |  | 13/09/2022 | 13/09/2022 | EXEECUTIVE ENGINEER, CENTRAL DRILLING DIVISION, PHE DTE | 11.2 | 0 | 0 | 0
26 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for repairing of boundary wall, drain and internal pathway at Head work site damaged due to Cyclonic Yassh of Bagnan W/S scheme in uluberia Sub-Division, under Howrah Division P.H.E. Dte. |  |  | VCH/000701/2022-2023 | BP-2022-23-110 | 06/07/2022 | 06/07/2022 | BISWAJIT BAG | 4.95 | 0 | 0 | 0
27 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Supply of Temporary drinking water supply by PVC water tankers(capacity 1000 liters) to flood affected areas of Tajpur GP under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood -August 2021] | AE/Ulu |  | ORD/000492/2021-2022 | AE/USD(CAMP)/14 | 06/08/2021 | 13/08/2021 | DEBABRATA CHAKRABORTY | 0.42 | 0 | 0 | 0
28 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Disinfection of different type Hand tube wells in flood affected areas of Debipur GP & Harishpur GP of Udaynarayanpur Block under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood -October 2021] | AE/Ulu |  | ORD/000503/2021-2022 | AE/USD(CAMP)/22 | 08/10/2021 | 15/10/2021 | ADITYA HAZRA | 2.37 | 0 | 0 | 0
29 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Disinfection of different type hand tube wells in flood affected areas of Kanupat Monsukha GP & Sonatala GP of Udaynarayanpur Block under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood October 2021] | AE/Ulu |  | ORD/000504/2021-2022 | AE/USD(CAMP)/23 | 08/10/2021 | 15/10/2021 | BINOY KOLEY | 3.41 | 0 | 0 | 0
30 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Disinfection of different type of Hand tube wells in flood affected areas of Gazipur GP, Tajpur GP & Nopara(Part) and minor Repair of Hand Tube well of Amta-II Block under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood (2nd Phase) -August 2021] | AE/Ulu |  | ORD/000491/2021-2022 | AE/USD(CAMP)/13 | 06/08/2021 | 13/08/2021 | SITALAMATA PUMP CENTRE | 0.81 | 0 | 0 | 0
31 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Disinfection of different type of Hand tube wells in flood affected areas of Binola Krishna Bati GP of Amta-II Block under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood -October 2021] | AE/Ulu |  | ORD/000506/2021-2022 | AE/USD(CAMP)/25 | 08/10/2021 | 15/10/2021 | M/S AHAMED CONSTRUCTION | 1.28 | 0 | 0 | 0
32 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Disinfection of different type of Hand tube wells in flood affected areas of Bhatora GP of Amta-II Block under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood -October 2021] | AE/Ulu |  | ORD/000499/2021-2022 | AE/USD(CAMP)/18 | 08/10/2021 | 15/10/2021 | DEV DAS SHAW | 1.33 | 0 | 0 | 0
33 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Disinfection of different type of Hand tube wells in flood affected areas of Thalia GP of Amta-II Block under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood(2nd Phase) -August 2021] | AE/Ulu |  | ORD/000487/2021-2022 | AE/USD(CAMP)/09 | 06/08/2021 | 13/08/2021 | DEV DAS SHAW | 1.28 | 0 | 0 | 0
34 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work order for Disinfection of different type of Hand tube wells in flood affected areas of Amragori GP of Amta-II Block under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood(2nd Phase) -August 2021] | AE/Ulu |  | ORD/000488/2021-2022 | AE/USD(CAMP)/10 | 06/08/2021 | 13/08/2021 | M/S AHAMED CONSTRUCTION | 1.71 | 0 | 0 | 0
35 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Disinfection of different type of Hand tube wells in flood affected areas of Ghoraberia Chitnan GP of Amta-II Block under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood -October 2021] | AE/Ulu |  | ORD/000500/2021-2022 | AE/USD(CAMP)/19 | 08/10/2021 | 15/10/2021 | DEV DAS SHAW | 1.33 | 0 | 0 | 0
36 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Disinfection of different type of Hand tube wells in flood affected areas of Jhamti GP of Amta-II Block under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood -October 2021] | AE/Ulu |  | ORD/000513/2021-2022 | AE/USD(CAMP)/28 | 08/10/2021 | 15/10/2021 | ADITYA HAZRA | 0.95 | 0 | 0 | 0
37 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work order for Disinfection of different type of Hand tube wells in flood affected areas of Thalia GP of Amta-II Block under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood -October 2021] | AE/Ulu |  | ORD/000511/2021-2022 | AE/USD(CAMP)/26 | 08/10/2021 | 15/10/2021 | DEV DAS SHAW | 1.23 | 0 | 0 | 0
38 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Disinfection of different type of Hand tube wells in flood affected areas of Amragori GP of Amta-II Block under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood -October 2021] | AE/Ulu |  | ORD/000512/2021-2022 | AE/USD(CAMP)/27 | 08/10/2021 | 15/10/2021 | DEV DAS SHAW | 1.33 | 0 | 0 | 0
39 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work order for Disinfection of different type of Hand tube wells in flood affected areas of Binola Krishna Bati GP of Amta-II Block under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood(2nd Phase) -August 2021] | AE/Ulu |  | ORD/000486/2021-2022 | AE/USD(CAMP)/08 | 06/08/2021 | 13/08/2021 | DEV DAS SHAW | 1.04 | 0 | 0 | 0
40 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Disinfection of different type Hand tube wells in flood affected areas of Harali and RDA GP of Udaynarayanpur Block under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood -October 2021] | AE/Ulu |  | ORD/000505/2021-2022 | AE/USD(CAMP)/24 | 08/10/2021 | 15/10/2021 | BINOY KOLEY | 4.82 | 0 | 0 | 0
41 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Supply of Temporary drinking water supply by PVC water tankers(capacity 1000 liters) to flood affected areas of Bagnan-II GP under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood -August 2021] | AE/Ulu |  | ORD/000494/2021-2022 | AE/USD(CAMP)/16 | 06/08/2021 | 13/08/2021 | JAHANGIR ALAM | 0.42 | 0 | 0 | 0
42 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Disinfection of different type of Hand tube wells in flood affected areas of Bhatora GP of Amta-II Block under Uluberia Sub Division under Howrah Division, PHE Dte. [affected by Flood -August 2021] | AE/Ulu |  | ORD/000476/2021-2022 | AE/USD(CAMP)/01 | 05/08/2021 | 12/08/2021 | M/S AHAMED CONSTRUCTION | 1.23 | 0 | 0 | 0
43 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for repairing of Pump house and Store room boundary wall and ancillary work of HW site due to severe Cyclone "Yassh" of Belari w/s scheme under Uluberia Sub-Division, of Howrah Division P.H.E Dte. | AE/Ulu |  | ORD/000202/2022-2023 | 205/AE/USD | 11/07/2022 | 10/08/2022 | SHRI RANISATI VENTURES | 3.25 | 0 | 0 | 0
44 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for renovation of boundary wall of boundary wall at 3rd TW Site due to severe Cyclone "Yassh" of Baikhali W/S scheme in uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu |  | ORD/000209/2022-2023 | 213/AE/USD | 11/07/2022 | 10/08/2022 | S RAHA ENTERPRISE | 3.08 | 0 | 0 | 0
45 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for renovation of boundary wall at 2nd TW Site due to severe Cyclone "Yassh" of Mellock (Z-I) W/S scheme in uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu |  | ORD/000210/2022-2023 | 214/AE/USD | 11/07/2022 | 10/08/2022 | BANERJEE ENTERPRISE | 4.14 | 0 | 0 | 0
46 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for Reparing of Pipeline damaged due to "Yash Cyclone" under Shyampur w/s scheme under Howrah Division P.H.E Dte. | AE/Ulu |  | ORD/000222/2022-2023 | 223/AE/USD | 11/07/2022 | 10/08/2022 | NAG ENTERPRISE | 1.78 | 0 | 0 | 0
47 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for repairing of boundary wall and Pump Houses at HW, 2nd TW and 3rd TW Site due to severe Cyclone "Yassh" of Dakhin Durgapur W/S scheme in uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu |  | ORD/000199/2022-2023 | 207/AE/USD | 11/07/2022 | 10/08/2022 | S.M. CONSTRUCTION | 4.83 | 0 | 0 | 0
48 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for repairing of Pump house and Store room and ancillary work of HW site and 2nd TW site due to severe Cyclone "Yassh" of kalinagar w/s scheme under Uluberia Sub-Division, of Howrah Division P.H.E Dte. | AE/Ulu |  | ORD/000200/2022-2023 | 208/AE/USD | 11/07/2022 | 10/08/2022 | SK ANISUR | 4.83 | 0 | 0 | 0
49 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for renovation of Pump house and boundary wall at HW Site & 2nd Tw site due to severe Cyclone "Yassh" of Deuli W/S scheme in uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu |  | ORD/000207/2022-2023 | 211/AE/USD | 11/07/2022 | 10/08/2022 | NEW MAA TARA CONSTRUCTION | 4.84 | 0 | 0 | 0
50 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Repairing of Pump house and Store room and ancillary work of 3rd TW site due to severe Cyclone ¿Yassh¿ of Baikhali w/s scheme under Uluberia Sub-Division, of Howrah Division P.H.E Dte. | AE/Ulu |  | ORD/000346/2022-2023 | 412/AE/USD | 07/09/2022 | 22/10/2022 | S RAHA ENTERPRISE | 2.04 | 0 | 0 | 0
51 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Emergent repairing of Sub-Division office building and Rest shade within the campus of Uluberia Sub-Division office which were badly damaged due to Super cyclone Amphan & Yash of Bagnan W/S scheme in Uluberia Sub-Division, under Howrah Division P.H.E Dte. (SL NO.-3) | AE/Ulu |  | ORD/000338/2022-2023 | 385/AE/USD | 30/08/2022 | 14/10/2022 | PRIYANKA ENTERPRISE | 4.58 | 0 | 0 | 0
52 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for repairing of Pump house and Store room, Boundary wall and ancillary work of HW site and 2nd TW site due to severe Cyclone "Yassh" of Bhagabanpur w/s scheme under Uluberia Sub-Division, of Howrah Division P.H.E Dte. | AE/Ulu |  | ORD/000204/2022-2023 | 209/AE/USD | 11/07/2022 | 10/08/2022 | A.B. ENTERPRISE | 4.75 | 0 | 0 | 0
53 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Repairing of pipeline damaged due to "Yash Cyclone" under Shyampur Zone-II w/s scheme under Howrah Division P.H.E. Dte.( SL NO.- 1 ) | AE/Ulu |  | ORD/000311/2022-2023 | 372/AE/USD | 30/08/2022 | 14/10/2022 | NAG ENTERPRISE | 2.51 | 0 | 0 | 0
54 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Repairing of the Sub-Divisional office building and Rest shade which were damaged due to cyclonic storm "Yash" under Uluberia Sub-Division, under Howrah Division P.H.E Dte. (Phase-II). (SL NO.- 2) | AE/Ulu |  | ORD/000327/2022-2023 | 384/AE/USD | 30/08/2022 | 14/10/2022 | BISWAJIT BAG | 4.85 | 0 | 0 | 0
55 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for repairing of boundary wall, drain and internal pathway at Head work site damaged due to Cyclonic Yassh of Bagnan W/S scheme in Uluberia Sub-Division under Howrah Division P.H.E. Dte. | AE/Ulu |  | ORD/000143/2022-2023 | 164/AE/USD | 28/06/2022 | 12/08/2022 | BISWAJIT BAG | 4.85 | 0 | 0 | 0
56 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for renovation of boundary wall and Pump houses at HW Site & 2nd TW site due to severe Cyclone "Yassh" of Katagachi W/S scheme in uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu |  | ORD/000208/2022-2023 | 212/AE/USD | 11/07/2022 | 10/08/2022 | ASHOKE ENGINEERING WORKS | 4.82 | 0 | 0 | 0
57 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Repairing of Pump house and Store room and ancillary work of HW site and 2nd TW site due to severe Cyclone "Yassh" of Baikhali w/s scheme under Uluberia Sub-Division, of Howrah Division P.H.E Dte. | AE/Ulu |  | ORD/000344/2022-2023 | 411/AE/USD | 07/09/2022 | 22/10/2022 | KALIDAS ENTERPRISE | 4.84 | 0 | 0 | 0
58 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for renovation of boundary wall at HW Site due to severe Cyclone "Yassh" of Mellock (Z-I) W/S scheme in uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu |  | ORD/000211/2022-2023 | 215/AE/USD | 11/07/2022 | 10/08/2022 | ALLSOMA CONSTRUCTION | 4.16 | 0 | 0 | 0
59 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for repairing of Pump house and Store room and ancillary work of HW site and 2nd TW site due to severe Cyclone "Yassh" of Shyampur Zone-I w/s scheme under Uluberia Sub-Division, of Howrah Division P.H.E Dte. | AE/Ulu |  | ORD/000197/2022-2023 | 203/AE/USD | 11/07/2022 | 10/08/2022 | JAHANGIR ALAM | 3.5 | 0 | 0 | 0
60 | HOWRAH |  | Howrah Division | Restoration of damaged Pipeline and repairing of civil structure of different Piped Water Supply Scheme (PWSS) which were badly affected due to severe cyclonic storm YASSH within the Uluberia Sub-division under Howrah Division, PHE Dte | SM/09002 | Disaster | Work Order for renovation of boundary wall at 2nd Tw Site due to severe Cyclone "Yassh" of Silampur W/S scheme in uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu |  | ORD/000206/2022-2023 | 210/AE/USD | 11/07/2022 | 10/08/2022 | MA- SITALA ENGINEERING WORKS. | 4.38 | 0 | 0 | 0
Total | [13 empty] | 206.96 | 0 | 0