## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Retrofitting work for providing functional household tap connection (FHTC) from existing distribution system at Balichak PWSS. | SM/09105 | Retrofitting | Work Order for Construction of switch room ( 3.60 m x 3.0 m) with water supply & sanitary arrangement at 4th tube well site of Balichack PWSS of Amta-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. (As per approved drawing of Howrah Division, PHE Dte.) | AE/Ulu |  | ORD/000581/2022-2023 | 2598/HD | 07/12/2022 | 05/02/2023 | BINOY KOLEY | 4.7 | 0 | 0 | 100
Total | [13 empty] | 4.7 | 0 | 0