## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Mellok Brahman Dakuria | SM/09347 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Mellock Brahman Dhakuria PWSS, Bagnan-II Block Under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu | JE/USD | ORD/000253/2021-2022 | 2122/HD | 24/11/2021 | 09/12/2021 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.32 | 3.32 | 100 | 0
2 | HOWRAH |  | Central Drilling | Augmentation of Ground water based PWSS Mellok Brahman Dakuria | SM/09347 | Augmentation | SUPPLY & DELIVERY OF PEA SIZE GRAVELS CONSUMBLES AT SITE FOR CONSTRUCTION OF TUBE WELL IN DIFFERENT DISTRICT IN WEST BENGAL UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000139/2021-2022 | 189/ CMSD-I (D) | 30/09/2021 | 15/10/2021 | CHANDA ENTERPRISE | 4.8 | 1.08 | 22.49 | 0
3 | HOWRAH |  | Central Drilling | Augmentation of Ground water based PWSS Mellok Brahman Dakuria | SM/09347 | Augmentation | SUPPLY & DELIVERY OF BENTONITE POWDER SODIUM BASED CONSUMBLES AT SITE FOR CONSTRUCTION OF TUBE WELL IN DIFFERENT DISTRICT IN WEST BENGAL UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000252/2021-2022 | 190/ CMSD-I (D) | 30/09/2021 | 15/10/2021 | CHANDA ENTERPRISE | 2.93 | 0.59 | 20 | 0
4 | HOWRAH |  | Central Drilling | Augmentation of Ground water based PWSS Mellok Brahman Dakuria | SM/09347 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 230 MTRS DEPTH) BY DEPARTMENTAL RIG MACHINE FOR AMRAGORI PWSS, AMTA-II BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. |  |  | ORD/000050/2022-2023 | 299/CMSD-I (D) | 08/07/2022 | 23/07/2022 | DIPALI CONSTUCTION | 3.11 | 1.98 | 63.68 | 0
5 | HOWRAH |  | Central Drilling | Augmentation of Ground water based PWSS Mellok Brahman Dakuria | SM/09347 | Augmentation | PROVIDING TUBE WWLL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT AUG. OF MELLOCK PWSS, BANGAN-II BLOCK, HOWRAH DISTRICT UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000115/2022-2023 | 392/CMSD-II (D) | 01/08/2022 | 16/08/2022 | M/S PRACHI ENGINEERING | 4.99 | 4.67 | 93.56 | 0
6 | HOWRAH |  | Central Drilling | Augmentation of Ground water based PWSS Mellok Brahman Dakuria | SM/09347 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT AUG. OF MELLOCK, BAGNAN-II BLOCK, HOWRAH DISTRICT UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000116/2022-2023 | 391/CMSD-II (D) | 01/08/2022 | 16/08/2022 | M/S PRACHI ENGINEERING | 4.04 | 3.86 | 95.53 | 0
7 | HOWRAH |  | Central Drilling | Augmentation of Ground water based PWSS Mellok Brahman Dakuria | SM/09347 | Augmentation | CONSTRUCTION OF TUBE WELL IN HOWRAH DISTRICT BY UTILIZING SKILLED DEPARTMENTAL CREW AND DEPARTMENTAL MACHINERIES OF CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000117/2022-2023 | 239/CMSD-II (D) | 20/05/2022 | 04/06/2022 | CHANDA ENTERPRISE | 4.83 | 3.87 | 80.17 | 0
8 | HOWRAH |  | Central Drilling | Augmentation of Ground water based PWSS Mellok Brahman Dakuria | SM/09347 | Augmentation | PROVIDING PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL AT MELLOK, AMTA-II BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. |  |  | ORD/000119/2022-2023 | 298/CMSD-I (D) | 08/07/2022 | 23/07/2022 | DIPALI CONSTUCTION | 2.09 | 1.79 | 85.77 | 0
9 | HOWRAH |  | Central Drilling | Augmentation of Ground water based PWSS Mellok Brahman Dakuria | SM/09347 | Augmentation | SUPPLY & DELIVERY OF CONSUMABLES AT SITE WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL AT AUG. OF MELLOCK PWSS, BAGNAN-II BLOCK, HOWRAH DISTRICT UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000114/2022-2023 | 393/CMSD-II (D) | 01/08/2022 | 16/08/2022 | M/S PRACHI ENGINEERING | 1.88 | 1.79 | 94.83 | 0
10 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Mellok Brahman Dakuria | SM/09347 | Augmentation | Indent of Material |  |  | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 14/03/2022 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
11 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Mellok Brahman Dakuria | SM/09347 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Mellok Brahmandakuria water supply scheme, Head work site, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000190/2022-2023 | 783/ED | 09/02/2023 | 10/05/2023 | DIPALI CONSTRUCTION | 10.79 | 10.42 | 96.55 | 1
12 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Mellok Brahman Dakuria | SM/09347 | Augmentation | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. |  |  | ORD/000617/2023-2024 | 933/HMSD | 18/04/2023 | 18/09/2023 | S.P. CONSTRUCTION | 0.4 | 0.4 | 100 | 40
13 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Mellok Brahman Dakuria | SM/09347 | Augmentation | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Hooghly District) |  |  | ORD/000618/2023-2024 | 959/HMSD | 20/04/2023 | 21/10/2023 | SANJIB PRADHAN | 0.38 | 0.38 | 100 | 40
14 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Mellok Brahman Dakuria | SM/09347 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Mellok Brahmandakuria water supply scheme, T.W. No.- II, Block: Bagnan, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000862/2023-2024 | 3434/ED | 11/08/2023 | 09/11/2023 | DIPALI CONSTRUCTION | 10.74 | 10.42 | 97 | 50
15 | HOWRAH |  | Central Drilling | Augmentation of Ground water based PWSS Mellok Brahman Dakuria | SM/09347 | Augmentation | CONSTRUCTION OF TUBE WELL (250MM X 150MM X DEPTH 220 MTRS) FOR IIEST (TW-I), MELLOK, HOWRAH DISTRICT BY UTILIZING SKILLED DEPARTMENTAL CREW AND DEPARTMENTAL MACHINERIES OF CDD, PHE DTE. |  |  | ORD/000120/2022-2023 | 400/CDD | 20/05/2022 | 19/06/2022 | ASHUTOSH DAS & CO | 10.05 | 4.61 | 45.82 | 0
16 | HOWRAH |  | Central Drilling | Augmentation of Ground water based PWSS Mellok Brahman Dakuria | SM/09347 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 230 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR MELLOCK W/S SCH (Z-II, HW), BAGNAN-I BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000294/2022-2023 | 307/CDD | 27/04/2022 | 27/05/2022 | PADMA ENGINEERING & CO. | 10.33 | 9.7 | 93.94 | 0
17 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Mellok Brahman Dakuria | SM/09347 | Augmentation | Development of 2nd Tube well at Mellock Bramhan Dkhakuria PWSS of Bagnan-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu |  | ORD/000869/2022-2023 | 941/AE/USD | 22/03/2023 | 21/04/2023 | LOKENATH ENTERPRISES | 0.71 | 0.71 | 100 | 100
18 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Mellok Brahman Dakuria | SM/09347 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000091/2022-2023 | 775/HD | 24/02/2023 | 24/02/2023 | Resource Division | 46.08 | 0 | 0 | 0
19 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Mellok Brahman Dakuria | SM/09347 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000037/2023-2024 | 2753/HD | 28/07/2023 | 28/07/2023 | Resource Division | 12.32 | 0 | 0 | 0
20 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Mellok Brahman Dakuria | SM/09347 | Augmentation | Quatation Bill for New Service Connection of WBSEDCL at Mellock Brahmandakuria P-III W/S. Sch. |  |  | BILL/00741/2022-2023 | 141 | 20/01/2023 | 20/01/2023 | WBSEDCL | 2.6 | 0 | 0 | 0
21 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Mellok Brahman Dakuria | SM/09347 | Augmentation | NEW SERVICE CONNECTION FOR AUGMENTATION OF MELLOK BRAHMANDAKURIA PH NO-II |  |  | BILL/00756/2023-2024 | 41 | 17/05/2023 | 17/05/2023 | WBSEDCL | 2.74 | 0 | 0 | 0
22 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Mellok Brahman Dakuria | SM/09347 | Augmentation | Work Order for Construction of switch room (5.40m x 3.60 m) with water supply & sanitary arrangement at Head Work site of Augumentation of Mellock Brahman Dakuria PWSS of Bagnan-II Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. (As per approved drawing of Howrah Division, PHE Dte.) | AE/Ulu |  | ORD/000579/2022-2023 | 2596/HD | 07/12/2022 | 05/02/2023 | LOKENATH ENTERPRISES | 6.24 | 6.14 | 98.34 | 100
23 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Mellok Brahman Dakuria | SM/09347 | Augmentation | Work Order for Laying of Distribution System with providing FHTC for Augmentation of Mellock Brahman Dakuria PWSS of Bagnan-I & Bagnan-II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. [Mouza-Masiyara, Sondail, Bramhan Dhakuria- House Hold- 950 nos] (Part-B) | AE/Ulu | JE/USD | ORD/000396/2022-2023 | 1996/HD | 26/09/2022 | 10/11/2022 | CREATION CONSTRUCTION | 107.55 | 47.08 | 43.77 | 100
24 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Mellok Brahman Dakuria | SM/09347 | Augmentation | Work Order for Interconnection between tube wells & OHR at Mellock Bramhan Dkhakuria PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000052/2023-2024 | 1844/HD | 02/05/2023 | 01/07/2023 | GLOBUS CONSULTANCY | 7.34 | 4.63 | 63.11 | 100
25 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Mellok Brahman Dakuria | SM/09347 | Augmentation | Additional Laying of pipeline Mellock Brahman Dhakuria PWSS of Bagnan-I & II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Sondail & Masiyara) | AE/Ulu | JE/USD | ORD/000527/2023-2024 | 2033/AE/USD | 13/02/2024 | 13/04/2024 | DUNCON INDIA | 16.52 | 16.51 | 99.98 | 100
26 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Mellok Brahman Dakuria | SM/09347 | Augmentation | Work Order for Laying of Distribution System with providing FHTC and Construction of 400 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), for Augumentation of Mellock Brahman Dakuria PWSS of Bagnan-I & Bagnan-II Block under Uluberia Sub Division under Howrah Division P.H.E. Dte. in the District of Howrah.[Mouza-Subsit, House Hold- 1454] (Part-A) | AE/Ulu | JE/USD | ORD/000485/2022-2023 | 2170/HD | 21/10/2022 | 01/04/2025 | GHOSH CONCERN | 310.35 | 200.23 | 64.52 | 70
27 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Mellok Brahman Dakuria | SM/09347 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000053/2025-2026 | 4146/HD | 15/10/2025 | 15/10/2025 | Resource Division | 1.23 | 0 | 0 | 0
Total | [13 empty] | 1101.55 | 334.16 | 30.34