## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Pancharul | SM/09348 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Pancharul PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000251/2021-2022 | 2110/HD | 24/11/2021 | 09/12/2021 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.16 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Pancharul | SM/09348 | Augmentation | Work Order for Sinking of 2 (Two) nos PVC big dia Tube well 300 mm x 200 mm dia of 250 mtr deep for Augmentation of Pancharul W/S scheme at Udaynarayanpur Block in Uluberia Sub-Division P.H.E. Dte. under Howrah Division, P.H.E Dte. | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000108/2022-2023 | 1268/HD | 17/06/2022 | 17/07/2022 | M/S SYCHROTECH INDUSTRY | 34.92 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Pancharul | SM/09348 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000042/2022-2023 | 2639/HD | 09/12/2022 | 09/12/2022 | Resource Division | 21.34 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Pancharul | SM/09348 | Augmentation | Indent of Material |  |  | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 14/03/2022 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Pancharul | SM/09348 | Augmentation | Work Order for Laying Distribution System & providing Functional Household Tap Connection(FHTC) Kakraipota Mouza (570 nos) from existing distribution system at Augementation of Pancharul Piped Water Supply Scheme under Udaynaraunpur Block under Howrah Division, PHE Dte. (Part-B). | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000530/2021-2022 | 627/HD | 22/03/2022 | 06/05/2022 | ADITYA HAZRA | 95.54 | 0 | 0 | 0
6 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Pancharul | SM/09348 | Augmentation | Supply, delivery and installation of voltage correcting device and other allied works for Pancharul water supply scheme, T.W. No. II (Replacement tubewell), Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/001031/2022-2023 | 496/HMSD | 02/03/2023 | 01/04/2023 | SUDIKSHA CONSTRUCTION | 3.95 | 0 | 0 | 100
7 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Pancharul | SM/09348 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Pancharul water supply scheme, T.W. No.- II (Replacement tubewell), Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/001033/2022-2023 | 2106/HMSD | 24/11/2022 | 24/12/2022 | WIZARDTECH SOLUTION | 4.67 | 0 | 0 | 0
8 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Pancharul | SM/09348 | Augmentation | Installation of departmentally supplied submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Pancharul water supply scheme, T.W. No. I(Replacement tubewell), Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/001162/2022-2023 | 2147/HMSD | 29/11/2022 | 06/12/2022 | DAS ENTERPRISE | 0.63 | 0 | 0 | 0
9 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Pancharul | SM/09348 | Augmentation | Supply, delivery of submersible pumping machinery and other electrical/ mechanical equipments etc. for Pancharul water supply scheme, T.W. No. I(Replacement tubewell), Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/001163/2022-2023 | 2064/HMSD | 22/11/2022 | 29/11/2022 | DAS ENTERPRISE | 0.97 | 0 | 0 | 0
10 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Pancharul | SM/09348 | Augmentation | Supply, delivery of electrical/ mechanical equipments for Pancharul water supply scheme, T.W. No. I(Replacement tubewell), Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/001164/2022-2023 | 2063/HMSD | 22/11/2022 | 29/11/2022 | DAS ENTERPRISE | 0.96 | 0 | 0 | 0
11 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Pancharul | SM/09348 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2022-2023 | 1624/HD | 05/08/2022 | 05/08/2022 | Resource Division | 21.34 | 0 | 0 | 0
12 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Pancharul | SM/09348 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000035/2023-2024 | 2753/HD | 28/07/2023 | 28/07/2023 | Resource Division | 12.32 | 0 | 0 | 0
13 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Pancharul | SM/09348 | Augmentation | Work Order for Laying Distribution System & providing Functional Household Tap Connection(FHTC) Pancharul Mouza for (1567 nos) from existing distribution system at Augmentation of Pancharul Piped Water Supply Scheme under Udaynaraunpur Block under Howrah Division, PHE Dte. Pancharul Mouza for 1567 nos (Part-C) | AE/Ulu | JE/USD | ORD/000033/2022-2023 | 1002/HD | 02/05/2022 | 16/06/2022 | CREATION CONSTRUCTION | 121.95 | 0 | 0 | 100
14 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Pancharul | SM/09348 | Augmentation | Work Order for Laying Distribution System & providing Functional Household Tap Connection(FHTC) Subal Chack Mouza for (372 nos) from existing distribution system at Augmentation of Pancharul Piped Water Supply Scheme under Udaynaraunpur Block under Howrah Division, PHE Dte. (Part-D) | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000529/2021-2022 | 626/HD | 22/03/2022 | 06/05/2022 | MODERN CONSTRUCTION | 59.54 | 0 | 0 | 100
15 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Pancharul | SM/09348 | Augmentation | Additional Laying of distribution pipeline with FHTC at Mouza-Kakraipota for Augmentation of Pancharul PWSS of Udaynarayanpur Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000013/2024-2025 | 2646/HD | 07/06/2024 | 06/08/2024 | ADITYA HAZRA | 50.3 | 0 | 0 | 100
16 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Pancharul | SM/09348 | Augmentation | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Udaynarayanpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000282/2024-2025 | 4813/HD | 19/11/2024 | 19/03/2025 | HORIZEN | 13.59 | 0 | 0 | 60
17 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Pancharul | SM/09348 | Augmentation | Work Order for "Augmentation of Pancharul Water Supply scheme by Laying Distribution System, providing Functional Household Tap Connection(FHTC) work with GEO tagging of using Jal Swapna App, Construction of R.C.C Elevated Reservoir of Capacity 500 m3 of Staging Height 20 mtr including Soil Investigation, interconnection & Rising main between 2nd TW, 1st Tube well (HW site) & OHR under Howrah Division, P.H.E. Dte. (Part-A)" | AE/RWS,AE/Ulu | JE/USD | ORD/000129/2022-2023 | 1338/HD | 27/06/2022 | 29/01/2025 | JAHANGIR ALAM | 232.99 | 0 | 0 | 100
Total | [13 empty] | 1192.37 | 0 | 0