## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Mankur Deulgram | SM/09349 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Mankur & Deulgram PWSS, Bagnan-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu |  | ORD/000252/2021-2022 | 2121/HD | 24/11/2021 | 09/12/2021 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.58 | 4.58 | 100 | 0
2 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Mankur Deulgram | SM/09349 | Augmentation | Indent of Material |  |  | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 14/03/2022 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Mankur Deulgram | SM/09349 | Augmentation | Work Order for alternative laying of damaged UPVC pipe,construction of RCC stand post, valve chamber and other allied work at Mankur Water Supply scheme in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu |  | ORD/000538/2021-2022 | 670/HD | 23/03/2022 | 22/04/2022 | S.S ENTERPRISE | 4.9 | 4.86 | 99.23 | 0
4 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Mankur Deulgram | SM/09349 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Mankur Deulgram water supply scheme, T.W. No. III, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000868/2023-2024 | 3441/ED | 11/08/2023 | 09/11/2023 | M.S.C. ENTERPRISE | 11.5 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Mankur Deulgram | SM/09349 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000036/2023-2024 | 2753/HD | 28/07/2023 | 28/07/2023 | Resource Division | 15.4 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Mankur Deulgram | SM/09349 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000059/2023-2024 | 4695/HD | 26/12/2023 | 26/12/2023 | Resource Division | 48.28 | 0 | 0 | 0
7 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Mankur Deulgram | SM/09349 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Mankur Deulgram water supply scheme, T.W. No.- I & II, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000247/2022-2023 | 914/ ED | 22/02/2023 | 23/05/2023 | A.G. ENTERPRISE | 23.02 | 11.14 | 48.39 | 50
8 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Mankur Deulgram | SM/09349 | Augmentation | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Mankur Deulgram PWSS at Bagnan-I Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu |  | ORD/000334/2022-2023 | 1833/HD | 08/09/2022 | 18/10/2022 | AUXILIARY TUBEWELL DRILLERS | 35.39 | 32.28 | 91.21 | 100
9 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Mankur Deulgram | SM/09349 | Augmentation | Temporary Approach road towards Head works site for Augmentation of Makur Deulgram PWSS of Bagnan-I Block under Uluberia Sub Division under Howrah Divison PHE Dte. | AE/Ulu | JE/USD | ORD/000529/2023-2024 | 2037/AE/USD | 13/02/2024 | 13/04/2024 | NOBLE ENTERPRISE | 2 | 1.91 | 95.57 | 100
10 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Mankur Deulgram | SM/09349 | Augmentation | Construction of switch room ( 3.60 m x 3.0 m) with water supply & sanitary arrangement at 3rd tube well site of Mankur Deulgram PWSS of Bagnan-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. (As per approved drawing of Howrah Division, PHE Dte.) | AE/Ulu | JE/USD | ORD/000533/2023-2024 | 2036/AE/USD | 13/02/2024 | 13/04/2024 | JSZ GLOBAL | 4.85 | 4.65 | 95.95 | 100
11 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Mankur Deulgram | SM/09349 | Augmentation | Manku Bakshihat Road from 0.00 Km to 1.50 Km (in streches) Restoration of Head Crust due to laying of water Pipelines from PHE dte end for Augmentation of Mankur Deulgram piped water supply scheme under Highway Division P.W Roads Dte in the district Howrah during the year 2023-2024 |  |  | BILL/00233/2024-2025 | BP-2024-25-124 | 11/06/2024 | 11/06/2024 | EXECUTIVE ENGINEER HIGHWAY DIVISION P W ROADS HOWRAH | 2.08 | 0 | 0 | 0
12 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Mankur Deulgram | SM/09349 | Augmentation | Quotation for new service connection for Augmentation of Mankur Deulgram Water Supply Scheme, PH NO- II in the district Howrah under Electrical Division, PHE Dte. ( SM/09349), Reference Id- 106530323, Application no- 1007620510 |  |  | BILL/00085/2024-2025 | 38 | 09/04/2024 | 09/04/2024 | WBSEDCL | 10.4 | 0 | 0 | 0
13 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Mankur Deulgram | SM/09349 | Augmentation | Quotation for new service connection of Mankur Deulgram W/S. Sch. PH-II |  |  | BILL/06047/2023-2024 | 745 | 08/02/2024 | 08/02/2024 | WBSEDCL | 6.67 | 0 | 0 | 0
14 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Mankur Deulgram | SM/09349 | Augmentation | Construction of 750 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation at Mankur Deulgram PWSS at Bagnan-I Block under Uluberia Sub-Division PHE Dte under Howrah Division PHE Dte. | AE/Ulu | JE/USD | ORD/000553/2023-2024 | 895/HD | 27/02/2024 | 16/02/2026 | KALPANA TRADERS | 192.53 | 13.82 | 7.18 | 20
15 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Mankur Deulgram | SM/09349 | Augmentation | Work Order for Laying of Distribution Pipe Lines(UPVC & DI) with allied works and Providing Functional Household Tap Connection(FHTC). Interconnection between Tube wells and construction of switch room (5.40m x 3.60 m) with water supply & sanitary arrangement at Head Work site for Augmentation of MANKUR-DEULGRAM Water Supply Scheme In Bagnan-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu | JE/USD | ORD/000633/2022-2023 | 2746/HD | 15/12/2022 | 02/08/2025 | S.P. CONSTRUCTION | 674.25 | 437.38 | 64.87 | 60
Total | [13 empty] | 1549.03 | 510.63 | 32.96