## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Kanupat. | SM/09350 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Kanupat PWSS, Udaynarayanpur Block Under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000250/2021-2022 | 2109/HD | 24/11/2021 | 09/12/2021 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.05 | 3.05 | 100 | 0
2 | HOWRAH |  | Central Drilling | Augmentation of Ground water based PWSS Kanupat. | SM/09350 | Augmentation | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT KANUPAT PWSS, UDAYNARAYANPUR BLOCK, HOWRAH DIST, UNDER CDD, PHE DTE. |  |  | ORD/000261/2022-2023 | 307/CMSD-I | 08/07/2022 | 23/07/2022 | INDIA ENTERPRISE | 4.98 | 4.11 | 82.48 | 0
3 | HOWRAH |  | Central Drilling | Augmentation of Ground water based PWSS Kanupat. | SM/09350 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT KANUPAT PWSS, UDAYNARAYANPUR BLOCK, HOWRAH DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000262/2022-2023 | 306/CMSD-I | 08/07/2022 | 23/07/2022 | INDIA ENTERPRISE | 3.89 | 3.74 | 96.22 | 0
4 | HOWRAH |  | Central Drilling | Augmentation of Ground water based PWSS Kanupat. | SM/09350 | Augmentation | SUPPLY & DELIVERY OF CONSUMABLES AT SITE WITH OTHER WORKS FOR CONSTRUCTION OF TUBEWELL AT KANUPAT PWSS, UDAYNARAYANPUR BLOCK, HOWRAH DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000263/2022-2023 | 308/CMSD-I | 08/07/2022 | 23/07/2022 | INDIA ENTERPRISE | 1.8 | 1.52 | 84.22 | 0
5 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Kanupat. | SM/09350 | Augmentation | Indent of Material |  |  | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 14/03/2022 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
6 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Kanupat. | SM/09350 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Kanupat water supply scheme, T.W. No. II, Block: Udaynarayanpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/001125/2022-2023 | 1404/ED | 22/03/2023 | 20/06/2023 | MAA KALI ENTERPRISE | 8.27 | 8.07 | 97.58 | 0
7 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Kanupat. | SM/09350 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000020/2022-2023 | 1624/HD | 05/08/2022 | 05/08/2022 | Resource Division | 11.87 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Kanupat. | SM/09350 | Augmentation | Construction of approach road cum internal pathway at HW site of Kanupat PWSS Udaynarayanpur Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu |  | ORD/000157/2024-2025 | 4133/HD | 23/09/2024 | 08/10/2024 | BISWAJIT BAG | 6.64 | 0 | 0 | 0
9 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Kanupat. | SM/09350 | Augmentation | Work Order for Augmentation of Kanupat Water Supply scheme by laying distribution system, providing functional house hold tap connection (FHTC) work with geo tagging by using Jal Swapna app, construction of RCC elevated reservior of capacity 200 m3 of staging height 20 mtr including soil investigation under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000130/2022-2023 | 1339/HD | 27/06/2022 | 27/12/2023 | JAHANGIR ALAM | 216.52 | 216.5 | 99.99 | 90
10 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Kanupat. | SM/09350 | Augmentation | Shifting and stacking of serviceable DI pipes and specials within the campus at Kanupat Store under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000152/2024-2025 | 737/AE/USD | 30/08/2024 | 24/09/2024 | BISWAJIT BAG | 2.43 | 0.64 | 26.48 | 100
11 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Kanupat. | SM/09350 | Augmentation | Display Board at different PWSS at Uluberia-II Udaynarayanpur Block under uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000643/2023-2024 | 3218/AE/USD | 12/03/2024 | 11/04/2024 | ABONTICA ENTERPRISE | 4.26 | 4.26 | 100 | 100
12 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Kanupat. | SM/09350 | Augmentation | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Udaynarayanpur Block) (PART-A) | AE HQ |  | ORD/000225/2025-2026 | 4123/HD | 14/10/2025 | 13/11/2025 | JHARNA ENTERPRISE | 4.79 | 0 | 0 | 0
13 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Kanupat. | SM/09350 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000063/2025-2026 | 4146/HD | 15/10/2025 | 15/10/2025 | Resource Division | 0.92 | 0 | 0 | 0
Total | [13 empty] | 782.61 | 241.89 | 30.91