## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Bhursit Bamunpara PWSS, Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte. | AE/SADAR | JE Sadar | ORD/000283/2021-2022 | 2156/HD | 01/12/2021 | 16/12/2021 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.7 | 3.7 | 100 | 0
2 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000049/2022-2023 | 2839/HD | 23/12/2022 | 23/12/2022 | Resource Division | 23.41 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Indent of Material |  |  | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 14/03/2022 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
4 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bhursit Bamunpara water supply scheme T.W. No. New, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000250/2022-2023 | 917/ED | 22/02/2023 | 23/05/2023 | ANIK & CO. | 10.69 | 10.41 | 97.39 | 70
5 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Work Order for Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Bhursit Bamunpara PWSS of Jagatballavpur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR |  | ORD/000597/2022-2023 | 2713/HD | 14/12/2022 | 28/01/2023 | BALAJI UDDYOG | 27.45 | 25.21 | 91.85 | 100
6 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Work Order for Construction of 2 NOS 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 2000mm) with Sanitary and water Supply arrangement at 3RD & 4TH Tube well SiteS of Bhusit Bamun para PWSS at J.B.PUR Block of Howrah District under Howrah Division, PHE Dte. | AE/SADAR |  | ORD/000825/2022-2023 | 1054/HD | 15/03/2023 | 13/06/2023 | BASU CONSTRUCTION | 13.5 | 13.5 | 100 | 100
7 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2022-2023 | 1624/HD | 05/08/2022 | 05/08/2022 | Resource Division | 73.96 | 0 | 0 | 0
8 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation |  |  |  | BILL/01996/2023-2024 |  | 14/07/2023 | 14/07/2023 | WBSEDCL | 5 | 0 | 0 | 0
9 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Payment for WBSEDCL of Bhurshit Bamunpara Water Supply Scheme Pump House No-IV |  |  | BILL/00368/2023-2024 | BP-2023-24-171 | 24/07/2023 | 24/07/2023 | WBSEDCL | 5 | 0 | 0 | 0
10 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Additional Quotation money deposition for Bhurshit Bamunpara PWSS, P.H No.-III |  |  | BILL/02864/2023-2024 |  | 17/08/2023 | 17/08/2023 | WBSEDCL | 21.59 | 0 | 0 | 0
11 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Quotation Bill for New Service Connection at Bhursit Bamunpara, TW-III |  |  | BILL/00908/2022-2023 |  | 09/03/2023 | 09/03/2023 | WBSEDCL | 11.77 | 0 | 0 | 0
12 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Additional Quotation money deposition for Bhurshit Bamunpara PWSS Pump House No- III |  |  | BILL/00481/2023-2024 | BP-2023-24-237 | 23/08/2023 | 23/08/2023 | WBSEDCL | 21.59 | 0 | 0 | 0
13 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Work Order for Laying distribution system With FHTC Work of Pipe water supply from Augmentation of Bhursit Bamanpara water supply scheme under Howrah sadar Sub-division under Howrah Division, PHE Dte (Part-A) | AE/SADAR | JE/RWS/Sankrail,je_how_rws_jagat,JE Sadar | ORD/000523/2021-2022 | 586/HD | 15/03/2022 | 29/04/2022 | B.B.C ENTERPRISE | 65.18 | 64.94 | 99.63 | 40
14 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Work Order for Laying distribution system With FHTC Work of Pipe water supply from Augmentation of Bhursit Bamanpara water supply scheme under Howrah sadar Sub-division under Howrah Division, PHE Dte. (Part-B) | AE/SADAR | JE/RWS/Sankrail,je_how_rws_jagat,JE Sadar | ORD/000524/2021-2022 | 587/HD | 15/03/2022 | 29/04/2022 | DEV DAS SHAW | 75.85 | 37.64 | 49.62 | 60
15 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Bhursit Bamunpara water supply scheme, T.W. No. IV, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000825/2023-2024 | 3221/ED | 03/08/2023 | 01/11/2023 | ALAK KUMAR CHAKRABORTY | 10.85 | 10.77 | 99.29 | 70
16 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Additional Laying of Distribution system at Dhasa mouza under Pipe water supply from Augmentation of Bhursit Bamanpara water supply scheme under Howrah Sadar Sub-division under Howrah Division, Phe Dte. | AE/SADAR | je_how_rws_jagat | ORD/000662/2023-2024 | 1300/HD | 13/03/2024 | 27/04/2024 | M/S ASHIRBAD (INDIA) | 13.41 | 12.74 | 94.97 | 100
17 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Work Order for Construction Of 400 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/11/2012) Including All pipe Connection For Augmentation Of Bhurshit Bamunpara W/S Scheme In Jagatballavpur Block Of Howrah Division, P. H. E. Dte. | AE/SADAR | JE/RWS/Sankrail,je_how_rws_jagat,JE Sadar | ORD/000393/2022-2023 | 1884/HD | 14/09/2022 | 13/03/2023 | SUDHAMAY MAJUMDAR | 123.64 | 106.75 | 86.34 | 90
18 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Work Oder for laying distribution system With FHTC Work of Pipe water supply from Augmentation of Bhursit Bamanpara water supply scheme under Howrah Sadar Sub-division under Howrah Division, PHE Dte. (start node- 276 to 373) (Part-D) | AE/SADAR | JE/RWS/Sankrail,je_how_rws_jagat,JE Sadar | ORD/000526/2021-2022 | 589/HD | 15/03/2022 | 01/04/2025 | M/S. CHANDIMATA CONSTRUCTION | 71.69 | 63.87 | 89.09 | 100
19 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Jagatballavpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000283/2024-2025 | 4814/HD | 19/11/2024 | 19/03/2025 | HORIZEN | 10.11 | 0.03 | 0.34 | 44
Total | [13 empty] | 1101.59 | 349.56 | 31.73