## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Bhursit Bamunpara PWSS, Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte. | AE/SADAR | JE Sadar | ORD/000283/2021-2022 | 2156/HD | 01/12/2021 | 16/12/2021 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.7 | 3.7 | 100 | 0
2 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000049/2022-2023 | 2839/HD | 23/12/2022 | 23/12/2022 | Resource Division | 23.41 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Indent of Material |  |  | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 14/03/2022 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
4 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bhursit Bamunpara water supply scheme T.W. No. New, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000250/2022-2023 | 917/ED | 22/02/2023 | 23/05/2023 | ANIK & CO. | 10.69 | 10.41 | 97.39 | 70
5 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Work Order for Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Bhursit Bamunpara PWSS of Jagatballavpur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR |  | ORD/000597/2022-2023 | 2713/HD | 14/12/2022 | 28/01/2023 | BALAJI UDDYOG | 27.45 | 25.21 | 91.85 | 100
6 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Work Order for Construction of 2 NOS 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 2000mm) with Sanitary and water Supply arrangement at 3RD & 4TH Tube well SiteS of Bhusit Bamun para PWSS at J.B.PUR Block of Howrah District under Howrah Division, PHE Dte. | AE/SADAR |  | ORD/000825/2022-2023 | 1054/HD | 15/03/2023 | 13/06/2023 | BASU CONSTRUCTION | 13.5 | 13.5 | 100 | 100
7 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2022-2023 | 1624/HD | 05/08/2022 | 05/08/2022 | Resource Division | 73.96 | 0 | 0 | 0
8 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation |  |  |  | BILL/01996/2023-2024 |  | 14/07/2023 | 14/07/2023 | WBSEDCL | 5 | 0 | 0 | 0
9 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Payment for WBSEDCL of Bhurshit Bamunpara Water Supply Scheme Pump House No-IV |  |  | BILL/00368/2023-2024 | BP-2023-24-171 | 24/07/2023 | 24/07/2023 | WBSEDCL | 5 | 0 | 0 | 0
10 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Additional Quotation money deposition for Bhurshit Bamunpara PWSS, P.H No.-III |  |  | BILL/02864/2023-2024 |  | 17/08/2023 | 17/08/2023 | WBSEDCL | 21.59 | 0 | 0 | 0
11 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Quotation Bill for New Service Connection at Bhursit Bamunpara, TW-III |  |  | BILL/00908/2022-2023 |  | 09/03/2023 | 09/03/2023 | WBSEDCL | 11.77 | 0 | 0 | 0
12 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Additional Quotation money deposition for Bhurshit Bamunpara PWSS Pump House No- III |  |  | BILL/00481/2023-2024 | BP-2023-24-237 | 23/08/2023 | 23/08/2023 | WBSEDCL | 21.59 | 0 | 0 | 0
13 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Work Order for Laying distribution system With FHTC Work of Pipe water supply from Augmentation of Bhursit Bamanpara water supply scheme under Howrah sadar Sub-division under Howrah Division, PHE Dte (Part-A) | AE/SADAR | JE/RWS/Sankrail,je_how_rws_jagat,JE Sadar | ORD/000523/2021-2022 | 586/HD | 15/03/2022 | 29/04/2022 | B.B.C ENTERPRISE | 65.18 | 64.94 | 99.63 | 40
14 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Work Order for Laying distribution system With FHTC Work of Pipe water supply from Augmentation of Bhursit Bamanpara water supply scheme under Howrah sadar Sub-division under Howrah Division, PHE Dte. (Part-B) | AE/SADAR | JE/RWS/Sankrail,je_how_rws_jagat,JE Sadar | ORD/000524/2021-2022 | 587/HD | 15/03/2022 | 29/04/2022 | DEV DAS SHAW | 75.85 | 37.64 | 49.62 | 60
15 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Bhursit Bamunpara water supply scheme, T.W. No. IV, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000825/2023-2024 | 3221/ED | 03/08/2023 | 01/11/2023 | ALAK KUMAR CHAKRABORTY | 10.85 | 10.77 | 99.29 | 70
16 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Additional Laying of Distribution system at Dhasa mouza under Pipe water supply from Augmentation of Bhursit Bamanpara water supply scheme under Howrah Sadar Sub-division under Howrah Division, Phe Dte. | AE/SADAR | je_how_rws_jagat | ORD/000662/2023-2024 | 1300/HD | 13/03/2024 | 27/04/2024 | M/S ASHIRBAD (INDIA) | 13.41 | 12.74 | 94.97 | 100
17 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Work Order for Construction Of 400 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/11/2012) Including All pipe Connection For Augmentation Of Bhurshit Bamunpara W/S Scheme In Jagatballavpur Block Of Howrah Division, P. H. E. Dte. | AE/SADAR | JE/RWS/Sankrail,je_how_rws_jagat,JE Sadar | ORD/000393/2022-2023 | 1884/HD | 14/09/2022 | 13/03/2023 | SUDHAMAY MAJUMDAR | 123.64 | 106.75 | 86.34 | 90
18 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Work Oder for laying distribution system With FHTC Work of Pipe water supply from Augmentation of Bhursit Bamanpara water supply scheme under Howrah Sadar Sub-division under Howrah Division, PHE Dte. (start node- 276 to 373) (Part-D) | AE/SADAR | JE/RWS/Sankrail,je_how_rws_jagat,JE Sadar | ORD/000526/2021-2022 | 589/HD | 15/03/2022 | 01/04/2025 | M/S. CHANDIMATA CONSTRUCTION | 71.69 | 63.87 | 89.09 | 100
19 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Bhurshit Bamunpara | SM/09351 | Augmentation | Work Order for Laying distribution system With FHTC Work of Pipe water supply from Augmentation of Bhursit Bamanpara water supply scheme under Howrah sadar Sub-division under Howrah Division, PHE Dte. (start node- 188 to 274) (Part-C) | AE/SADAR | JE/RWS/Sankrail,je_how_rws_jagat,JE Sadar | ORD/000525/2021-2022 | 588/HD | 15/03/2022 | 01/01/2025 | N. G ENGINEERING | 93.7 | 90.42 | 96.49 | 100
Total | [13 empty] | 1185.17 | 439.94 | 37.12