## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Sinking of Eleven (11 ) Nos DWP Mark-II Hand Tube Well 100 mm x 40 mm dia 250 mtr Pipes within 179 Shyampur Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. | SM/09353 | Disaster | Work Order for Sinking of Eleven (11) nos DWP (Mark-II) Hand Tube well 100mm x 40mm dia 250 mtr Pipes within 179 Shyampur Assembly Constituency under Howrah Division PHE Dte. in connection with Supercyclone 'YAAS | AE/Ulu |  | ORD/000388/2021-2022 | 185/HD | 31/01/2022 | 17/03/2022 | M/S AHAMED CONSTRUCTION | 11.48 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Sinking of Eleven (11 ) Nos DWP Mark-II Hand Tube Well 100 mm x 40 mm dia 250 mtr Pipes within 179 Shyampur Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. | SM/09353 | Disaster | Work Order for Sinking of ten (10) nos DWP (Mark-II) Hand Pump Tube well 100mm x 40mm dia 250 mtr deep within different habitation of 178 Uluberia Dakshin Assembly Constituency under Howrah Division PHE Dte. (Group-K). | AE/SADAR,AE/Ulu |  | ORD/000554/2022-2023 | 2447/HD | 28/11/2022 | 12/01/2023 | M/S AHAMED CONSTRUCTION | 18.45 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Sinking of Eleven (11 ) Nos DWP Mark-II Hand Tube Well 100 mm x 40 mm dia 250 mtr Pipes within 179 Shyampur Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. | SM/09353 | Disaster | Material Requisition To Resource Division |  |  | RTOR000022/2021-2022 | 405/HD | 24/02/2022 | 24/02/2022 | Resource Division | 23.77 | 0 | 0 | 0
Total | [13 empty] | 53.7 | 0 | 0