## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. | SM/09424 | Disaster | Sinking of four (4) nos DWP (Mark-II) Hand Tube well 100mm x 40mm dia 250 mtr deep within different habitations of 181 Amta Assembly Constituency under Howrah Division PHE Dte. in connection with Supercyclone 'YAAS' (Group-A) | AE/Ulu |  | ORD/000338/2021-2022 | 2394/HD | 27/12/2021 | 10/02/2022 | ANATH BANDHU ENTERPRISE | 4.21 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. | SM/09424 | Disaster | Sinking of four (4) nos DWP (Mark-II) Hand Tube well 100mm x 40mm dia 250 mtr deep within different habitations of 181 Amta Assembly Constituency under Howrah Division PHE Dte. in connection with Supercyclone 'YAAS' (Group-C) | AE/Ulu |  | ORD/000340/2021-2022 | 2396/HD | 27/12/2021 | 10/02/2022 | M/S S.M ENTERPRISE | 4.2 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. | SM/09424 | Disaster | Sinking of four (4) nos DWP (Mark-II) Hand Tube well 100mm x 40mm dia 250 mtr deep within different habitations of 181 Amta Assembly Constituency under Howrah Division PHE Dte. in connection with Supercyclone 'YAAS' (Group-E) | AE/Ulu |  | ORD/000342/2021-2022 | 2398/HD | 27/12/2021 | 10/02/2022 | RADHA KRISHNA ENTERPRISE | 4.2 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. | SM/09424 | Disaster | Sinking of four (4) nos DWP (Mark-II) Hand Tube well 100mm x 40mm dia 250 mtr deep within different habitations of 181 Amta Assembly Constituency under Howrah Division PHE Dte. in connection with Supercyclone 'YAAS' (Group-J) | AE/Ulu |  | ORD/000347/2021-2022 | 2403/HD | 27/12/2021 | 10/02/2022 | DEV DAS SHAW | 4.21 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. | SM/09424 | Disaster | Sinking of four (4) nos DWP (Mark-II) Hand Tube well 100mm x 40mm dia 250 mtr deep within different habitations of 181 Amta Assembly Constituency under Howrah Division PHE Dte. in connection with Supercyclone 'YAAS' (Group-L) | AE/Ulu |  | ORD/000349/2021-2022 | 2405/HD | 27/12/2021 | 10/02/2022 | MAITY CONSTRUCTIONS | 4.22 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. | SM/09424 | Disaster | Sinking of four (2) nos DWP (Mark-II) Hand Tube well 100mm x 40mm dia 250 mtr deep within different habitations of 181 Amta Assembly Constituency under Howrah Division PHE Dte. in connection with Supercyclone 'YAAS' (Group-M) | AE/Ulu |  | ORD/000350/2021-2022 | 2406/HD | 27/12/2021 | 26/01/2022 | SK ANISUR | 2.11 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. | SM/09424 | Disaster | Sinking of four (4) nos DWP (Mark-II) Hand Tube well 100mm x 40mm dia 250 mtr deep within different habitations of 181 Amta Assembly Constituency under Howrah Division PHE Dte. in connection with Supercyclone 'YAAS' (Group-B) | AE/Ulu |  | ORD/000339/2021-2022 | 2395/HD | 27/12/2021 | 10/02/2022 | A.B. CONSTRUCTION | 4.2 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. | SM/09424 | Disaster | Sinking of four (4) nos DWP (Mark-II) Hand Tube well 100mm x 40mm dia 250 mtr deep within different habitations of 181 Amta Assembly Constituency under Howrah Division PHE Dte. in connection with Supercyclone 'YAAS' (Group-D) | AE/Ulu |  | ORD/000341/2021-2022 | 2397/HD | 27/12/2021 | 10/02/2022 | 786 ENTERPRISE | 4.2 | 0 | 0 | 0
9 | HOWRAH |  | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. | SM/09424 | Disaster | Sinking of four (4) nos DWP (Mark-II) Hand Tube well 100mm x 40mm dia 250 mtr deep within different habitations of 181 Amta Assembly Constituency under Howrah Division PHE Dte. in connection with Supercyclone 'YAAS' (Group-F) | AE/Ulu |  | ORD/000343/2021-2022 | 2399/HD | 27/12/2021 | 10/02/2022 | M/S M.R ENTERPRISE | 4.2 | 0 | 0 | 0
10 | HOWRAH |  | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. | SM/09424 | Disaster | Sinking of four (4) nos DWP (Mark-II) Hand Tube well 100mm x 40mm dia 250 mtr deep within different habitations of 181 Amta Assembly Constituency under Howrah Division PHE Dte. in connection with Supercyclone 'YAAS' (Group-G) | AE/Ulu |  | ORD/000344/2021-2022 | 2400/HD | 27/12/2021 | 10/02/2022 | M/S AHAMED CONSTRUCTION | 4.21 | 0 | 0 | 0
11 | HOWRAH |  | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. | SM/09424 | Disaster | Sinking of four (4) nos DWP (Mark-II) Hand Tube well 100mm x 40mm dia 250 mtr deep within different habitations of 181 Amta Assembly Constituency under Howrah Division PHE Dte. in connection with Supercyclone 'YAAS' (Group-I) | AE/Ulu |  | ORD/000346/2021-2022 | 2402/HD | 27/12/2021 | 10/02/2022 | DEV DAS SHAW | 4.21 | 0 | 0 | 0
12 | HOWRAH |  | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. | SM/09424 | Disaster | Sinking of four (4) nos DWP (Mark-II) Hand Tube well 100mm x 40mm dia 250 mtr deep within different habitations of 181 Amta Assembly Constituency under Howrah Division PHE Dte. in connection with Supercyclone 'YAAS' (Group-K) | AE/Ulu |  | ORD/000348/2021-2022 | 2404/HD | 27/12/2021 | 10/02/2022 | DEV DAS SHAW | 4.21 | 0 | 0 | 0
13 | HOWRAH |  | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. | SM/09424 | Disaster | Sinking of four (4) nos DWP (Mark-II) Hand Tube well 100mm x 40mm dia 250 mtr deep within different habitations of 181 Amta Assembly Constituency under Howrah Division PHE Dte. in connection with Supercyclone 'YAAS' (Group-H) | AE/Ulu |  | ORD/000345/2021-2022 | 2401/HD | 27/12/2021 | 10/02/2022 | SK ANISUR | 4.21 | 0 | 0 | 0
14 | HOWRAH |  | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. | SM/09424 | Disaster | Material Requisition To Resource Division |  |  | RTOR000016/2021-2022 | 95/HD | 17/01/2022 | 17/01/2022 | Resource Division | 76.03 | 0 | 0 | 0
15 | HOWRAH |  | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. | SM/09424 | Disaster | Material Requisition To Resource Division |  |  | RTOR000012/2021-2022 | 2374/HD | 24/12/2021 | 24/12/2021 | Resource Division | 8.03 | 0 | 0 | 0
16 | HOWRAH |  | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. | SM/09424 | Disaster | Material Requisition To Resource Division |  |  | RTOR000003/2022-2023 | 1158/HD | 31/05/2022 | 31/05/2022 | Resource Division | 51.06 | 0 | 0 | 0
17 | HOWRAH |  | Howrah Division | Sinking of Fifty (50) Nos DWP ( Mark-II) Hand Tube Well 100 mm x 40mm dia 250 mtr deep within 181 Amta Assembly Constituency under Howrah Division, PHE Dte in connection with super cyclone YAAS. | SM/09424 | Disaster | Material Requisition To Resource Division |  |  | RTOR000001/2022-2023 | 953/HD | 28/04/2022 | 28/04/2022 | Resource Division | 24.64 | 0 | 0 | 0
Total | [13 empty] | 212.36 | 0 | 0