## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Augmentation of Ground water PWSS for Islampur | SM/09428 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Islampur, JagatBallavpur under Howrah Sadar Sub-Division of Howrah Division PHE Dte. | AE/SADAR | JE/RWS/Jagatballavpur | ORD/000279/2021-2022 | 2152/HD | 01/12/2021 | 16/12/2021 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.03 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Augmentation of Ground water PWSS for Islampur | SM/09428 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000053/2022-2023 | 2839/HD | 23/12/2022 | 23/12/2022 | Resource Division | 27.6 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Augmentation of Ground water PWSS for Islampur | SM/09428 | Augmentation | Indent of Material |  |  | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 14/03/2022 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
4 | HOWRAH |  | Electrical | Augmentation of Ground water PWSS for Islampur | SM/09428 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Islampur (Replacement) water supply scheme, T.W. No. I & II, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000109/2022-2023 | 711/ED | 03/02/2023 | 04/05/2023 | T.N. BANERJEE | 21.42 | 0 | 0 | 1
5 | HOWRAH |  | Howrah Division | Augmentation of Ground water PWSS for Islampur | SM/09428 | Augmentation | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Islampur PWSS at Jagatballavpur Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR | JE/RWS/Jagatballavpur | ORD/000335/2022-2023 | 1834/HD | 08/09/2022 | 18/10/2022 | B K ENTERPRISE | 35.33 | 0 | 0 | 0
6 | HOWRAH |  | Electrical | Augmentation of Ground water PWSS for Islampur | SM/09428 | Augmentation | Car hiring bill for Car No. WB15C5554 for the month of July 2023 |  |  | ORD/002118/2022-2023 | 215_AE_II_ED | 24/03/2023 | 24/04/2023 | DILIP KUMAR GHOSH | 0.15 | 0 | 0 | 5
7 | HOWRAH |  | Electrical | Augmentation of Ground water PWSS for Islampur | SM/09428 | Augmentation | Car hiring & fuel bill for the month of July 2023 |  |  | ORD/000828/2023-2024 | 0444_0445_0447 | 31/07/2023 | 31/08/2023 | JAMECO AGENCIES PRIVATE LIMITED. | 0.73 | 0 | 0 | 5
8 | HOWRAH |  | Electrical | Augmentation of Ground water PWSS for Islampur | SM/09428 | Augmentation | Hire charges bill of vehicle no. WB04G2822 for the month of july 2023 |  |  | ORD/002117/2022-2023 | 203_AE_I_ED | 23/03/2023 | 23/04/2023 | DASHRATH KUMAR PRAJAPATI | 0.15 | 0 | 0 | 5
9 | HOWRAH |  | Electrical | Augmentation of Ground water PWSS for Islampur | SM/09428 | Augmentation | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte. |  |  | ORD/000829/2023-2024 | 958/HMSD | 20/04/2023 | 21/10/2023 | ARINDAM AUDDY | 0.15 | 0 | 0 | 5
10 | HOWRAH |  | Howrah Division | Augmentation of Ground water PWSS for Islampur | SM/09428 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2022-2023 | 1624/HD | 05/08/2022 | 05/08/2022 | Resource Division | 95.73 | 0 | 0 | 0
11 | HOWRAH |  | Howrah Division | Augmentation of Ground water PWSS for Islampur | SM/09428 | Augmentation | Work Order for Construction of Pump House, Boundary Wall, 450 cum Capacity OHR, Rising Main , Laying Distribution Pipeline & Providing FHTC (4480 nos) For AUGMENTATION OF Islampur PWSS at Jagatballavpur Block under Howrah Sadar Sub Division of HOWRAH DIVISION, P. H. E. DTE.. | AE/SADAR | je_how_rws_jagat | ORD/000507/2022-2023 | 2256/HD | 04/11/2022 | 03/05/2023 | SUBHASH BOSE | 571.07 | 0 | 0 | 25
Total | [13 empty] | 1269.54 | 0 | 0