## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Aumentation of PWSS for Surikhali | SM/09429 | Augmentation | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 79-80-81-82-92, 79-49-29 under Uluberia-II block under Howrah Division, PHE Dte. (Part-C) | AE/Ulu | JE/USD | ORD/000037/2022-2023 | 827/HD | 11/04/2022 | 11/05/2022 | A.N ROY & CO | 4.72 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Aumentation of PWSS for Surikhali | SM/09429 | Augmentation | Work Order for providing Functional Household Tap Connection (FHTC) at Augumentation of Surikhali Water Supply Scheme (Zone-II) at under Uluberia-II block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-C) | AE/Ulu | JE/USD | ORD/000046/2022-2023 | 841/HD | 11/04/2022 | 11/05/2022 | SK ANISUR | 4.98 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Aumentation of PWSS for Surikhali | SM/09429 | Augmentation | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 92-93-94-95-96-97-98, 96-99-100-101-102-103 under Uluberia-II block under Howrah Division, PHE Dte. (Part-B) | AE/Ulu | JE/USD | ORD/000036/2022-2023 | 826/HD | 11/04/2022 | 11/05/2022 | ARINDAM ENTERPRISE | 4.77 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Aumentation of PWSS for Surikhali | SM/09429 | Augmentation | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 34-35-36-37-38-39, 38-40-41-42-44-45-47-48 under Uluberia-II block under Howrah Division, PHE Dte. (Part-G) | AE/Ulu | JE/USD | ORD/000041/2022-2023 | 831/HD | 11/04/2022 | 11/05/2022 | A.B. ENTERPRISE | 4.81 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Aumentation of PWSS for Surikhali | SM/09429 | Augmentation | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 8-9-10-11-12-13-14-15-16-17, 9-21-18-19-20 under Uluberia-II block under Howrah Division, PHE Dte. (Part-E) | AE/Ulu | JE/USD | ORD/000039/2022-2023 | 829/HD | 11/04/2022 | 11/05/2022 | SUNIL ENTERPRISE | 4.71 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Aumentation of PWSS for Surikhali | SM/09429 | Augmentation | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 21-26-31-32-33-34, 13-18 under Uluberia-II block under Howrah Division, PHE Dte. (Part-F) | AE/Ulu | JE/USD | ORD/000040/2022-2023 | 830/HD | 11/04/2022 | 11/05/2022 | MONIRUL ISLAM | 4.82 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Aumentation of PWSS for Surikhali | SM/09429 | Augmentation | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 43-46-50 under Uluberia-II block under Howrah Division, PHE Dte. (Part-J) | AE/Ulu | JE/USD | ORD/000018/2022-2023 | 834/HD | 11/04/2022 | 11/05/2022 | JOY GURU TRADING | 4.54 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Aumentation of PWSS for Surikhali | SM/09429 | Augmentation | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 87-88-89-91-90-, 85-87, 83-85-86, 83-84, 79-83under Uluberia-II block under Howrah Division, PHE Dte. (Part-A) | AE/Ulu | JE/USD | ORD/000035/2022-2023 | 825/HD | 11/04/2022 | 11/05/2022 | DEBABRATA CHAKRABORTY | 4.37 | 0 | 0 | 0
9 | HOWRAH |  | Howrah Division | Aumentation of PWSS for Surikhali | SM/09429 | Augmentation | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 11-23-25-29-30 under Uluberia-II block under Howrah Division, PHE Dte. (Part-D) | AE/Ulu | JE/USD | ORD/000038/2022-2023 | 828/HD | 11/04/2022 | 11/05/2022 | BINOY KOLEY | 4.83 | 0 | 0 | 0
10 | HOWRAH |  | Howrah Division | Aumentation of PWSS for Surikhali | SM/09429 | Augmentation | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 56-57-54-52, 54-55, 57-62-64, 56-58-59-60-61-65-62, 65-66 under Uluberia-II block under Howrah Division, PHE Dte. (Part-K) | AE/Ulu | JE/USD | ORD/000019/2022-2023 | 835/HD | 11/04/2022 | 11/05/2022 | SHIV SHAKTI CONSTRUCTION | 4.75 | 0 | 0 | 0
11 | HOWRAH |  | Howrah Division | Aumentation of PWSS for Surikhali | SM/09429 | Augmentation | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section62-68-69-72-75-76-77-78, 61-63, under Uluberia-II block under Howrah Division, PHE Dte. (Part-L) | AE/Ulu | JE/USD | ORD/000021/2022-2023 | 836/HD | 11/04/2022 | 11/05/2022 | CONSTRUCTION UDOUG | 4.67 | 0 | 0 | 0
12 | HOWRAH |  | Howrah Division | Aumentation of PWSS for Surikhali | SM/09429 | Augmentation | Work Order for providing Functional Household Tap Connection (FHTC) at Augumentation of Surikhali Water Supply Scheme (Zone-II) at under Uluberia-II block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-A) | AE/Ulu | JE/USD | ORD/000044/2022-2023 | 839/HD | 11/04/2022 | 11/05/2022 | APEX ENGINEERING | 4.97 | 0 | 0 | 0
13 | HOWRAH |  | Howrah Division | Aumentation of PWSS for Surikhali | SM/09429 | Augmentation | Work Order for providing Functional Household Tap Connection (FHTC) at Augumentation of Surikhali Water Supply Scheme (Zone-II) at under Uluberia-II block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-B) | AE/Ulu | JE/USD | ORD/000045/2022-2023 | 840/HD | 11/04/2022 | 11/05/2022 | S.M. CONSTRUCTION | 4.97 | 0 | 0 | 0
14 | HOWRAH |  | Howrah Division | Aumentation of PWSS for Surikhali | SM/09429 | Augmentation | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 73-74-75-76-70-73-67-70-71-67-47-71 under Uluberia-II block under Howrah Division, PHE Dte. (Part-M) | AE/Ulu | JE/USD | ORD/000013/2022-2023 | 837/HD | 11/04/2022 | 11/05/2022 | NAUTANDAS & CO. | 4.8 | 0 | 0 | 0
15 | HOWRAH |  | Howrah Division | Aumentation of PWSS for Surikhali | SM/09429 | Augmentation | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 1-2-3-4-5-6-7-8, 2-22-23-24-25 under Uluberia-II block under Howrah Division, PHE Dte. (Part-H) | AE/Ulu | JE/USD | ORD/000016/2022-2023 | 832/HD | 11/04/2022 | 11/05/2022 | S.S ENTERPRISE | 4.83 | 0 | 0 | 0
16 | HOWRAH |  | Howrah Division | Aumentation of PWSS for Surikhali | SM/09429 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Surikhali PWSS, Uluberia-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. |  |  | VCH/000829/2021-2022 | BP-2021-22-364 | 28/02/2022 | 28/02/2022 | APEX ENGINEERING | 3.47 | 0 | 0 | 0
17 | HOWRAH |  | Howrah Division | Aumentation of PWSS for Surikhali | SM/09429 | Augmentation | Indent of Material |  |  | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 14/03/2022 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
18 | HOWRAH |  | Howrah Division | Aumentation of PWSS for Surikhali | SM/09429 | Augmentation | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 24-27-28, 27-43-51-52-53, 51-56 under Uluberia-II block under Howrah Division, PHE Dte. (Part-I) | AE/Ulu | JE/USD | ORD/000017/2022-2023 | 833/HD | 11/04/2022 | 11/05/2022 | NAG ENTERPRISE | 4.73 | 0 | 0 | 0
19 | HOWRAH |  | Electrical | Aumentation of PWSS for Surikhali | SM/09429 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Surikhali water supply scheme, Zone-I, P.H. No. II, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000105/2022-2023 | 604/ED | 02/02/2023 | 03/05/2023 | D. K. ELECTRIC | 10.99 | 0 | 0 | 0
20 | HOWRAH |  | Electrical | Aumentation of PWSS for Surikhali | SM/09429 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Surikhali water supply scheme, Zone-I, P.H. No. III & IV, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/000870/2023-2024 | 3443/ED | 11/08/2023 | 09/11/2023 | D. K. ELECTRIC | 21.98 | 0 | 0 | 0
21 | HOWRAH |  | Electrical | Aumentation of PWSS for Surikhali | SM/09429 | Augmentation | Hiring of 1 (One) Diesel Luxury Taxi on contract carriage for office of the Assistant Engineer-II, ED, PHED |  |  | ORD/002538/2022-2023 | 215_ae_ed | 24/03/2023 | 23/03/2024 | DILIP KUMAR GHOSH | 5 | 0 | 0 | 20
22 | HOWRAH |  | Howrah Division | Aumentation of PWSS for Surikhali | SM/09429 | Augmentation | Work Order for Laying UPVC & DI pipeline & providing Functional Household Tap Connection (FHTC) at Augmentation of Surikhali Water Supply Scheme (Zone-I) under Uluberia-II block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-A) | AE/Ulu | JE/USD | ORD/000521/2021-2022 | 563/HD | 14/03/2022 | 28/04/2022 | MODERN CONSTRUCTION | 84.8 | 0 | 0 | 100
23 | HOWRAH |  | Howrah Division | Aumentation of PWSS for Surikhali | SM/09429 | Augmentation | Work Order for Interconnection for 2nd TW and 1st Tube well (HW site) at Augumentation of Surikhali Water Supply scheme (Zone-I) in Uluberia-II Block under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000020/2022-2023 | 838/HD | 11/04/2022 | 11/05/2022 | MONIRUL ISLAM | 3.45 | 0 | 0 | 100
24 | HOWRAH |  | Howrah Division | Aumentation of PWSS for Surikhali | SM/09429 | Augmentation | Work Order for Sinking of 3 (three) nos PVC big dia Tube well 250 mm x 150 mm dia of 250 mtr deep for Augmentation of Surikhali W/S scheme at Uluberia-II Block in Uluberia Sub-Division under Howrah Division P.H.E Dte. | AE/Ulu | JE/USD | ORD/000190/2022-2023 | 1515/HD | 22/07/2022 | 21/08/2022 | NADIA TUBEWELLS | 39.12 | 0 | 0 | 0
25 | HOWRAH |  | Electrical | Aumentation of PWSS for Surikhali | SM/09429 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Surikhali water supply scheme, Zone-I, P.H. No. I, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000243/2022-2023 | 2104/HMSD | 24/11/2022 | 24/12/2022 | M.G. CONSTRUCTIONS & CO. | 4.94 | 0 | 0 | 0
26 | HOWRAH |  | Electrical | Aumentation of PWSS for Surikhali | SM/09429 | Augmentation | Supply, Delivery of actuator operated butterfly valvefor Augmentation of Surikhali W/S. Sch. Z-I, PH-I |  |  | ORD/002321/2022-2023 | 2156//HMSD | 30/11/2022 | 28/02/2023 | M.G. CONSTRUCTIONS & CO. | 0.99 | 0 | 0 | 100
27 | HOWRAH |  | Howrah Division | Aumentation of PWSS for Surikhali | SM/09429 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000024/2021-2022 | 407/HD | 24/02/2022 | 24/02/2022 | Resource Division | 7.99 | 0 | 0 | 0
28 | HOWRAH |  | Electrical | Aumentation of PWSS for Surikhali | SM/09429 | Augmentation | Hiring of diesel car |  |  | BILL/00005/2023-2024 | 05 | 13/04/2023 | 13/04/2023 | TRIDIP SARKAR | 0.4 | 0 | 0 | 0
29 | HOWRAH |  | Electrical | Aumentation of PWSS for Surikhali | SM/09429 | Augmentation | Hire Charges Bill of V.No.- WB-15C-5554 for office of the E/E. PHED |  |  | ORD/001027/2023-2024 | 591*AE-II/ED | 18/08/2023 | 17/08/2024 | DILIP KUMAR GHOSH | 5 | 0 | 0 | 30
30 | HOWRAH |  | Howrah Division | Aumentation of PWSS for Surikhali | SM/09429 | Augmentation | Work Order for Laying UPVC pipeline & providing Functional Household Tap Connection (FHTC) at Augumentation of Surikhali Water Supply Scheme (Zone-I) at section (103-106-109-113-126-129-130-137-140-143-148-153-107-104) under Uluberia-II block under Uluberia Sub-Division under Howrah Division, PHE Dte.(Part-B) | AE/Ulu | JE/USD | ORD/000520/2021-2022 | 564/HD | 14/03/2022 | 13/04/2022 | JOY GURU TRADING | 12.27 | 0 | 0 | 100
Total | [13 empty] | 789.86 | 0 | 0