## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati | SM/09586 | Augmentation | Work Order for Laying Distribution Pipeline At Narendrapur Mouza Node No. 367 to 450 (Part-3) of Shekrahati Water Supply Scheme in Jagatballavpur Block Of Howrah District. | AE/SADAR |  | ORD/000532/2021-2022 | 629/HD | 22/03/2022 | 06/05/2022 | BUILT INDIA | 37.92 | 38.47 | 101.46 | 0
2 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati | SM/09586 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000048/2022-2023 | 2839/HD | 23/12/2022 | 23/12/2022 | Resource Division | 23.04 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati | SM/09586 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Sekrahati PWSS, Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte. |  |  | VCH/000955/2021-2022 | BP-2021-22-403 | 14/03/2022 | 14/03/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.18 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati | SM/09586 | Augmentation | Indent of Material |  |  | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 14/03/2022 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati | SM/09586 | Augmentation | Work Order for Sinking of 1 (One) No. 250 X 150 mm Dia and 230 m deep additional tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Augmentation of Shekrahati PWSS of Jagat Ballavpur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR |  | ORD/000658/2022-2023 | 169/HD | 13/01/2023 | 27/02/2023 | MUNSHI ENTERPRISE | 12.98 | 12.68 | 97.7 | 100
6 | HOWRAH |  | Electrical | Augmentation of Ground Water Based PWSS for Shekrahati | SM/09586 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Shekrahati water supply scheme, T.W. No. I & II, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000248/2022-2023 | 915/ED | 22/02/2023 | 23/05/2023 | A.G. ENTERPRISE | 21.49 | 10.47 | 48.7 | 65
7 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati | SM/09586 | Augmentation | Work Order for Laying Distribution Pipeline At Sekrahati Mouza Node No. 220 to 366 (Part-2) of Shekrahati Water Supply Scheme In Jagatballavpur Block Of Howrah District. | AE/SADAR |  | ORD/000005/2022-2023 | 803/HD | 07/04/2022 | 22/05/2022 | SWASTIK ENTERPRISE | 56.88 | 57.38 | 100.88 | 100
8 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati | SM/09586 | Augmentation | Work Order for Restoration of damaged concrete branch roads due to laying of pipe line at Narendrapur Mouza (Node No. 367 to 450) of Sekrahati PWSS under Howrah Divnision PHE Dte. | AE/SADAR |  | ORD/000685/2022-2023 | 273/HD | 19/01/2023 | 05/03/2023 | BUILT INDIA | 10.4 | 10.18 | 97.89 | 0
9 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati | SM/09586 | Augmentation | Work Order for Construction of Pump House ( 5.40m x 3.60 m) at 3rd Tube Well Site of Sekrahati PWSS at J.B.Pur Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR | je6/maad | ORD/000059/2023-2024 | 1851/HD | 02/05/2023 | 31/07/2023 | M.K ENTERPRISE | 6.19 | 5.61 | 90.69 | 100
10 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati | SM/09586 | Augmentation | Work Order for Pipeline Work From 3rd Tubewell to Delivery line (Node No 326 to 312) at Sekrahati PWSS at J.B.Pur Block under Howrah Sadar Suv-Division, P.H.E. Dte. | AE/SADAR | je6/maad | ORD/000061/2023-2024 | 1853/HD | 02/05/2023 | 01/06/2023 | DEBABRATA CHAKRABORTY | 4.33 | 3.64 | 84.04 | 100
11 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati | SM/09586 | Augmentation | Work Order for Construction of Boundary Wall at 3rd Tube Well Site of Sekrahati PWSS at J.B.Pur Block of Howrah District under Howrah Division, P. H. E. Dte. (12 m X 12 m) | AE/SADAR | je6/maad | ORD/000070/2023-2024 | 1931/HD | 10/05/2023 | 09/07/2023 | M/S RAJBALLOVI CONSTRUCTION | 4.13 | 4.08 | 98.74 | 100
12 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati | SM/09586 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2022-2023 | 1624/HD | 05/08/2022 | 05/08/2022 | Resource Division | 20.07 | 0 | 0 | 0
13 | HOWRAH |  | Electrical | Augmentation of Ground Water Based PWSS for Shekrahati | SM/09586 | Augmentation | Quotation Bill for New Service Connection at Sekrahati W/S. Sch. TW-III, Howrah |  |  | BILL/01880/2022-2023 | 213 | 24/03/2023 | 24/03/2023 | WBSEDCL | 2.98 | 0 | 0 | 0
14 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati | SM/09586 | Augmentation | Work Order for Providing FHTC (Functional Household Tap Connection) At Sekrahati Mouza (Part-2) of Shekrahati Water Supply Scheme isn Jagatballavpur Block Of Howrah District (PART-B) | AE/SADAR | JE Sadar | ORD/000531/2021-2022 | 628/HD | 22/03/2022 | 06/05/2022 | SUSHANTA MONDAL | 26.5 | 25.85 | 97.52 | 100
15 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati | SM/09586 | Augmentation | Work Order for Providing FHTC (Functional Household Tap Connection) At Narendrapur Mouza (Part-3) of Shekrahati Water Supply Scheme In Jagatballavpur Block Of Howrah District. | AE/SADAR | JE Sadar | ORD/000012/2022-2023 | 804/HD | 07/04/2022 | 22/05/2022 | KAMIRUL SK AND CO. | 56.29 | 54.4 | 96.63 | 98
16 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati | SM/09586 | Augmentation | Laying Distribution Pipeline at Uncovered Area Near 3rd Tubewell (Node 326 to 309, 312 to 315 & 313 to 331) For Providing FHTC of Sekrahati Water Supply Scheme under Howrah Sadar Sub-Division PHE Dte. | AE/SADAR | JE Sadar | ORD/000664/2023-2024 | 209/HSSD | 29/02/2024 | 30/03/2024 | MA-DURGA ENTERPRISE | 1.61 | 1.6 | 99.49 | 100
17 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati | SM/09586 | Augmentation | Road Restoration work due to road cutting by PHE for laying water pipeline at Howrah Amta Road from 32.50 Km to 35.70 Km (Both side) Under Howrah Division, P.W.D. during the year 2024-25. |  |  | BILL/00828/2024-2025 | BP-2024-25-493 | 27/11/2024 | 27/11/2024 | EXECUTIVE ENGINEER HOWRAH DIVISION, PWD. | 13.23 | 0 | 0 | 0
18 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati | SM/09586 | Augmentation | Work Order for Construction Of 400 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref :Dept. Super Struc. DRG. No. PCI/OHR/11/2012) Including All pipe Connection, Design od piles and soil test, Laying Distribution Pipeline At Krishnandapur Mouza Node No. 1 to 219 (Part-1) and Providing FHTC (Functional Household Tap Connection) at Krishnandapur Mouza (Part-1) for Augmentation Of SEKRAHATI Water Supply Scheme In Jagatballavpur Block Of Howrah Division PHED. | AE/SADAR | JE Sadar | ORD/000131/2022-2023 | 1340/HD | 27/06/2022 | 02/10/2025 | JAHANGIR ALAM | 204.08 | 114.66 | 56.18 | 80
19 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based PWSS for Shekrahati | SM/09586 | Augmentation | Work Order for Rising Main Pipeline Work From 2nd Pump House to 1st Pump House & OHR of Shekrahati Water Supply Scheme In Jagatballavpur Block Of Howrah District. | AE/SADAR | JE Sadar | ORD/000591/2022-2023 | 2605/HD | 07/12/2022 | 21/01/2023 | JAHANGIR ALAM | 2.62 | 0 | 0 | 100
Total | [13 empty] | 1022.12 | 339.02 | 33.17