## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Augmentation of Nischintapur piped water supply scheme. | SM/09720 | Augmentation | Indent of Material |  |  | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 14/03/2022 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Augmentation of Nischintapur piped water supply scheme. | SM/09720 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Nischintapur PWSS, Amta-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. |  |  | VCH/000827/2021-2022 | BP-2021-22-366 | 28/02/2022 | 28/02/2022 | STEELCONC AND ASSOCIATES | 3.86 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Augmentation of Nischintapur piped water supply scheme. | SM/09720 | Augmentation | Work Order for Laying Distribution system, & FHTC (3145 nos) for Augmentation of Nischintapur PWSS under Amta-II Block under Uluberia Sub-Division under Howrah Division PHE Dte. | AE/Ulu | JE/USD | ORD/000387/2021-2022 | 184/HD | 31/01/2022 | 31/05/2022 | VISHAL CONSTRUCTION CO. | 348.97 | 345.67 | 99.06 | 100
4 | HOWRAH |  | Howrah Division | Augmentation of Nischintapur piped water supply scheme. | SM/09720 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2021-2022 | 204/HD | 01/02/2022 | 01/02/2022 | Resource Division | 19.32 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Augmentation of Nischintapur piped water supply scheme. | SM/09720 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2022-2023 | 1222/HD | 09/06/2022 | 09/06/2022 | Resource Division | 6.21 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Augmentation of Nischintapur piped water supply scheme. | SM/09720 | Augmentation | Work Order for Sinking of 1 (One) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Augmentation of Nischintapur PWSS of Amta-II Block of Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000608/2022-2023 | 2724/HD | 14/12/2022 | 13/01/2023 | DEV DAS SHAW | 13.64 | 12.89 | 94.49 | 100
7 | HOWRAH |  | Electrical | Augmentation of Nischintapur piped water supply scheme. | SM/09720 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Nischintapur water supply scheme T.W. No. New, Block: Amta-II, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000036/2023-2024 | 1713/ED | 18/04/2023 | 17/07/2023 | PADMA ENGINEERING CO. | 10.74 | 10.4 | 96.8 | 80
8 | HOWRAH |  | Howrah Division | Augmentation of Nischintapur piped water supply scheme. | SM/09720 | Augmentation | Interconnection between 3rd TW with LDS for Augmentation of Nischintapur Piped Water Supply scheme in Amta-II Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000313/2024-2025 | 4858/HD | 22/11/2024 | 12/12/2024 | DEV DAS SHAW | 15.37 | 4 | 26.04 | 100
9 | HOWRAH |  | Howrah Division | Augmentation of Nischintapur piped water supply scheme. | SM/09720 | Augmentation | Quotation money depostion for new service connection at Nischintapur Water Supply Scheme |  |  | BILL/01743/2023-2024 | BP-2023-24-775 | 29/03/2024 | 29/03/2024 | WBSEDCL | 15.58 | 0 | 0 | 0
10 | HOWRAH |  | Howrah Division | Augmentation of Nischintapur piped water supply scheme. | SM/09720 | Augmentation | Additional LDS work to reduce water scanty problem from 3rd TW to Ghoshpara at Mouza Sheoraberia of Nischintapur PWSS under Amta-II Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000114/2025-2026 | 3145/HD | 15/07/2025 | 29/08/2025 | KALIDAS ENTERPRISE | 21.67 | 0 | 0 | 80
11 | HOWRAH |  | Howrah Division | Augmentation of Nischintapur piped water supply scheme. | SM/09720 | Augmentation | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Amta-II Block) (PART-B) | AE HQ |  | ORD/000219/2025-2026 | 4117/HD | 14/10/2025 | 13/11/2025 | ABONTICA ENTERPRISE | 4.79 | 0 | 0 | 0
12 | HOWRAH |  | Howrah Division | Augmentation of Nischintapur piped water supply scheme. | SM/09720 | Augmentation | Additional LDS work to reduce water scanty problem from 4th TW to Nischintapur at Mouza Nischintapur of Nischintapur PWSS under Amta-II Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu |  | ORD/000279/2025-2026 | 4413/HD | 25/11/2025 | 09/01/2026 | A. R. CONSTRUCTION | 22.93 | 0 | 0 | 0
13 | HOWRAH |  | Howrah Division | Augmentation of Nischintapur piped water supply scheme. | SM/09720 | Augmentation | Construction of Two storied switch room (3.6 x3.0)with water supply & sanitary arrangement at 3rd Tube well site of Nischintapur W/S scheme (SM/09720) of Amta-II Block under Uluberia Sub-Division under the Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000317/2024-2025 | 4859/HD | 22/11/2024 | 21/01/2025 | DEV DAS SHAW | 7.79 | 0 | 0 | 100
14 | HOWRAH |  | Howrah Division | Augmentation of Nischintapur piped water supply scheme. | SM/09720 | Augmentation | Retrofitting of Pump house and ancillary work of HW Site, 2nd TW, 3rd TW site of Nischintapur W/S scheme at Amta-II Block under Uluberia Sub-Division of Howrah Division P.H.E Dte. | AE/Ulu | JE/USD | ORD/000404/2024-2025 | 1473/AE/USD | 14/01/2025 | 13/02/2025 | MANIRUL ISLAM | 2.39 | 0 | 0 | 100
15 | HOWRAH |  | Howrah Division | Augmentation of Nischintapur piped water supply scheme. | SM/09720 | Augmentation | Structural repairing and renovation of the 3.50 lakh liter capacity OHR at HW site of Nischintapur PWSS under Amta-II block, under Uluberia Sub-Division PHE Dte under Howrah Division PHE Dte. (SM/09720) | AE/Ulu | JE/USD | ORD/000081/2025-2026 | 2764/HD | 12/06/2025 | 12/07/2025 | MANIRUL ISLAM | 11.36 | 0 | 0 | 100
16 | HOWRAH |  | Howrah Division | Augmentation of Nischintapur piped water supply scheme. | SM/09720 | Augmentation | Retrofitting work of boundary wall along with Approach Road and other ancillary works at HW Site of Nischintapur W/S scheme within Amta-II Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000082/2025-2026 | 2765/HD | 12/06/2025 | 27/07/2025 | MANIRUL ISLAM | 10.71 | 0 | 0 | 100
17 | HOWRAH |  | Howrah Division | Augmentation of Nischintapur piped water supply scheme. | SM/09720 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2025-2026 | 4146/HD | 15/10/2025 | 15/10/2025 | Resource Division | 1.23 | 0 | 0 | 0
Total | [13 empty] | 1029.76 | 372.96 | 36.22