## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. | SM/09930 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Mato PWSS, Amta-I Block Under Uluberia SubDivision of Howrah Division PHE Dte. | AE/Ulu | JE/USD | ORD/000268/2021-2022 | 2150/HD | 01/12/2021 | 16/12/2021 | RADIANT | 3.07 | 3.07 | 100 | 0
2 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. | SM/09930 | Augmentation | Indent of Material |  |  | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 14/03/2022 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. | SM/09930 | Augmentation | Work Order for Laying HDPE pipeline & providing Functional Household Tap Connection (FHTC) at Augumentation of Mato Water Supply Scheme under Amta-I block under Uluberia SubDivision under Howrah Division, PHE Dte. (Part-C) Mouza-GHORADAHA | AE/Ulu | JE/USD | ORD/000007/2022-2023 | 806/HD | 07/04/2022 | 22/05/2022 | JOY CHANDI CONSTRUCTION | 64.62 | 66.51 | 102.92 | 100
4 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. | SM/09930 | Augmentation | Work Order for Laying HDPE pipeline & providing Functional Household Tap Connection (FHTC) at Augumentation of Mato Water Supply Scheme under Amta-I block under Uluberia SubDivision under Howrah Division, PHE Dte. (Part-B) Mouza-BARUE | AE/Ulu | JE/USD | ORD/000006/2022-2023 | 805/HD | 07/04/2022 | 22/05/2022 | BISWAJIT BAG | 65.21 | 67.16 | 102.99 | 100
5 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. | SM/09930 | Augmentation | Work Order for Dismantling, Demolition and Disposal of Rubbish, reinforcement, broken pipes & specials, Debris and filling the site upto existing ground level and clearing properly including complete in all respect of 136 cum capacity & 20.0 m staging height dilapidated RCC Over head Reservoir of Mato water supply scheme of Amta-I Blockunder Uluberia Sub-Division of Howrah Divsion PHE Dte. | AE/Ulu |  | ORD/000697/2022-2023 | 328/HD | 24/01/2023 | 25/03/2023 | BISWAJIT BAG | 3.89 | 3.89 | 100 | 0
6 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. | SM/09930 | Augmentation | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-B) (Phase-1) | AE/Ulu | JE/USD | ORD/000441/2022-2023 | 524/AE/USD | 27/09/2022 | 11/11/2022 | BISWAJIT BAG | 4.99 | 4.91 | 98.31 | 0
7 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. | SM/09930 | Augmentation | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-B) (Phase-2) | AE/Ulu | JE/USD | ORD/000442/2022-2023 | 525/AE/USD | 27/09/2022 | 11/11/2022 | BISWAJIT BAG | 4.99 | 5.11 | 102.31 | 0
8 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. | SM/09930 | Augmentation | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-B) (Phase-3) | AE/Ulu | JE/USD | ORD/000443/2022-2023 | 526/AE/USD | 27/09/2022 | 11/11/2022 | BISWAJIT BAG | 4.8 | 4.9 | 102.09 | 0
9 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. | SM/09930 | Augmentation | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-B) (Phase-4) | AE/Ulu | JE/USD | ORD/000444/2022-2023 | 527/AE/USD | 27/09/2022 | 11/11/2022 | BISWAJIT BAG | 4.98 | 5.13 | 102.97 | 0
10 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. | SM/09930 | Augmentation | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-C) (Phase-2) | AE/Ulu | JE/USD | ORD/000449/2022-2023 | 531/AE/USD | 27/09/2022 | 11/11/2022 | JOY CHANDI CONSTRUCTION | 4.94 | 5.07 | 102.7 | 0
11 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. | SM/09930 | Augmentation | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-C) (Phase-5) | AE/Ulu | JE/USD | ORD/000452/2022-2023 | 534/AE/USD | 27/09/2022 | 11/11/2022 | JOY CHANDI CONSTRUCTION | 4.97 | 5.11 | 102.79 | 0
12 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. | SM/09930 | Augmentation | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-C) (Phase-6) | AE/Ulu | JE/USD | ORD/000453/2022-2023 | 535/AE/USD | 27/09/2022 | 11/11/2022 | JOY CHANDI CONSTRUCTION | 4.98 | 5.09 | 102.34 | 0
13 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. | SM/09930 | Augmentation | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-B) (Phase-5) | AE/Ulu | JE/USD | ORD/000446/2022-2023 | 528/AE/USD | 27/09/2022 | 11/11/2022 | BISWAJIT BAG | 5 | 5.09 | 101.92 | 0
14 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. | SM/09930 | Augmentation | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-B) (Phase-6) | AE/Ulu | JE/USD | ORD/000447/2022-2023 | 529/AE/USD | 27/09/2022 | 11/11/2022 | BISWAJIT BAG | 4.98 | 5.09 | 102.25 | 0
15 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. | SM/09930 | Augmentation | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-C) (Phase-1) | AE/Ulu | JE/USD | ORD/000448/2022-2023 | 530/AE/USD | 27/09/2022 | 11/11/2022 | JOY CHANDI CONSTRUCTION | 4.99 | 5.13 | 102.89 | 0
16 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. | SM/09930 | Augmentation | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-C) (Phase-3) | AE/Ulu | JE/USD | ORD/000450/2022-2023 | 532/AE/USD | 27/09/2022 | 11/11/2022 | JOY CHANDI CONSTRUCTION | 4.92 | 5.06 | 102.82 | 0
17 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. | SM/09930 | Augmentation | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-C) (Phase-4) | AE/Ulu | JE/USD | ORD/000451/2022-2023 | 533/AE/USD | 27/09/2022 | 11/11/2022 | JOY CHANDI CONSTRUCTION | 4.97 | 5.07 | 102.01 | 0
18 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. | SM/09930 | Augmentation | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-C) (Phase-7) | AE/Ulu | JE/USD | ORD/000454/2022-2023 | 536/AE/USD | 27/09/2022 | 11/11/2022 | JOY CHANDI CONSTRUCTION | 4.99 | 5.14 | 102.92 | 0
19 | HOWRAH |  | Electrical | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. | SM/09930 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MATO PIPED W/S SCHEME, T.W. No. V, Block: Amta-I, District - Howrah under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5,Junior Engineer6 | ORD/002507/2023-2024 | 423/ED | 29/02/2024 | 29/05/2024 | DEY ENTERPRISE | 10.43 | 10.16 | 97.4 | 85
20 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. | SM/09930 | Augmentation | Sinking of 1 (one) Nos. replaced & 1 (one) Nos new (4th) Tube Well 250 X 150 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000628/2023-2024 | 1214/HD | 11/03/2024 | 10/05/2024 | LOKENATH ENTERPRISES | 30.28 | 27.64 | 91.27 | 100
21 | HOWRAH |  | Electrical | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. | SM/09930 | Augmentation | Quotation for new service connection for Mato w/s scheme, P/H No. 5, near Ghoradaha Primary School Block- Amta- I, Dist. - Howrah. Application No. 1007444170 Ref. id: 106409240 SM/09930 |  |  | BILL/06163/2023-2024 | 798 | 23/02/2024 | 23/02/2024 | WBSEDCL | 14.15 | 0 | 0 | 0
22 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. | SM/09930 | Augmentation | Work Order for Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (Ref.OHR Drawing No.PC-I/OHR/07/2012 , Sheet No.1&2) (pile foundation)& Laying of HDPE & DI pipeline at (Part-A) Mouza-MATO & providing Functional Household Tap Connection (FHTC) at Augumentation of Mato Pipe Water Supply Scheme at Amta-I block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu | JE/USD | ORD/000394/2022-2023 | 1928/HD | 19/09/2022 | 24/05/2025 | KAMRULA CONSTRUCTION CO | 164.72 | 94.92 | 57.62 | 92
23 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. | SM/09930 | Augmentation | Additional laying distribution pipeline with FHTC at Mato PWSS of Amta-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Location: Ghoradaha, Barui & Mato part) | AE/Ulu | JE/USD | ORD/000631/2024-2025 | 1226/HD | 05/03/2025 | 19/04/2025 | MA DURGA ENTERPRISE | 26.57 | 0 | 0 | 0
24 | HOWRAH |  | Howrah Division | Augmentation of Ground Water Based Mato PWSS to accommodate FHTC in Amta-I Block Within Howrah District under Howrah Division PHE Dte. | SM/09930 | Augmentation | Construction of Kiosk (one no (Size inside 3.0 x 3.0m)) at 5th TW Site and interconnection with 5thTW and ancilary works at Mato PWSS under uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000911/2024-2025 | 1751/AE/USD | 04/03/2025 | 03/04/2025 | MA DURGA ENTERPRISE | 3.35 | 0 | 0 | 100
Total | [13 empty] | 963.98 | 339.24 | 35.19