## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | Work Order for Soil Investigation for the work of Construction of R.C.C Elevated Reservoir of Capacity 1000m3 Staging Height 20 mtr. For Paschim Bainan W/S Scheme under Uluberia Sub-Division, under Howrah Division, P.H.E.Dte. | AE/Ulu | JE/USD | ORD/000394/2021-2022 | 221/HD | 03/02/2022 | 23/02/2022 | PROSENJIT DAS | 0.65 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Paschim Bainan PWSS, Bagnan-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu | JE/USD | ORD/000264/2021-2022 | 2146/HD | 01/12/2021 | 16/12/2021 | RADIANT | 3.89 | 3.89 | 100 | 0
3 | HOWRAH |  | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | Work Order for Sinking of 3 (Three) nos PVC big dia Tube well 300 mm x 200 mm dia of 250 mtr deep for Augmentation of Paschim Bainan W/S scheme at Bagnan-I Block in Uluberia SubDivision P.H.E. Dte. under Howrah Division, P.H.E Dte. | AE/Ulu | JE/USD | ORD/000030/2022-2023 | 1010/HD | 05/05/2022 | 04/06/2022 | AUXILIARY TUBEWELL DRILLERS | 49.48 | 45.68 | 92.33 | 0
4 | HOWRAH |  | Electrical | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | Service connection for P.H. No.-III of Ground Based Piped Water Supply Scheme for Paschim Bainan | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000011/2022-2023 | 1006615110/Quot/03 | 10/08/2022 | 10/08/2023 | WBSEDCL | 0.68 | 0 | 0 | 0
5 | HOWRAH |  | Electrical | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000308/2021-2022 | GO2122007937PH | 05/01/2022 | 05/01/2023 | WBSEDCL | 0.68 | 0 | 0 | 0
6 | HOWRAH |  | Electrical | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | Quotation bill for service connection P.H. No.-III at Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000010/2022-2023 | 1046/ED | 21/08/2022 | 21/08/2023 | WBSEDCL | 0.68 | 0 | 0 | 0
7 | HOWRAH |  | Electrical | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | Supply, Delivery & Installation of submersible pumping machinery & other Electrical/Mechanical equipments etc. including allied works fo Paschim Bainan W/S. Sch. TW-I | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000049/2022-2023 | 2103/HMSD | 24/11/2022 | 24/12/2022 | KARUNAMOY ENGINEERING | 4.87 | 4.87 | 100 | 0
8 | HOWRAH |  | Electrical | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | Electric Supply at Bagnan |  |  | VCH/002238/2022-2023 | 46 | 22/08/2022 | 22/08/2022 | WBSEDCL | 0.68 | 0 | 0 | 0
9 | HOWRAH |  | Electrical | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | Electric Supply at Paschim Bainan |  |  | VCH/002245/2022-2023 | 53 | 23/08/2022 | 23/08/2022 | WBSEDCL | 0.68 | 0 | 0 | 0
10 | HOWRAH |  | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | Indent of Material |  |  | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 14/03/2022 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
11 | HOWRAH |  | Electrical | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | New Connection in for Paschim Bainan W/S. Sch. |  |  | VCH/002696/2022-2023 | 94 | 20/10/2022 | 20/10/2022 | WBSEDCL | 4.12 | 0 | 0 | 0
12 | HOWRAH |  | Electrical | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | New Connection at Paschim Bainan W/S. Sch. |  |  | VCH/002587/2022-2023 |  | 17/10/2022 | 17/10/2022 | WBSEDCL | 4.12 | 0 | 0 | 0
13 | HOWRAH |  | Electrical | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | Supply, Delivery & Installation of submersible pumping machinery & other Electrical/Mechanical equipments etc. including allied works fo Paschim Bainan W/S. Sch. RW-IV | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000047/2022-2023 | 1793/ED | 02/11/2022 | 31/01/2023 | HINDUSTAN ENGINEERING CORPORATION ( E & M ) | 10.84 | 10.83 | 99.95 | 0
14 | HOWRAH |  | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | Construction of switch room (3.60m X 3.0m) with water supply & sanitary arrangement at 4th tube well site of Augmentation of Paschim Bainan PWSS of Bagnan-I Block under Uluberia Sub-Division under Howrah Division, P.H.E Dte. (As per approved drawing of Howrah Division, PHE Dte). | AE/Ulu | JE/USD | ORD/000438/2022-2023 | 510/AE/USD | 27/09/2022 | 11/11/2022 | K.N ENTERPRISE | 4.45 | 4.24 | 95.33 | 0
15 | HOWRAH |  | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | Development of 5th Tube well at Augmentation of Paschim Bainan PWSS of Bagnan-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu |  | ORD/000872/2022-2023 | 943/AE/USD | 22/03/2023 | 21/04/2023 | LOKENATH ENTERPRISES | 0.71 | 0.71 | 100 | 100
16 | HOWRAH |  | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000034/2022-2023 | 1955/HD | 21/09/2022 | 21/09/2022 | Resource Division | 0.05 | 0 | 0 | 0
17 | HOWRAH |  | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000011/2022-2023 | 1402/HD | 07/07/2022 | 07/07/2022 | Resource Division | 87.96 | 0 | 0 | 0
18 | HOWRAH |  | Electrical | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | Quotation Bill for New Service Connection at Paschim Bainan W/S. Sch. PH-V |  |  | BILL/03699/2023-2024 | 231 | 01/09/2023 | 01/09/2023 | WBSEDCL | 4.96 | 0 | 0 | 0
19 | HOWRAH |  | Electrical | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Paschim Bainan water supply scheme, T.W. No. V, VI & VII, Block: Bagnan-I, District - Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000883/2023-2024 | 3456/ED | 11/08/2023 | 09/11/2023 | SANKAR PRASAD DUTTA & CO. | 33.21 | 10.59 | 31.89 | 35
20 | HOWRAH |  | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | Work Order for Augmentation of Paschim Bainan Water Supply scheme with LDS, Laying of Rising main & FHTC work at Bagnan-I Block of Howrah District under Howrah Division, PHE Dte. | AE/Ulu | JE/USD | ORD/000528/2021-2022 | 592/HD | 15/03/2022 | 15/01/2023 | S.P. CONSTRUCTION | 1002.85 | 899.81 | 89.73 | 100
21 | HOWRAH |  | Electrical | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Paschim Bainan water supply scheme, T.W. No. III, Block: Bagnan-I, District - Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000031/2022-2023 | 1915/ED | 21/11/2022 | 19/02/2023 | MAA KALI ENTERPRISE | 10.01 | 9.74 | 97.26 | 97
22 | HOWRAH |  | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | Connection with 5th Tube well site to distribution line with providing FHTC at Paschim Bainan PWSS under Bagnan-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000022/2024-2025 | 248/AE/USD | 12/06/2024 | 12/07/2024 | S R TRADING CORPORATION | 4.71 | 4.63 | 98.3 | 100
23 | HOWRAH |  | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | Construction of 1000 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection at Augmentation of Paschim Bainan PWSS of Bagnan-I Block under Uluberia Sub Division under Howrah Division PHE Dte. | AE/Ulu | JE/USD | ORD/000525/2023-2024 | 607/HD | 09/02/2024 | 29/01/2026 | PIKASU BOSE | 239.3 | 17.56 | 7.34 | 24
24 | HOWRAH |  | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Bagnan-I Block) | AE HQ |  | ORD/000229/2025-2026 | 4127/HD | 14/10/2025 | 13/11/2025 | ABONTICA ENTERPRISE | 4.79 | 0 | 0 | 0
25 | HOWRAH |  | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | Construction of switch room (5.40m X 3.60m) with water supply & sanitary arrangement at Head Work site of Augmentation of Paschim Bainan PWSS of Bagnan-I Block under Uluberia Sub-Division under Howrah Division, P.H.E Dte. (As per approved drawing of Howrah Division, PHE Dte). | AE/Ulu | JE/USD | ORD/000420/2022-2023 | 509/AE/USD | 27/09/2022 | 11/11/2022 | S.P. CONSTRUCTION | 4.99 | 0 | 0 | 100
26 | HOWRAH |  | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000286/2024-2025 | 4815/HD | 19/11/2024 | 17/02/2025 | TECH VISION | 12.67 | 0.85 | 6.74 | 100
27 | HOWRAH |  | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | Additional laying distribution pipeline with FHTC at Paschim Bainan PWSS of Bagnan-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000605/2023-2024 | 1137/HD | 06/03/2024 | 31/12/2024 | JOY CHANDI CONSTRUCTION | 96.07 | 72.74 | 75.71 | 100
28 | HOWRAH |  | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000041/2025-2026 | 4146/HD | 15/10/2025 | 15/10/2025 | Resource Division | 1.85 | 0 | 0 | 0
29 | HOWRAH |  | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | Quotation for providing dedicated transformer at Paschim Bainan Water Supply Scheme, PH NO- I in the district Howrah under Electrical Division, PHE Dte. ( SM/10020), Reference Id- 860321509, Application ID- 100000126309 |  |  | BILL/01022/2024-2025 | BP-2024-25-547 | 13/03/2025 | 13/03/2025 | WBSEDCL | 12.61 | 0 | 0 | 0
30 | HOWRAH |  | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | Quotation for new service connection for Augmentation of paschim w/s scheme, Ph No- VII (koria), in the district Howrah under Electrical Division, PHE Dte. ( SM/10020 ) Reference Id- 106993987, Application no- 1008460992 |  |  | BILL/01136/2024-2025 | W/176 | 30/07/2025 | 30/07/2025 | WBSEDCL | 8.63 | 0 | 0 | 0
31 | HOWRAH |  | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | Quotation for new service connection for Augmentation of paschim w/s scheme, Ph No- VI (khajutty), in the district Howrah under Electrical Division, PHE Dte. ( SM/10020 ) Reference Id- 106992039, Application no- 1008456690 |  |  | BILL/01135/2024-2025 | W/175 | 31/07/2025 | 31/07/2025 | WBSEDCL | 13.44 | 0 | 0 | 0
32 | HOWRAH |  | Howrah Division | Augmentation of Ground Based Piped Water Supply Scheme for Paschim Bainan to Accomodate FHTC. | SM/10020 | Augmentation | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte.(Phase-II). | AE HQ | je_blk_ballyjag_how | ORD/000199/2025-2026 | 3670/HD | 02/09/2025 | 30/04/2026 | TECH VISION | 21.25 | 0 | 0 | 22
Total | [13 empty] | 2159.05 | 1086.14 | 50.31