## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Central Drilling | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | FUEL CHARGES FOR CAR NO. WB-25H-1114, WB-05-2798, WB-04H-6870 & WB-25H-5187. |  |  | ORD/000028/2022-2023 | 713/CDD | 26/07/2022 | 25/08/2022 | MIRA SERVICE STATION | 1.08 | 1.08 | 100 | 0
2 | HOWRAH |  | Central Drilling | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-IV & ABOVE) (AMBASSADOR / EQUIVALENT) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE SEMC-II, PHE DTE. |  |  | ORD/000222/2021-2022 | 236/CMSD-I (D) | 14/12/2021 | 29/12/2021 | SIDDHARTHA CHATTERJEE | 0.95 | 0.86 | 90.93 | 0
3 | HOWRAH |  | Central Drilling | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | PROVIDING ADDITIONAL BENTONITE FOR CONSTRUCTION OF TUBE WELL AT KANPUR W/S SCHEME (Z-II, TW-II) AMTA-I BLOCK AND OTHERS UNDER CDD, PHE DTE. |  |  | ORD/000094/2022-2023 | 198/CMSD-I(D) | 16/06/2022 | 19/06/2022 | M/S PRACHI ENGINEERING | 0.89 | 0.59 | 66.67 | 0
4 | HOWRAH |  | Central Drilling | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | PROVIDING DRILLING CREWS AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 220 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR AUG OF KANPUR W/S SCHEME (Z-II, TW-II) AMTA-I BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. |  |  | ORD/000013/2022-2023 | 450/CDD | 24/05/2022 | 23/06/2022 | M/S SAIKAT ENTERPRISE | 13.21 | 11.74 | 88.85 | 0
5 | HOWRAH |  | Central Drilling | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 220 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR AUG. OF KANPUR W/S SCHEME (Z-II, HW) AMTA-I BLOCK UNDER HOWRAH DISTRICT, CDD, PHE DTE. |  |  | ORD/000012/2022-2023 | 451/CDD | 24/05/2022 | 23/06/2022 | M/S SAIKAT ENTERPRISE | 13.21 | 11.57 | 87.59 | 0
6 | HOWRAH |  | Central Drilling | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | PROVIDING TUBE WELL MATERIALS OF 200 MM NOMINAL DIA CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT KANPUR (Z-II) W/S SCHEME, UNDER HOWRAH DISTRICT, CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000037/2022-2023 | 273/CMSD-II (D) | 01/06/2022 | 16/06/2022 | M/S PRACHI ENGINEERING | 4.83 | 3.63 | 75.18 | 0
7 | HOWRAH |  | Central Drilling | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 220 MTRS DEPTH) BY KORES RIG MACHINE FOR KANPUR (Z-II) W/S SCH, AMTA BLOCK UNDER HOWRAH DISTRICT, CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000038/2022-2023 | 271/CMSD-II (D) | 01/06/2022 | 16/06/2022 | M/S PRACHI ENGINEERING | 3.53 | 3.38 | 95.77 | 0
8 | HOWRAH |  | Central Drilling | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | PROVIDING TUBE WELL MATERIALS OF 300 MM NOMINAL DIA CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT KANPUR (Z-II) W/S SCH, UNDER HOWRAH DISTRICT, CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000039/2022-2023 | 272/CMSD-II (D) | 01/06/2022 | 16/06/2022 | M/S PRACHI ENGINEERING | 4.81 | 4.63 | 96.25 | 0
9 | HOWRAH |  | Central Drilling | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR HANRAL W/S SCH, POLBA DADPUR BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000158/2022-2023 | 293/CDD | 27/04/2022 | 27/05/2022 | PADMA ENGINEERING & CO. | 11.23 | 0.15 | 1.35 | 100
10 | HOWRAH |  | Central Drilling | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | SUPPLY & DELIVERY OF CONSUMABLES AT SITE WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL AT AUG. OF MELLOCK PWSS, BAGNAN-II BLOCK, HOWRAH DISTRICT UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000114/2022-2023 | 393/CMSD-II (D) | 01/08/2022 | 16/08/2022 | M/S PRACHI ENGINEERING | 1.88 | 0.02 | 0.95 | 0
11 | HOWRAH |  | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000043/2022-2023 | 2639/HD | 09/12/2022 | 09/12/2022 | Resource Division | 33.45 | 0 | 0 | 0
12 | HOWRAH |  | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Indent of Material |  |  | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 14/03/2022 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
13 | HOWRAH |  | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Kanpur PWSS, Amta-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. |  |  | VCH/000828/2021-2022 | BP-2021-22-367 | 28/02/2022 | 28/02/2022 | STEELCONC AND ASSOCIATES | 3.86 | 0 | 0 | 0
14 | HOWRAH |  | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Work Order for Construction of switch room (3.60m x 3.0m) with water supply & sanitary arrangement at 3rd tube well site of Augmentation of Kanpur(Zone-II) PWSS of Amta-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. (As per approved drawing of Howrah Division, PHE Dte.) | AE/Ulu |  | ORD/000578/2022-2023 | 2595/HD | 07/12/2022 | 05/02/2023 | A.N ROY & CO | 4.79 | 4.58 | 95.62 | 100
15 | HOWRAH |  | Electrical | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipment's etc. including allied works for Kanpur water supply scheme, T.W. No. I (Replacement tubewell), Block - Amta - I District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | ORD/000062/2022-2023 | 2105/HMSD | 24/11/2022 | 24/12/2022 | MOITRA ENGINEERING CO. | 4.82 | 4.81 | 99.89 | 0
16 | HOWRAH |  | Central Drilling | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBEWELL BY DEPARTMENTAL RIG MACHINE AT AMODGHATA W/S SCH TW-II, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000367/2022-2023 | 377/CMSD-II | 01/08/2022 | 16/08/2022 | C.M. ENTERPRISE | 2.93 | 0.02 | 0.64 | 0
17 | HOWRAH |  | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Work Order for Interconnection between tube wells & OHR at Augmentation of Kanpur Zone-II PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu |  | ORD/000051/2023-2024 | 1843/HD | 02/05/2023 | 01/07/2023 | PRADIP KUMAR JATI | 9.35 | 9.43 | 100.79 | 100
18 | HOWRAH |  | Central Drilling | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 210 mtrs. Depth) by utilising Departmental machineries for baidyapur W/S Scheme, Tarakeswar block under hooghly District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000433/2022-2023 | 1724/CDD | 29/12/2022 | 28/01/2023 | DEY ENTERPRISE | 13.83 | 2.27 | 16.43 | 0
19 | HOWRAH |  | Electrical | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Supply, Delivery & Installation of S/M/P & other E/M equipments etc. Including allied works for Kanpur W/S. Sch. Z-II, TW-II |  |  | ORD/002088/2022-2023 | 1549/ED | 20/09/2022 | 19/12/2022 | D. K. ELECTRIC | 10.14 | 10.13 | 99.96 | 1
20 | HOWRAH |  | Electrical | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | "Supply, Delivery & Installation of S/M/P & other E/M equipments etc. Including allied works for Kanpur W/S. Sch. Z-II, TW-II Howarah" |  |  | ORD/002114/2022-2023 | 1549//ED | 20/09/2022 | 27/09/2022 | D. K. ELECTRIC | 10.13 | 0 | 0 | 1
21 | HOWRAH |  | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000038/2023-2024 | 2753/HD | 28/07/2023 | 28/07/2023 | Resource Division | 18.48 | 0 | 0 | 0
22 | HOWRAH |  | Electrical | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Quotation Bill for New Service Connection at Kanpur W/S. Sch. TW-VI |  |  | BILL/04172/2023-2024 | 405 | 09/11/2023 | 09/11/2023 | WBSEDCL | 3.34 | 0 | 0 | 0
23 | HOWRAH |  | Electrical | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Quotation bill for New Service connection at Aug. of Kanpur W/S. Sch. |  |  | BILL/00789/2022-2023 | 159 | 10/02/2023 | 10/02/2023 | WBSEDCL | 6.45 | 0 | 0 | 0
24 | HOWRAH |  | Electrical | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Hire & Fuel Charges Bills |  |  | BILL/01890/2022-2023 | 230 | 29/03/2023 | 29/03/2023 | JAMECO AGENCIES PRIVATE LIMITED. | 1.72 | 0 | 0 | 0
25 | HOWRAH |  | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Additional Laying of pipeline Augmentation of Kanpur Zone-II PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Basantapur part mouza). | AE/Ulu |  | ORD/000357/2023-2024 | 683/AE/USD | 06/11/2023 | 05/01/2024 | PRADIP KUMAR JATI | 3.51 | 0 | 0 | 0
26 | HOWRAH |  | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Additional Laying of pipeline Augmentation of Kanpur Zone-II PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (Pearapur & Habla Mouza) | AE/Ulu | JE/USD | ORD/000347/2024-2025 | 5290/HD | 17/12/2024 | 31/01/2025 | SUNIRMAN ENTERPRISE | 13.41 | 0 | 0 | 0
27 | HOWRAH |  | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Work Order for Laying HDPE pipeline & providing Functional Household Tap Connection (FHTC) at Augumentation of Kanpur Piped Water Supply Scheme (Zone-II) under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-A) Mouza-Habla | AE/Ulu | JE/USD | ORD/000240/2022-2023 | 1714/HD | 24/08/2022 | 08/10/2022 | USHA CONCERN | 33.16 | 33.13 | 99.9 | 20
28 | HOWRAH |  | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Work Order for Laying HDPE pipeline & providing Functional Household Tap Connection (FHTC) at Augumentation of Kanpur Piped Water Supply Scheme (Zone-II) under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-D) Mouza-Bhetkepara | AE/Ulu | JE/USD | ORD/000238/2022-2023 | 1712/HD | 24/08/2022 | 08/10/2022 | BISWAJIT BAG | 50.4 | 50.4 | 99.99 | 100
29 | HOWRAH |  | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Work Order for Laying HDPE pipeline & Providing Functional Household Tap Connection (FHTC) at Augumentation of Kanpur Piped Water Supply Scheme (Zone-II) under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-C) Mouza-Basantapur. | AE/Ulu | JE/USD | ORD/000343/2022-2023 | 1855/HD | 09/09/2022 | 08/11/2022 | M/S EL-CON | 225.77 | 190.08 | 84.19 | 100
30 | HOWRAH |  | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Work Order for Laying HDPE pipeline & providing Functional Household Tap Connection (FHTC) at Augumentation of Kanpur Piped Water Supply Scheme (Zone-II) under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-B) Mouza-PearapurHowrah. | AE/Ulu | JE/USD | ORD/000239/2022-2023 | 1713/HD | 24/08/2022 | 08/10/2022 | SUNIRMAN ENTERPRISE | 38.67 | 38.59 | 99.78 | 100
31 | HOWRAH |  | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Work Order for Construction of 500 cum Capacity 20 Mtr. staging height RCC Over Head Reservoir (Ref. Drawing No.PC-I/OHR/09/2012 (Sheet No.1&2) & Laying HDPE & DI pipeline & providing Functional Household Tap Connection (FHTC) at Augumentation of Kanpur Piped Water Supply Scheme (Zone-II) under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-E) | AE/Ulu | JE/USD | ORD/000357/2022-2023 | 1908/HD | 15/09/2022 | 14/03/2023 | PRADIP KUMAR JATI | 155.22 | 155.09 | 99.92 | 100
32 | HOWRAH |  | Electrical | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Kanpur water supply scheme, T.W. No.-II, Block: Amta-I, District - Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer6 | ORD/001387/2023-2024 | 4737/ED | 15/12/2023 | 14/03/2024 | D. K. ELECTRIC | 10.74 | 10.74 | 99.95 | 100
33 | HOWRAH |  | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Additional Laying of pipeline Augmentation of Kanpur Zone-II PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Bhetkepara mouza) | AE/Ulu |  | ORD/000445/2023-2024 | 216/HD | 17/01/2024 | 17/03/2024 | BISWAJIT BAG | 13.11 | 12.75 | 97.23 | 100
34 | HOWRAH |  | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Wall writing IEC message along with logo picture etc. of multiple colour as will be supplied by the PHE Dte. on smooth durable wall surface preferably of Govt. premises boundary wall under Amta-I and Amta-II Block of Uluberia Sub Division under Howrah Division PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000549/2023-2024 | 847/HD | 22/02/2024 | 08/03/2024 | TRIMARV SOLUTIONS PRIVATE LIMITED | 4.1 | 4.02 | 98.07 | 100
35 | HOWRAH |  | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Sinking of additonal 1 (One) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Kanpur Zone-II PWSS of Amta-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000668/2023-2024 | 1307/HD | 14/03/2024 | 13/04/2024 | AUXILIARY TUBEWELL DRILLERS | 14.71 | 13.91 | 94.58 | 100
36 | HOWRAH |  | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Emergent Road restoration work at Basantapur Mouza of Kanpur Zone II PWSS of Amta-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (SM/10021) | AE/Ulu | JE/USD | ORD/000412/2024-2025 | 1483/AE/USD | 16/01/2025 | 05/02/2025 | BISWAJIT BAG | 4.83 | 0 | 0 | 0
37 | HOWRAH |  | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Balance laying distribution pipeline at Kanpur Zone II PWSS of Amta-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte.(Basantapur part) | AE/Ulu |  | ORD/000090/2025-2026 | 2807/HD | 17/06/2025 | 15/09/2025 | PRADIP KUMAR JATI | 96.92 | 0 | 0 | 0
38 | HOWRAH |  | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Construction of boundary wall at HW Site and additional pipeline at Basantupur Mouza of Augmentation of Kanpur Zone-II PWSS under Amta-I in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000456/2023-2024 | 246/HD | 18/01/2024 | 18/03/2024 | PRADIP KUMAR JATI | 52.5 | 33.31 | 63.45 | 70
39 | HOWRAH |  | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | 1 no Kiosk (Size inside 2.44 x 1.52m) and additional laying distribution pipeline with FHTC at Kanpur Zone-II PWSS of Amta-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000046/2024-2025 | 2904/HD | 26/06/2024 | 20/08/2025 | MAITY CONSTRUCTION | 22.06 | 0 | 0 | 100
40 | HOWRAH |  | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Additional laying distribution pipeline with FHTC at Kanpur Zone II PWSS of Amta-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte.(Basantapur part) | AE/Ulu | JE/USD | ORD/000183/2024-2025 | 4425/HD | 30/09/2024 | 28/01/2025 | PRADIP KUMAR JATI | 96.97 | 0 | 0 | 90
41 | HOWRAH |  | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Providing Scheme Information Board at Head works site of different PWSS under uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000058/2025-2026 | 61/AE/USD | 07/04/2025 | 02/05/2025 | ABONTICA ENTERPRISE | 3.76 | 0 | 0 | 100
42 | HOWRAH |  | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Providing Scheme Information Board at Head works site of different PWSS under uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000406/2024-2025 | 1475/AE/USD | 15/01/2025 | 04/02/2025 | ABONTICA ENTERPRISE | 4.26 | 0 | 0 | 100
43 | HOWRAH |  | Electrical | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KANPUR water supply scheme, Zone-II, TW No. IV, Block: Amta-I, District - Howrah under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/003100/2024-2025 | 485/ED | 18/03/2025 | 16/06/2025 | APEX ENGINEERING & PROJECT CO. | 10.94 | 0 | 0 | 95
44 | HOWRAH |  | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Providing and erection of land Information Board (size 0.9m x 0.6m) at different demarcated Lands possessed by PHED for different PWSS under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000092/2025-2026 | 2867/HD | 20/06/2025 | 20/07/2025 | ABONTICA ENTERPRISE | 23.31 | 0 | 0 | 100
45 | HOWRAH |  | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000008/2025-2026 | 4146/HD | 15/10/2025 | 15/10/2025 | Resource Division | 1.23 | 0 | 0 | 0
46 | HOWRAH |  | Howrah Division | Augmentation of Kanpur Piped water supply scheme (Zone-II) | SM/10021 | Augmentation | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte.(Phase-II). | AE HQ | je_blk_ballyjag_how | ORD/000199/2025-2026 | 3670/HD | 02/09/2025 | 30/04/2026 | TECH VISION | 21.25 | 0 | 0 | 22
Total | [13 empty] | 1592.93 | 610.9 | 38.35