## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Augmentation of Maju piped water supply scheme. | SM/10035 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000052/2022-2023 | 2839/HD | 23/12/2022 | 23/12/2022 | Resource Division | 35.16 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Augmentation of Maju piped water supply scheme. | SM/10035 | Augmentation | Indent of Material |  |  | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 14/03/2022 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Augmentation of Maju piped water supply scheme. | SM/10035 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Maju PWSS, Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte |  |  | VCH/000960/2021-2022 | BP-2021-22-407 | 14/03/2022 | 14/03/2022 | STEELCONC AND ASSOCIATES | 4.28 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Augmentation of Maju piped water supply scheme. | SM/10035 | Augmentation | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Maju PWSS at Jagatballavpur Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR | JE Sadar | ORD/000336/2022-2023 | 1835/HD | 08/09/2022 | 18/10/2022 | B K ENTERPRISE | 35.32 | 33.02 | 93.49 | 0
5 | HOWRAH |  | Howrah Division | Augmentation of Maju piped water supply scheme. | SM/10035 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000015/2022-2023 | 1624/HD | 05/08/2022 | 05/08/2022 | Resource Division | 62.17 | 0 | 0 | 0
6 | HOWRAH |  | Electrical | Augmentation of Maju piped water supply scheme. | SM/10035 | Augmentation | Quotation bill for new service connection at Aug. of Maju Khetra W/S. Sch. TW-III |  |  | BILL/00845/2022-2023 | 172 | 28/02/2023 | 28/02/2023 | WBSEDCL | 3.58 | 0 | 0 | 0
7 | HOWRAH |  | Electrical | Augmentation of Maju piped water supply scheme. | SM/10035 | Augmentation | Quotation Bill for New Service Connection at Maju W/S. Sch. TW-IV |  |  | BILL/00909/2022-2023 | 187 | 13/03/2023 | 13/03/2023 | WBSEDCL | 3.06 | 0 | 0 | 0
8 | HOWRAH |  | Electrical | Augmentation of Maju piped water supply scheme. | SM/10035 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MAJU PIPED W/S SCHEME, T.W. No. I (Replacement), Block: Jagatballavpur, District - Howrah under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000374/2024-2025 | 1461/ED | 25/07/2024 | 23/10/2024 | BISALAXMI ENTERPRISE | 11.31 | 10.08 | 89.18 | 30
9 | HOWRAH |  | Electrical | Augmentation of Maju piped water supply scheme. | SM/10035 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Maju water supply scheme, T.W. No. I & II, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000246/2022-2023 | 913/ED | 22/02/2023 | 23/05/2023 | POLYCON ENGINEERS | 21.5 | 21.49 | 99.95 | 30
10 | HOWRAH |  | Electrical | Augmentation of Maju piped water supply scheme. | SM/10035 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Maju water supply scheme, T.W. No. III, Block: Jagatballavpur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000867/2023-2024 | 3440/ED | 11/08/2023 | 09/11/2023 | POLYCON ENGINEERS | 10.75 | 10.47 | 97.38 | 40
11 | HOWRAH |  | Howrah Division | Augmentation of Maju piped water supply scheme. | SM/10035 | Augmentation | Construction of R.C.C Slab Culvert, Construction of 1(one) no. Pump House (5.40m x 3.60m), construction of 2(Two) nos. boundary wall, construction of approach road and land Development at 2nd tubewell site and allied pipe laying work (DI) for connecting tubewell with the distribution main at Maju PWSS under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000032/2024-2025 | 2836/HD | 20/06/2024 | 17/12/2024 | SAMIRON GHOSH | 51.95 | 40.2 | 77.39 | 50
12 | HOWRAH |  | Howrah Division | Augmentation of Maju piped water supply scheme. | SM/10035 | Augmentation | Sinking 2 nos. 250 X 150 mm dia and 240 m deep tube well drilling by direct rotary method with 150 mm. dia. PVC. strainer of 30 m. length having 250 mm dia. 60 m. long PVC housing pipe & 150 mm dia. 150 m. long well pipe alongwith 3m blank pipe all complete including cost of materials at Maju PWSS at Jagatballavpur Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P. H. E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000670/2023-2024 | 1309/HD | 14/03/2024 | 13/05/2024 | ACME CONSTRUCTION | 29.18 | 27.65 | 94.74 | 100
13 | HOWRAH |  | Howrah Division | Augmentation of Maju piped water supply scheme. | SM/10035 | Augmentation | Work Order for Construction Of 700 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir with Rising Main Pipeline Work & Laying Distribution Pipeline & Providing FHTC (Functional Household Tap Connection) with Boundary Wall and Pump House and 2 nos. Canal Crossing of Augmentation of Maju PWSS Jagatballavpur Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000419/2022-2023 | 2095/HD | 12/10/2022 | 09/04/2025 | SAMIRON GHOSH | 838.17 | 572.01 | 68.24 | 50
14 | HOWRAH |  | Howrah Division | Augmentation of Maju piped water supply scheme. | SM/10035 | Augmentation | Work Order for Additional Laying Distribution Pipeline & allied works of Maju PWSS at J.Bpur Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000042/2023-2024 | 1785/HD | 28/04/2023 | 19/08/2024 | SAMIRON GHOSH | 322.25 | 305.79 | 94.89 | 100
Total | [13 empty] | 1941.87 | 1020.7 | 52.56