## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC | SM/10145 | Augmentation | Work Order for Soil Investigation for the work of Construction of R.C.C Elevated Reservoir of Capacity 700m3 Staging Height 20 mtr. for Kalyanpur Birampur W/S Scheme under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/RWS | JE/RWS/Bagnan I | ORD/000415/2021-2022 | 386/HD | 22/02/2022 | 14/03/2022 | PROSENJIT DAS | 0.65 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC | SM/10145 | Augmentation | Work Order for Sinking of 2 (Two) nos PVC big dia Tube well 300 mm x 200 mm dia of 250 mtr deep for Augmentation of Kalyanpur-Birampur W/S scheme at Bagnan-I Block in Uluberia SubDivision P.H.E. Dte. Under Howrah Division, P.H.E Dte. | AE/RWS,AE/Ulu | JE/RWS/Bagnan I | ORD/000028/2022-2023 | 1009/HD | 05/05/2022 | 04/06/2022 | AQUATECH ENGINEERS | 35.2 | 0 | 0 | 0
3 | HOWRAH |  | Electrical | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC | SM/10145 | Augmentation | Supply, Delivery & Installation of submersible pumping machinery & other Electrical/Mechanical equipments etc. including allied works for Kalyanpur Birampur W/S. Sch.PH-II | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000048/2022-2023 | 2101/HMSD | 24/11/2022 | 24/12/2022 | DIPA CHHETRI | 4.25 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC | SM/10145 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000041/2022-2023 | 2639/HD | 09/12/2022 | 09/12/2022 | Resource Division | 12.08 | 0 | 0 | 0
5 | HOWRAH |  | Howrah Division | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC | SM/10145 | Augmentation | Indent of Material |  |  | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 14/03/2022 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC | SM/10145 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Kalyanpur Birampur, Bagnan-I under Uluberia Sub-Division of Howrah Division PHE Dte. |  |  | VCH/000961/2021-2022 | BP-2021-22-408 | 14/03/2022 | 14/03/2022 | RADIANT | 3.68 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC | SM/10145 | Augmentation | WBSRDA PAYMENT |  |  | VCH/000564/2022-2023 |  | 07/09/2022 | 07/09/2022 | WBSRDA | 13.77 | 0 | 0 | 0
8 | HOWRAH |  | Electrical | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC | SM/10145 | Augmentation | Supply, delivery and installation of voltage correcting device and other allied works for Kalyanpur Birampur water supply scheme, P.H. No.-II, District- Howrah under Electrical Division, PHE Dte. |  |  | ORD/001426/2021-2022 | 1245/HMSD | 14/07/2021 | 04/08/2021 | A.G. ENTERPRISE | 2.74 | 0 | 0 | 0
9 | HOWRAH |  | Electrical | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC | SM/10145 | Augmentation | Supply, delivery of electro mechanical equipments for Kalyanpur Birampur water supply scheme, P.H. No. II (Replacement tubewell), District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000069/2022-2023 | 36/HMSD | 05/01/2023 | 04/02/2023 | P.K. ENTERPRISE | 3.55 | 0 | 0 | 0
10 | HOWRAH |  | Electrical | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC | SM/10145 | Augmentation | Supply, delivery of electro mechanical equipments for Kalyanpur Birampur water supply scheme, P.H. No. I (Replacement tubewell), District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000068/2022-2023 | 35/HMSD | 05/01/2023 | 04/02/2023 | J.K. ENGINEERING CO. | 2.87 | 0 | 0 | 0
11 | HOWRAH |  | Electrical | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC | SM/10145 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Kalyanpur Birampur water supply scheme, P.H. No. - I (Replacement Tubewell), Block Bagnan-I District - Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000064/2022-2023 | 2100/HMSD | 24/11/2022 | 24/12/2022 | OSMAN SEKH | 4.12 | 0 | 0 | 0
12 | HOWRAH |  | Howrah Division | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC | SM/10145 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2022-2023 | 1624/HD | 05/08/2022 | 05/08/2022 | Resource Division | 18.99 | 0 | 0 | 0
13 | HOWRAH |  | Electrical | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC | SM/10145 | Augmentation | Shifting of LT OH Line |  |  | BILL/00212/2022-2023 | 144 | 30/01/2023 | 30/01/2023 | WBSEDCL | 0.27 | 0 | 0 | 0
14 | HOWRAH |  | Howrah Division | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC | SM/10145 | Augmentation | Payment against requirement of fund for restoration of PMGSY Road WB-09-250 (T032- Malick Pukur ) |  |  | BILL/00315/2023-2024 | BP-2023-24-115 | 27/06/2023 | 27/06/2023 | WBSRDA | 10.14 | 0 | 0 | 0
15 | HOWRAH |  | Howrah Division | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC | SM/10145 | Augmentation | Payment against requestion of fund for restoration of PMGSY road Package No- WB-09-250 (TO-32- Mallick Pukur) of Augmentation of Kalyanpur and Birampur Water Supply Scheme |  |  | BILL/00548/2023-2024 | BP-2023-24-259 | 31/08/2023 | 31/08/2023 | WBSRDA | 10.14 | 0 | 0 | 0
16 | HOWRAH |  | Howrah Division | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC | SM/10145 | Augmentation | Work Order for Augmentation of Kalyanpur Birampur Water Supply Schemem with LDS, Rising Main, FHTC work, at Bagnan-I Block of Howrah Division, PHE Dte. | AE/Ulu | JE/USD | ORD/000022/2022-2023 | 966/HD | 29/04/2022 | 07/05/2022 | M/S EL-CON | 714.88 | 0 | 0 | 100
17 | HOWRAH |  | Howrah Division | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC | SM/10145 | Augmentation | Work order for Additional laying of pipeline at Augmentation of Kalyanpur Birampur Water Supply Scheme at Bagnan-I Block under Uluberia Sub-Division PHE Dte of Howrah Division PHE Dte. | AE/Ulu | JE/USD | ORD/000089/2023-2024 | 1987/HD | 15/05/2023 | 12/09/2023 | M/S EL-CON | 247.87 | 0 | 0 | 100
18 | HOWRAH |  | Howrah Division | Augmentation of ground based piped Water Supply Scheme for Kalyanpur Birampur to Accomodate FHTC | SM/10145 | Augmentation | Construction of 700 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection at Augmentation of Kalyanpur Birampur PWSS of Bagnan-I Block under Uluberia Sub-Divison under Howrah Division, PHE Dte. | AE/Ulu | JE/USD | ORD/000012/2024-2025 | 2645/HD | 07/06/2024 | 30/09/2025 | UNIQUE AGENCY | 191 | 0 | 0 | 50
Total | [13 empty] | 1789.37 | 0 | 0