## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Jujarsah | SM/10146 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000062/2022-2023 | 2839/HD | 23/12/2022 | 23/12/2022 | Resource Division | 56.12 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Jujarsah | SM/10146 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Jujarsha PWSS, Panchla Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte |  |  | VCH/000957/2021-2022 | BP-2021-22-405 | 14/03/2022 | 14/03/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.36 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Jujarsah | SM/10146 | Augmentation | Indent of Material |  |  | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 14/03/2022 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0 | 0
4 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Jujarsah | SM/10146 | Augmentation | Work Order for Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 2000mm) with Sanitary and water Supply arrangement at 4th T/well site of Jujarsah PWSS at Panchla Block of Howrah District under Howrah Division, PHE Dte.. | AE/SADAR | je_how_rws_jagat | ORD/000074/2023-2024 | 1760/HD | 27/04/2023 | 26/06/2023 | GRAFTON TARMAC ENGINEERING AND CIVIL | 26.45 | 0 | 0 | 0
5 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Jujarsah | SM/10146 | Augmentation | Supply, Delivery & Installation of voltage correcting device & other allied works for Jujursha W/S. Sch. PH-I Howrah | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/001160/2022-2023 | 1372/HMSD | 27/07/2022 | 03/08/2022 | MAA KALI ENTERPRISE | 2.85 | 2.85 | 100 | 0
6 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Jujarsah | SM/10146 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2022-2023 | 1624/HD | 05/08/2022 | 05/08/2022 | Resource Division | 258.1 | 0 | 0 | 0
7 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Jujarsah | SM/10146 | Augmentation | Quotation Bill for New Service Connection at Jujarsah W/S. Sch.PH-III |  |  | BILL/04080/2023-2024 | 348 | 11/10/2023 | 11/10/2023 | WBSEDCL | 3.71 | 0 | 0 | 0
8 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Jujarsah | SM/10146 | Augmentation | Work Order for Laying Distribution Pipeline With FHTC of Jujarsah PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. From Section 263-307 to Section 526-533 (Part-B) | AE/SADAR | je_how_rws_jagat,JE Sadar | ORD/000367/2022-2023 | 1827/HD | 07/09/2022 | 08/06/2026 | M/S ASHIRBAD (INDIA) | 149.32 | 77.93 | 52.19 | 40
9 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Jujarsah | SM/10146 | Augmentation | Work Order for Laying Distribution Pipeline With FHTC of Jujarsah PWSS at Panchla Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. From Section Node 678-679 to Section Node 804-806 (Part-E) | AE/SADAR | je_how_rws_jagat | ORD/000339/2022-2023 | 1851/HD | 09/09/2022 | 28/03/2025 | ADITYA HAZRA | 204.49 | 33.7 | 16.48 | 30
10 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Jujarsah | SM/10146 | Augmentation | Work Order for Laying Distribution Pipeline With FHTC of Jujarsah PWSS at Panchla Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. From Section Node 110-123 to Section Node 611-613 (Part-C) | AE/SADAR | je_how_rws_jagat | ORD/000340/2022-2023 | 1852/HD | 09/09/2022 | 08/11/2022 | UNIVERSAL CORPORATION | 158.4 | 100.9 | 63.7 | 60
11 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Jujarsah | SM/10146 | Augmentation | Work Order for Laying Distribution Pipeline With FHTC of Jujarsah PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. From Section Node 248-265 to Section Node 449-453 (Part-D) | AE/SADAR | je_how_rws_jagat | ORD/000359/2022-2023 | 1819/HD | 06/09/2022 | 27/06/2026 | N. G ENGINEERING | 183.13 | 102.13 | 55.77 | 30
12 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Jujarsah | SM/10146 | Augmentation | Work Order for Construction Of 1250 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir with Rising Main Pipeline Work & Laying Distribution Pipeline & Providing FHTC (Functional Household Tap Connection) of Augmentation of Jujarsah PWSS Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. (Part-A) | AE/SADAR | je_how_rws_jagat | ORD/000392/2022-2023 | 1842/HD | 08/09/2022 | 25/06/2025 | G.B. CONSTRUCTION AND CO | 356.33 | 189.92 | 53.3 | 30
13 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Jujarsah | SM/10146 | Augmentation | Work Order for Sinking of 4 (Four) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Augmentation of Jujarshah PWSS of Panchla Block Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | je_how_rws_jagat | ORD/000692/2022-2023 | 310/HD | 20/01/2023 | 10/01/2025 | SPG ENTERPRISES | 68.81 | 0 | 0 | 0
14 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Jujarsah | SM/10146 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Jujarsah water supply scheme, T.W. No.- I & II, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000245/2022-2023 | 912/ED | 22/02/2023 | 17/06/2025 | MAA KALI ENTERPRISE | 23.16 | 0 | 0 | 50
15 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Jujarsah | SM/10146 | Augmentation | Additional distribution pipe line with Rider line and allied works at Jujarsaha PWSS at Panchla Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte. (SM/10146) | AE/SADAR | je_how_rws_jagat | ORD/000064/2024-2025 | 3099/HD | 08/07/2024 | 31/10/2025 | MA MANASA CONSTRUCTION | 176.73 | 0 | 0 | 60
16 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Jujarsah | SM/10146 | Augmentation | Quotation money deposition for new service connection at Jujarsah w/s scheme, T.W. No.-V, Dist.-Howrah under PHE Dte. Application No- 1008476183 Reference ID- 107005259 SM Code- 10146 |  |  | BILL/04959/2025-2026 |  | 17/12/2025 | 17/12/2025 | WBSEDCL | 4.02 | 0 | 0 | 0
17 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Jujarsah | SM/10146 | Augmentation | Quotation money deposition for new service connection at Jujarsah w/s scheme, T.W. No.-IV, Dist.-Howrah under PHE Dte. Application No- 1008415264 Reference ID- 106963650 SM Code- 10146 |  |  | BILL/04958/2025-2026 |  | 17/12/2025 | 17/12/2025 | WBSEDCL | 3.68 | 0 | 0 | 0
18 | HOWRAH |  | Electrical | Augmentation of Ground water based PWSS Jujarsah | SM/10146 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Jujarsah water supply scheme, T.W. No. III, IV & V, Block: Panchla, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000866/2023-2024 | 3439/ED | 11/08/2023 | 27/04/2026 | H.K.DAS & CO. | 35.18 | 0 | 0 | 60
19 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Jujarsah | SM/10146 | Augmentation | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Panchla and Uluberia-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000287/2024-2025 | 4816/HD | 19/11/2024 | 13/04/2026 | TECH VISION | 12.48 | 0 | 0 | 78
20 | HOWRAH |  | Howrah Division | Augmentation of Ground water based PWSS Jujarsah | SM/10146 | Augmentation | Supplying,fitting,fixing and erecting of Display Board at Banharishpur PWSS [SM/11723], Jujarsah PWSS [SM/10146], Samanti PWSS [SM/12562] of Panchla Block under Howrah Sadar Sub-Division ,under Howrah Division, P.H.E Dte. | AE/SADAR | JE Sadar | ORD/000996/2024-2025 | 229/HSSD | 28/02/2025 | 15/03/2025 | ABONTICA ENTERPRISE | 0.86 | 0 | 0 | 100
Total | [13 empty] | 2241.36 | 507.43 | 22.64