## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Bagnan-I | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. | SM/11000 | New | Work Order for Preparation of DPR for new piped water supply scheme of Haturie Kandarpur PWSS, Bagnan-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu | JE/RWS/Bagnan I | ORD/000447/2021-2022 | 248/HD | 07/02/2022 | 22/02/2022 | STEELCONC AND ASSOCIATES | 3.61 | 3.61 | 100 | 0
2 | HOWRAH | Bagnan-I | Central Drilling | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. | SM/11000 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 300 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR SHYAMPUR W/S SCHEME (REPLACEMENT TW-I), BASANTI BLOCK UNDER SOUTH 24 PGS DISTRICT, CDD, PHE DTE. |  |  | ORD/000110/2022-2023 | 57/CDD | 08/04/2022 | 08/05/2022 | PADMA ENGINEERING & CO. | 14.55 | 12.42 | 85.41 | 0
3 | HOWRAH | Bagnan-I | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. | SM/11000 | New | Material Requisition To Resource Division |  |  | RTOR000046/2022-2023 | 2639/HD | 09/12/2022 | 09/12/2022 | Resource Division | 46.12 | 0 | 0 | 0
4 | HOWRAH | Bagnan-I | Electrical | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. | SM/11000 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Haturie-Kandarpur water supply scheme, T.W. No.- I, II & III, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000157/2022-2023 | 3510/ED | 30/12/2022 | 30/03/2023 | MAHADEV ENTERPRISE | 32.2 | 31.14 | 96.73 | 40
5 | HOWRAH | Bagnan-I | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. | SM/11000 | New | Work Order for Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at 2nd TW site at Haturie Kandarpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000826/2022-2023 | 1055/HD | 15/03/2023 | 13/06/2023 | SR TRADING CORPORATION | 7.18 | 7.18 | 100 | 100
6 | HOWRAH | Bagnan-I | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. | SM/11000 | New | Work Order for Sinking of 3 (Three) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Haturia Kandarpur PWSS of Bagnan-I Block Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/USD | ORD/000602/2022-2023 | 2718/HD | 14/12/2022 | 12/02/2023 | LOKENATH ENTERPRISES | 54.06 | 52.07 | 96.31 | 100
7 | HOWRAH | Bagnan-I | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. | SM/11000 | New | Work Order for Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at Head Work Site at Haturie Kandarpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000823/2022-2023 | 1052/HD | 15/03/2023 | 13/06/2023 | M/S M.R ENTERPRISE | 7.14 | 7.14 | 100 | 100
8 | HOWRAH | Bagnan-I | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. | SM/11000 | New | Work Order for Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at 3rd TW site at Haturie Kandarpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000828/2022-2023 | 1057/HD | 15/03/2023 | 13/06/2023 | MARUTI CONSTRUCTION | 7.19 | 6.92 | 96.27 | 100
9 | HOWRAH | Bagnan-I | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. | SM/11000 | New | Material Requisition To Resource Division |  |  | RTOR000023/2022-2023 | 1624/HD | 05/08/2022 | 05/08/2022 | Resource Division | 45.57 | 0 | 0 | 0
10 | HOWRAH | Bagnan-I | Electrical | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. | SM/11000 | New | New service connection at Haturie Kandarpur W/S. Sch. PH-II |  |  | BILL/00847/2022-2023 | 171 | 28/02/2023 | 28/02/2023 | WBSEDCL | 0.55 | 0 | 0 | 0
11 | HOWRAH | Bagnan-I | Electrical | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. | SM/11000 | New | NEW SERVICE CONNECTION FOR HATURIA KANDARPUR PWSS, PUMP HOUSE-III |  |  | BILL/02061/2023-2024 | 109 | 19/07/2023 | 19/07/2023 | WBSEDCL | 0.76 | 0 | 0 | 0
12 | HOWRAH | Bagnan-I | Electrical | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. | SM/11000 | New | New service connection at Haturie Kandarpur W/S. Sch. PH-I |  |  | BILL/00846/2022-2023 | 171 | 28/02/2023 | 28/02/2023 | WBSEDCL | 0.55 | 0 | 0 | 0
13 | HOWRAH | Bagnan-I | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. | SM/11000 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) of Haturia Kandarpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Natibpur (Jl-52) (Part-D) | AE/Ulu | JE/USD | ORD/000415/2022-2023 | 2058/HD | 29/09/2022 | 13/11/2022 | MAA TARA CONSTRUCTION | 61.1 | 57.31 | 93.81 | 100
14 | HOWRAH | Bagnan-I | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. | SM/11000 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) of Haturia Kandarpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza- JOTE BIRESWAR(Jl-51) (Part-C) | AE/Ulu | JE/USD | ORD/000414/2022-2023 | 2057/HD | 29/09/2022 | 19/12/2024 | NIRMAL UDYOG | 74.66 | 38.61 | 51.71 | 100
15 | HOWRAH | Bagnan-I | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. | SM/11000 | New | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) of Haturia Kandarpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Singara (Jl-53) (Part-E) | AE/Ulu | JE/RWS/Bagnan I,JE/USD | ORD/000416/2022-2023 | 2059/HD | 29/09/2022 | 13/11/2022 | SADHURHAT CO OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 39.47 | 38.34 | 97.12 | 100
16 | HOWRAH | Bagnan-I | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. | SM/11000 | New | Work Order for Interconnection for 2nd TW and 1st Tube well (HW site) at Haturia Kandarpopur Piped Water Supply scheme in Bagnan-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000417/2022-2023 | 2060/HD | 29/09/2022 | 29/10/2022 | ASHOKE ENGINEERING WORKS | 15.63 | 5.78 | 36.95 | 95
17 | HOWRAH | Bagnan-I | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. | SM/11000 | New | Work Order for Laying Additional Distribution System(HDPE & DI) & providing Functional Household Tap Connections (FHTC) of Haturia Kandarpur PWSS within Mouza-Singara(53) of Haturia-I GP under Bagnan-I block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000820/2022-2023 | 1049/HD | 15/03/2023 | 13/06/2023 | SADHURHAT CO OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 11.44 | 10.89 | 95.19 | 100
18 | HOWRAH | Bagnan-I | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. | SM/11000 | New | Additional Laying Distribution system (HDPE & DI) & providing Functional Household Tap connection (FHTC) of Haturia Kandarpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000312/2023-2024 | 4341/HD | 04/12/2023 | 02/02/2024 | MAA TARA CONSTRUCTION | 18.77 | 18.36 | 97.85 | 100
19 | HOWRAH | Bagnan-I | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. | SM/11000 | New | Material Requisition To Resource Division |  |  | RTOR000085/2023-2024 | 170/HD | 15/01/2024 | 15/01/2024 | Resource Division | 10.47 | 0 | 0 | 0
20 | HOWRAH | Bagnan-I | Electrical | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. | SM/11000 | New | Quotation for new service connection for Ground Water Based Pwss Haturie Kandarpur, in the district Howrah under Electrical Division, PHE Dte. Reference Id- 106616946, Application no- 1007818648 ( SM/11000) |  |  | BILL/00849/2024-2025 | 246 | 24/06/2024 | 24/06/2024 | WBSEDCL | 3.19 | 0 | 0 | 0
21 | HOWRAH | Bagnan-I | Electrical | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. | SM/11000 | New | Quotation for new service connection for Haturie Kandarpur w/s scheme in the district Howrah under Electrical Division, PHE Dte. Reference Id- 106616939, Application no- 1007818619 |  |  | BILL/00848/2024-2025 | 249 | 24/06/2024 | 24/06/2024 | WBSEDCL | 16.08 | 0 | 0 | 0
22 | HOWRAH | Bagnan-I | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. | SM/11000 | New | Construction of 450 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), pipe connection, Laying Distribution System (HDPE & DI) & providing Functional Household Tap Connection (FHTC) for HATURIA KANDARPUR PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Haturia Kandarpur (Jl-49) & Khanpur (Jl-50)) [No. of FHTC = 2433] | AE/Ulu | JE/USD | ORD/000194/2023-2024 | 3197/HD | 04/09/2023 | 31/01/2026 | B.M. ENTERPRISE | 481.61 | 229.93 | 47.74 | 65
23 | HOWRAH | Bagnan-I | Howrah Division | Haturie kandarpur Piped Water Supply Scheme Block: Bagnan-I, District - Howrah. | SM/11000 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte.(Phase-II). | AE HQ |  | ORD/000199/2025-2026 | 3670/HD | 02/09/2025 | 01/11/2025 | TECH VISION | 21.25 | 0 | 0 | 0
Total | [13 empty] | 973.14 | 519.71 | 53.41