## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH | Bagnan-I | Howrah Division | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. | SM/11007 | New | Work Order for Preparation of DPR for new piped water supply scheme of Murgaberia PWSS, Bagnan-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu | JE/RWS/Bagnan I | ORD/000448/2021-2022 | 249/HD | 07/02/2022 | 22/02/2022 | STEELCONC AND ASSOCIATES | 3.11 | 0 | 0 | 0
2 | HOWRAH | Bagnan-I | Howrah Division | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. | SM/11007 | New | Material Requisition To Resource Division |  |  | RTOR000045/2022-2023 | 2639/HD | 09/12/2022 | 09/12/2022 | Resource Division | 32.55 | 0 | 0 | 0
3 | HOWRAH | Bagnan-I | Electrical | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. | SM/11007 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Murgaberia water supply scheme, T.W. No.- I & II, Block: Bagnan-I, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000139/2022-2023 | 3516/ED | 30/12/2022 | 30/03/2023 | BIJAN ENTERPRISE | 20.25 | 0 | 0 | 70
4 | HOWRAH | Bagnan-I | Howrah Division | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. | SM/11007 | New | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Murgaberia PWSS at Bagnan-I Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE/RWS/Bagnan I | ORD/000395/2022-2023 | 1971/HD | 22/09/2022 | 01/11/2022 | ACME CONSTRUCTION | 35.36 | 0 | 0 | 0
5 | HOWRAH | Bagnan-I | Howrah Division | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. | SM/11007 | New | Work Order for Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at Head Work Site at Murgaberia PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000824/2022-2023 | 1053/HD | 15/03/2023 | 13/06/2023 | KALIDAS ENTERPRISE | 7.18 | 0 | 0 | 100
6 | HOWRAH | Bagnan-I | Howrah Division | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. | SM/11007 | New | Work Order for Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at 2nd TW site at Murgaberia PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000827/2022-2023 | 1056/HD | 15/03/2023 | 13/06/2023 | GRAVITA ENTERPRISE | 7.17 | 0 | 0 | 100
7 | HOWRAH | Bagnan-I | Howrah Division | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. | SM/11007 | New | Material Requisition To Resource Division |  |  | RTOR000022/2022-2023 | 1624/HD | 05/08/2022 | 05/08/2022 | Resource Division | 36.79 | 0 | 0 | 0
8 | HOWRAH | Bagnan-I | Electrical | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. | SM/11007 | New | Quotation Bill for New Service Connection at Murgaberia W/S. Sch. PH-I |  |  | BILL/00848/2022-2023 | 170 | 28/02/2023 | 28/02/2023 | WBSEDCL | 0.55 | 0 | 0 | 0
9 | HOWRAH | Bagnan-I | Electrical | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. | SM/11007 | New | Quotation Bill for New service connection at Murgaberia W/S. Sch. PH-II |  |  | BILL/00849/2022-2023 | 170 | 28/02/2023 | 28/02/2023 | WBSEDCL | 0.55 | 0 | 0 | 0
10 | HOWRAH | Bagnan-I | Howrah Division | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. | SM/11007 | New | Laying Distribution System(UPVC & DI) & providing Functional Household Tap Connection (FHTC) of Murgaberia PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte.(Mouza-Chak monohar(54) | AE/Ulu | JE/USD | ORD/000330/2023-2024 | 4469/HD | 12/12/2023 | 25/02/2024 | M/S. GHOSH CONSTRUCTION | 74.17 | 0 | 0 | 100
11 | HOWRAH | Bagnan-I | Howrah Division | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. | SM/11007 | New | Restoration of Road at Murgaberia under Murgaberia PWSS under Uluberia Sub-Division of Howrah Division,PHEDte. | AE/Ulu | JE/USD | ORD/000017/2024-2025 | 239/AE/USD | 10/06/2024 | 25/07/2024 | BISWAJIT BAG | 19.58 | 0 | 0 | 100
12 | HOWRAH | Bagnan-I | Howrah Division | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. | SM/11007 | New | Material Requisition To Resource Division |  |  | RTOR000084/2023-2024 | 170/HD | 15/01/2024 | 15/01/2024 | Resource Division | 5.73 | 0 | 0 | 0
13 | HOWRAH | Bagnan-I | Howrah Division | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. | SM/11007 | New | Work Order for Construction of 300 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Design including Soil Investigation, Laying Distribution Pipeline & Providing FHTC (1350 nos ) for Murgaberia PWSS of Bagnan-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-I) | AE/Ulu | JE/USD | ORD/000589/2022-2023 | 2649/HD | 09/12/2022 | 01/12/2025 | B.B.C ENTERPRISE | 338.67 | 0 | 0 | 60
14 | HOWRAH | Bagnan-I | Howrah Division | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. | SM/11007 | New | Additional Laying distribution system at Chakmanohar mouza under Murgaberia PWSS of Bagnan-I Block of Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000117/2024-2025 | 3883/HD | 05/09/2024 | 18/01/2025 | MANIRUL ISLAM | 17.29 | 0 | 0 | 100
15 | HOWRAH | Bagnan-I | Howrah Division | Murgaberia Piped Water Supply Scheme Block- Bagnan-I, Howrah. | SM/11007 | New | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000286/2024-2025 | 4815/HD | 19/11/2024 | 17/02/2025 | TECH VISION | 12.67 | 0 | 0 | 100
Total | [13 empty] | 611.61 | 0 | 0