## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block | SM/11159 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000057/2022-2023 | 2839/HD | 23/12/2022 | 23/12/2022 | Resource Division | 20.31 | 0 | 0 | 0
2 | HOWRAH |  | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block | SM/11159 | Augmentation | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Makardah PWSS Under Domjur Block of Howrah Sadar Sub-Division PHE Dte. | AE/SADAR |  | ORD/000230/2022-2023 | 83/HSSD | 12/08/2022 | 27/08/2022 | APEX ENGINEERING | 4.15 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block | SM/11159 | Augmentation | Work Order for Land Development work at Makardaha Head Work Site For Makardaha PWSS under Howrah Divnision PHE Dte. | AE/SADAR |  | ORD/000066/2023-2024 | 1927/HD | 10/05/2023 | 09/07/2023 | NATURAL RESOURCES CONSORTIUM | 2.97 | 2.96 | 99.79 | 100
4 | HOWRAH |  | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block | SM/11159 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000089/2022-2023 | 593/HD | 13/02/2023 | 13/02/2023 | Resource Division | 53.91 | 0 | 0 | 0
5 | HOWRAH |  | Electrical | Makardaha PWSS with provision of FHTC in connection of Domjur Block | SM/11159 | Augmentation | Quotation Bill for for New Service Connection at Makardaha W/S. Sch. PH-II |  |  | BILL/04314/2023-2024 | 424 | 17/11/2023 | 17/11/2023 | WBSEDCL | 9.12 | 0 | 0 | 0
6 | HOWRAH |  | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block | SM/11159 | Augmentation | Augmentation of Makardaha |  |  | BILL/00278/2022-2023 | BP-2022-23-534 | 09/03/2023 | 09/03/2023 | WBSEDCL | 0.66 | 0 | 0 | 0
7 | HOWRAH |  | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block | SM/11159 | Augmentation | Work Order for Laying Distribution System Pipeleine (Node No. 503 to 662 & 669) & FHTC work [Mouza: Ankurhati (CT) : PART-2] for Augmentation of Makardah PWSS at Domjur Block under Howrah Division P.H.E Dte. | AE/SADAR | je6/maad,JE Sadar | ORD/000511/2022-2023 | 2382/HD | 18/11/2022 | 18/12/2022 | ANUSKA ENTERPRISE | 86.39 | 75.8 | 87.75 | 90
8 | HOWRAH |  | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block | SM/11159 | Augmentation | Work Order for Laying Distribution System Pipeleine (Node No. 232 to 357) & FHTC work [Mouza: Jhaluarber] for Augmentation of Makardah PWSS at Domjur Block under Howrah Division P.H.E Dte. | AE/SADAR | je6/maad,JE Sadar | ORD/000631/2022-2023 | 2991/HD | 29/12/2022 | 28/01/2023 | QUICK CONCRETE PROJECT | 66.11 | 33.18 | 50.19 | 95
9 | HOWRAH |  | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block | SM/11159 | Augmentation | Work Order for Laying Distribution System Pipeleine (Node No. 358 to 502 & 545) & FHTC work [Mouza: Ankurhati (CT) : PART-1] for Augmentation of Makardah PWSS at Domjur Block under Howrah Division P.H.E Dte. | AE/SADAR | je6/maad | ORD/000510/2022-2023 | 2319/HD | 11/11/2022 | 11/12/2022 | MENOKA ENGINEERING WORKS | 82.16 | 38.12 | 46.4 | 70
10 | HOWRAH |  | Electrical | Makardaha PWSS with provision of FHTC in connection of Domjur Block | SM/11159 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Makardaha water supply scheme, T.W. No. III & IV, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000285/2022-2023 | 935/ED | 22/02/2023 | 23/05/2023 | GLACIER ENGINEERING CO. | 21.83 | 21.55 | 98.68 | 30
11 | HOWRAH |  | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block | SM/11159 | Augmentation | Work Order for Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Makardha PWSS at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte | AE/SADAR | je6/maad | ORD/000399/2022-2023 | 1999/HD | 26/09/2022 | 05/11/2022 | M/S SYCHROTECH INDUSTRY | 26.39 | 25.79 | 97.75 | 100
12 | HOWRAH |  | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block | SM/11159 | Augmentation | Sinking of 01 (One) No. 250 X 150 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Makardha PWSS at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR | JE Sadar | ORD/000545/2023-2024 | 805/HD | 20/02/2024 | 21/03/2024 | AUXILIARY TUBEWELL DRILLERS | 14.12 | 13.95 | 98.76 | 100
13 | HOWRAH |  | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block | SM/11159 | Augmentation | Emergency Restoration of damaged concrete road due to laying of pipe line at Ankurhati stadium of Makardaha PWSS under Howrah Sadar Sub-Division PHE Dte. | AE/SADAR | JE Sadar | ORD/000031/2024-2025 | 639/HSSD | 25/06/2024 | 25/07/2024 | UNIVERSAL CORPORATION | 2.16 | 2.09 | 96.75 | 100
14 | HOWRAH |  | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block | SM/11159 | Augmentation | Shifting of LT Cable from transformer to Makardaha pwss P.H.No.-I, on full deposite scheme , Dist.-Howrah under PHE Dte. Application No- 100000106104 Reference ID- 860298084 SM Code- 11159 |  |  | BILL/00106/2024-2025 | BP-2024-25-46 | 07/05/2024 | 07/05/2024 | WBSEDCL | 20.94 | 0 | 0 | 0
15 | HOWRAH |  | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block | SM/11159 | Augmentation | Payment for Way Leave Plan and Survey Charges Makardaha PWSS |  |  | BILL/01654/2023-2024 | BP-2023-24-737 | 27/03/2024 | 27/03/2024 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 0.14 | 0 | 0 | 0
16 | HOWRAH |  | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block | SM/11159 | Augmentation | Bill Document for Payment of Wayleave facility charges |  |  | BILL/00276/2024-2025 | BP-2024-25-154 | 08/07/2024 | 08/07/2024 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 5.01 | 0 | 0 | 0
17 | HOWRAH |  | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block | SM/11159 | Augmentation | Bill Document for Payment of Wayleave Plan & Survey charges |  |  | BILL/00159/2024-2025 | BP-2024-25-98 | 28/05/2024 | 28/05/2024 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 0.09 | 0 | 0 | 0
18 | HOWRAH |  | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block | SM/11159 | Augmentation | Bill Document for Payment of Wayleave facility charges |  |  | BILL/00114/2024-2025 | BP-2024-25-56 | 10/05/2024 | 10/05/2024 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 8.04 | 0 | 0 | 0
19 | HOWRAH |  | Electrical | Makardaha PWSS with provision of FHTC in connection of Domjur Block | SM/11159 | Augmentation | Quotation money deposition for new service connection at Makardah water supply scheme , P.H No-III, Dist- Howrah under ED PHED. App. No.-1007939058 SM/11159 |  |  | BILL/01647/2024-2025 | 409 | 21/08/2024 | 21/08/2024 | WBSEDCL | 13.4 | 0 | 0 | 0
20 | HOWRAH |  | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block | SM/11159 | Augmentation | Work Order for Laying of Distribution Pipeline (Node No. 663 To 944) & FHTC work [Mouza: Ankurhati (CT) : PART-3] for Augmentation of Makardah PWSS at Domjur Block under Howrah Division, P. H. E. Dte. (Part-7) | AE/SADAR | je6/maad,JE Sadar | ORD/000427/2022-2023 | 2100/HD | 12/10/2022 | 02/01/2025 | UNIVERSAL CORPORATION | 153.73 | 72.51 | 47.17 | 15
21 | HOWRAH |  | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block | SM/11159 | Augmentation | Work Order for Construction of 3 (three) nos of Boundary Wall for Augmentation of Makardah PWSS at Domjur Block under Howrah Division PHE Dte | AE/SADAR | je6/maad,JE Sadar | ORD/000404/2022-2023 | 1991/HD | 26/09/2022 | 30/11/2024 | JOY GURU TRADING | 17.93 | 0 | 0 | 60
22 | HOWRAH |  | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block | SM/11159 | Augmentation | Work Order for Construction of 450 cum Capacity OHR, Rising Main Pipe line, Laying of Distribution Pipeline (Node No. R-1 To 231) & FHTC work [Mouza: Makardah (CT)] for Augmentation of Makardah PWSS at Domjur Block under Howrah Division, P. H. E. Dte. (Part-3) | AE/SADAR | je6/maad,JE Sadar | ORD/000431/2022-2023 | 2099/HD | 12/10/2022 | 02/06/2025 | NATURAL RESOURCES CONSORTIUM | 349.1 | 176.92 | 50.68 | 50
23 | HOWRAH |  | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block | SM/11159 | Augmentation | Work Order for Construction of 3 (Three) Nos. of Pump House for Augmentation of Makardah PWSS at Domjur Block under Howrah Division P.H.E Dte. | AE/SADAR | je6/maad,JE Sadar | ORD/000403/2022-2023 | 1990/HD | 26/09/2022 | 10/11/2022 | S.B. ENTERPRISE | 17.72 | 0 | 0 | 100
24 | HOWRAH |  | Electrical | Makardaha PWSS with provision of FHTC in connection of Domjur Block | SM/11159 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Makardaha water supply scheme, T.W. No.- New, Block: Domjur, District- Howrah under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000860/2023-2024 | 3432/ED | 11/08/2023 | 01/07/2025 | GLACIER ENGINEERING CO. | 10.75 | 0 | 0 | 50
25 | HOWRAH |  | Howrah Division | Makardaha PWSS with provision of FHTC in connection of Domjur Block | SM/11159 | Augmentation | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Piped Water Supply Schemes in different Blocks in the District of Howrah under Howrah Division, PHE Dte. | AE HQ | je_blk_ballyjag_how | ORD/000111/2024-2025 | 3730/HD | 29/08/2024 | 28/09/2024 | HORIZEN | 4.93 | 0 | 0 | 100
Total | [13 empty] | 992.06 | 462.88 | 46.66