## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOWRAH |  | Howrah Division | Rampur PWSS | SM/11168 | Augmentation | Preparation of DPR for augmentation of existing piped water supply scheme of Rampur PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000266/2021-2022 | 2148/HD | 01/12/2021 | 16/12/2021 | APEX ENGINEERING | 3.17 | 6.35 | 200 | 0
2 | HOWRAH |  | Howrah Division | Rampur PWSS | SM/11168 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000036/2022-2023 | 2113/HD | 09/11/2022 | 09/11/2022 | Resource Division | 10.38 | 0 | 0 | 0
3 | HOWRAH |  | Howrah Division | Rampur PWSS | SM/11168 | Augmentation | Repairing of Pump house and Store room and ancillary work of HW site and 2nd TW site at Rampur w/s scheme at Udaynarayanpur Block under Uluberia Sub-Division, of Howrah Division P.H.E Dte. | AE/Ulu |  | ORD/000274/2022-2023 | 347/AE/USD | 22/08/2022 | 06/10/2022 | S RAHA ENTERPRISE | 3.5 | 3.49 | 99.62 | 0
4 | HOWRAH |  | Howrah Division | Rampur PWSS | SM/11168 | Augmentation | Work Order for Repairing of OHR including land development of Rampur PWSS scheme in Udayanarayanpur Block, under Howrah Division P.H.E. Dte. Dte. | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000773/2022-2023 | 790/H.D | 27/02/2023 | 29/03/2023 | MAITY CONSTRUCTIONS | 6.6 | 6.24 | 94.49 | 100
5 | HOWRAH |  | Howrah Division | Rampur PWSS | SM/11168 | Augmentation | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Augmentation of Rampur Water Supply Scheme in Udaynarayanpur Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-A) (Section-A) | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000341/2022-2023 | 1853/HD | 09/09/2022 | 08/11/2022 | DEV DAS SHAW | 144.42 | 141.01 | 97.64 | 40
6 | HOWRAH |  | Howrah Division | Rampur PWSS | SM/11168 | Augmentation | Work order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Rampur Water Supply Scheme In Udaynarayanpur Block under Howrah Division, PHE Dte. (Part-D) | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000288/2022-2023 | 225/RWS | 01/09/2022 | 01/10/2022 | MAITY CONSTRUCTIONS | 4.75 | 4.38 | 92.15 | 100
7 | HOWRAH |  | Howrah Division | Rampur PWSS | SM/11168 | Augmentation | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Rampur Water Supply Scheme In Udaynarayanpur Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-C) | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000237/2022-2023 | 1711/HD | 24/08/2022 | 23/09/2022 | NANDY UDYOG | 9.36 | 7.59 | 81.06 | 50
8 | HOWRAH |  | Howrah Division | Rampur PWSS | SM/11168 | Augmentation | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Rampur Water Supply Scheme In Udaynarayanpur Block under Howrah Division, PHE Dte. (Part-E) | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000289/2022-2023 | 226 / RWS | 01/09/2022 | 01/10/2022 | MAITY CONSTRUCTIONS | 4.75 | 4.38 | 92.21 | 100
9 | HOWRAH |  | Howrah Division | Rampur PWSS | SM/11168 | Augmentation | Work Order for Laying Additional Distribution Pipe Lines With Allied Works of leftout area for RAMPUR Water Supply Scheme In Udaynarayanpur Block under Howrah Division, PHE Dte.(Part-A) | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000062/2023-2024 | 1867/HD | 03/05/2023 | 02/07/2023 | DEV DAS SHAW | 26.22 | 26.17 | 99.82 | 100
10 | HOWRAH |  | Howrah Division | Rampur PWSS | SM/11168 | Augmentation | Work Order for Laying Additional Distribution Pipe Lines With Allied Works of leftout area for RAMPUR Water Supply Scheme In Udaynarayanpur Block under Howrah Division, PHE Dte.(Part-B) | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000072/2023-2024 | 1933/HD | 10/05/2023 | 09/07/2023 | CONSTRUCTION CORNER | 29.82 | 29.55 | 99.12 | 50
11 | HOWRAH |  | Howrah Division | Rampur PWSS | SM/11168 | Augmentation | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Augmentation of Rampur Water Supply Scheme In Udaynarayanpur Block under Uluberia Sub-Division under Howrah Division, PHE Dte.(Part-B) (Section-A) | AE/RWS | JE/RWS/Udaynaryanpur,JE Sadar | ORD/000358/2022-2023 | 1909/HD | 15/09/2022 | 30/10/2022 | CONSTRUCTION CORNER | 114.82 | 114.14 | 99.4 | 35
12 | HOWRAH |  | Howrah Division | Rampur PWSS | SM/11168 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2024-2025 | 3884/HD | 05/09/2024 | 05/09/2024 | Resource Division | 7.39 | 0 | 0 | 0
13 | HOWRAH |  | Howrah Division | Rampur PWSS | SM/11168 | Augmentation | Continuous work order for hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/10/2025 to 30/11/2025) | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000215/2025-2026 | 321/RWS | 25/09/2025 | 25/11/2025 | SANJIB BARMAN | 0.79 | 0 | 0 | 0
Total | [13 empty] | 365.98 | 343.3 | 93.8